## Dashboard
Drilling to Date
DD
| Met | 27
| Geotech | 14
| A Vein DD | 7
| Infill | 5
| G Vein DD | 4
RC
| A Vein RC | 42
| Infill | 38
| G Vein RC | 38
|  |  | Actual | Monthly
S042 | Drilling | vendor | 1223 |  | Red

## Pivot_Summary (hidden)
Rig 38
Row Labels | Sum of Total Costs
| 3780 | Type | Total Cost
DDRD | 48065.74 | DDRD | 117511.39
GT | 156449.69 | GT | 292723.41
Index | 37 | MET | 796476.73
MET | 256886.28 | INF | 474557.5
(blank) | 0 | EXT | 208987.98
Grand Total | 465218.71
|  | Total | 1890257.01
Rig 41
Row Labels | Sum of Total Costs
DDRD | 69445.65
GT | 136273.72
Index | 37
MET | 539590.45
2025-06-13 17:02 | 0
2025-06-14 17:02 | 0
2025-06-15 17:02 | 0
2025-06-16 17:02 | 0
(blank) | #VALUE!
Grand Total | #VALUE!
Strike
Row Labels | Sum of Total Costs
EXT | 208987.98
Index | 28
INF | 474557.5
(blank) | 19201.02
Grand Total | 702774.5

## Scheduler
|  |  | Schedule |  |  | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Adequate? | Planned | Actual | Activity Type | Rig | Notes | time axis 2025-05-08 to 2025-10-25
GENERAL EARTH WORKS | [5 empty] | 2025-05-08: Task 1 - ACCESS; 2025-05-15: Task 2 - RingRoad; 2025-05-22: Task 3 - Station Link; 2025-07-06: Task 5 - Test Pits; 2025-08-25: Task 7 - Rehab
[5 empty] | Survey | 2025-05-08: Initial Survey; 2025-07-02: Collar Survey; 2025-08-02: Collar Survey; 2025-09-06: Collar Survey
|  |  | DDR1 |  | Drilling Phase | [41 empty] | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | Met | GeoT* | GeoT* | GeoT* | GeoT* | GeoT* | GeoT* | GeoT* | GeoT* | GeoT* | Met | Met | Met | Met | Met | Met | Met | Met | GT | GT | GT | GT | GT | DDRD | DDRD | DDRD | Met | Met | Met | Met | Inf | Inf | Inf | Inf | ExtG | ExtG | ExtG | ExtG | Inf | Inf | Inf | Inf | Inf | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met | Additonal Met
TRUE | 2045 | 3260 | Drilling | DD PQ -> HQ | Predicted | [41 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 15 | 15 | 15 | 15 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
|  |  | DR41 |  | Actual | [40 empty] | 0 | 51.5 | 56 | 52.5 | 21.4 | 58.6 | 30 | 32.6 | 23 | 65.1 | 43.9 | 36.1 | 45.4 | 21 | 20.6 | 34.4 | 15.8 | 30.4 | 38.5 | 26.2 | 36.8 | 32.6 | 21 | 27.5 | 28.2 | 31.8 | 17.5 | 36.7 | 24.1 | 33 | 32.2 | 33.8 | 60.6 | 49.4 | 60.6 | 49.4 | 42.4 | 60 | 36.1 | 60 | 51.5 | 39.2 | 16.6 | 22.4 | 43.9 | 48.4 | 24.6 | 49.7 | 29.8 | 24.3 | 63.7 | 28.7 | 64.8 | 45.7 | 59.3 | 44.9 | 44.1 | 7.2 | 44.4 | 30 | 30.8 | 66.4 | 66 | 69 | 33 | 57.5 | 16.5 | 72.7 | 46.8 | 68 | 51 | 30 | 35.9 | 72.7 | 21.4 | 42 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30.4 | 32.5 | 0.5 | 33 | 13.6 | 30.6 | 27.7 | 26.7 | 15.5 | 30 | 22.2 | 28.8 | 23.5 | 12.6 | 29.7 | 24.3 | 24 | 29.4 | 5.9 | 12.6 | 27 | 48 | 48.4 | 31.2 | 37 | 32.7 | 27.2 | 6.8 | 10.9 | 12 | 4.7 | 39 | 8.9 | 27 | 21 | 21 | 22.7 | 30.1 | 0 | 46.1 | 37 | 29.7
[5 empty] | Difference | [40 empty] | 0 | 26.5 | 31 | 27.5 | -3.6 | 33.6 | 5 | 7.6 | -2 | 40.1 | 18.9 | 11.1 | 20.4 | -4 | -4.4 | 9.4 | -9.2 | 5.4 | 13.5 | 1.2 | 11.8 | 7.6 | -4 | 2.5 | 3.2 | 6.8 | -7.5 | 11.7 | -0.9 | 8 | 7.2 | 8.8 | 30.6 | 19.4 | 30.6 | 19.4 | 12.4 | 30 | 6.1 | 30 | 21.5 | 14.2 | -8.4 | -2.6 | 18.9 | 23.4 | -0.4 | 24.7 | 4.8 | -5.7 | 33.7 | -1.3 | 34.8 | 15.7 | 29.3 | 14.9 | 14.1 | -17.8 | 19.4 | 5 | 5.8 | 36.4 | 36 | 39 | 3 | 27.5 | -13.5 | 42.7 | 16.8 | 38 | 21 | 0 | 5.9 | 42.7 | -3.6 | 17 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 5.4 | 7.5 | -14.5 | 18 | -1.4 | 15.6 | 2.7 | 1.7 | -9.5 | 5 | -2.8 | 3.8 | -1.5 | -12.4 | 4.7 | -0.7 | -1 | 4.4 | -19.1 | -12.4 | 2 | 23 | 23.4 | 6.2 | 12 | 7.7 | 2.2 | -18.2 | -14.1 | -13 | -20.3 | 14 | -16.1 | 2 | -4 | -4 | -2.3 | 5.1 | -25 | 21.1 | 12 | 4.7
[5 empty] | Cumulative Difference | [40 empty] | 0 | 26.5 | 57.5 | 85 | 81.4 | 115 | 120 | 127.6 | 125.6 | 165.7 | 184.6 | 195.7 | 216.1 | 212.1 | 207.7 | 217.1 | 207.9 | 213.3 | 226.8 | 228 | 239.8 | 247.4 | 243.4 | 245.9 | 249.1 | 255.9 | 248.4 | 260.1 | 259.2 | 267.2 | 274.4 | 283.2 | 313.8 | 333.2 | 363.8 | 383.2 | 395.6 | 425.6 | 431.7 | 461.7 | 483.2 | 497.4 | 489 | 486.4 | 505.3 | 528.7 | 528.3 | 553 | 557.8 | 552.1 | 585.8 | 584.5 | 619.3 | 635 | 664.3 | 679.2 | 693.3 | 675.5 | 694.9 | 699.9 | 705.7 | 742.1 | 778.1 | 817.1 | 820.1 | 847.6 | 834.1 | 876.8 | 893.6 | 931.6 | 952.6 | 952.6 | 958.5 | 1001.2 | 997.6 | 1014.6 | 1039.6 | 1064.6 | 1089.6 | 1114.6 | 1139.6 | 1164.6 | 1189.6 | 1195 | 1202.5 | 1188 | 1206 | 1204.6 | 1220.2 | 1222.9 | 1224.6 | 1215.1 | 1220.1 | 1217.3 | 1221.1 | 1219.6 | 1207.2 | 1211.9 | 1211.2 | 1210.2 | 1214.6 | 1195.5 | 1183.1 | 1185.1 | 1208.1 | 1231.5 | 1237.7 | 1249.7 | 1257.4 | 1259.6 | 1241.4 | 1227.3 | 1214.3 | 1194 | 1208 | 1191.9 | 1193.9 | 1189.9 | 1185.9 | 1183.6 | 1188.7 | 1163.7 | 1184.8 | 1196.8 | 1201.5
[5 empty] | 7 Day rolling average | 2025-06-23: 38.5714; 2025-06-30: 38.1571; 2025-07-07: 28.9571; 2025-07-14: 27.9; 2025-07-21: 41.9571; 2025-07-28: 48.3714; 2025-08-04: 33.6286; 2025-08-11: 47.3429; 2025-08-18: 41.2714; 2025-08-25: 51.6429; 2025-09-01: 43.2857; 2025-09-08: 47.2; 2025-09-15: 23.5143; 2025-09-22: 23.1857; 2025-09-29: 24.4571; 2025-10-06: 27.7429; 2025-10-13: 19.0857; 2025-10-20: 27.6
Enabling Earthwork's Task | [5 empty] | 2025-05-25: Task 4.1 - Prelim Pad Prep; 2025-05-26: Task 4.1 - Prelim Pad Prep; 2025-05-27: Task 4.1 - Prelim Pad Prep; 2025-06-06: Task 4.1 - Prelim Pad Prep; 2025-06-07: Task 4.1 - Prelim Pad Prep; 2025-06-08: Task 4.1 - Prelim Pad Prep
TRUE | 13 | 15 | Earthworks |  |  | 2025-05-25: 2.5; 2025-05-26: 2.5; 2025-05-27: 2.5; 2025-06-06: 2.5; 2025-06-07: 2.5; 2025-06-08: 2.5; 2025-10-05: task 7; 2025-10-06: task 7; 2025-10-07: task 7; 2025-10-08: task 7; 2025-10-09: task 7; 2025-10-10: task 7; 2025-10-11: task 7; 2025-10-12: task 7; 2025-10-13: task 7; 2025-10-14: task 7; 2025-10-15: task 7; 2025-10-16: task 7; 2025-10-17: task 7; 2025-10-18: task 7; 2025-10-19: task 7; 2025-10-20: task 7; 2025-10-21: task 7; 2025-10-22: task 7; 2025-10-23: task 7; 2025-10-24: task 7; 2025-10-25: task 7
|  |  | DDR2 |  | Drilling Phase | 2025-07-08: Met; 2025-07-09: Met; 2025-07-10: Met; 2025-07-11: Met; 2025-07-12: Met; 2025-07-13: Met; 2025-07-14: Met; 2025-07-15: Met; 2025-07-16: Met; 2025-07-17: Met; 2025-07-18: Met; 2025-07-19: Met; 2025-07-20: GeoT *; 2025-07-21: GeoT *; 2025-07-22: GeoT *; 2025-07-23: Met; 2025-07-24: Met; 2025-07-25: GeoT *; 2025-07-26: GeoT *; 2025-07-27: GeoT *; 2025-07-28: GeoT *; 2025-07-29: GeoT *; 2025-07-30: GeoT *; 2025-07-31: GeoT *; 2025-08-01: Met; 2025-08-02: Met; 2025-08-03: Met; 2025-08-04: Met; 2025-08-05: Met; 2025-08-06: Met; 2025-08-07: Met; 2025-08-08: ExtA; 2025-08-09: ExtA; 2025-08-10: ExtA; 2025-08-11: GT; 2025-08-12: ExtA; 2025-08-13: ExtA; 2025-08-14: ExtA; 2025-08-15: ExtA; 2025-08-16: Inf; 2025-08-17: Inf; 2025-08-18: ExtG; 2025-08-19: ExtG; 2025-08-20: ExtG; 2025-08-21: Inf; 2025-08-22: Inf; 2025-08-23: Inf; 2025-08-24: Inf; 2025-08-25: Inf; 2025-08-26: Inf; 2025-08-27: Inf; 2025-08-28: Inf; 2025-08-29: Inf; 2025-08-30: Inf; 2025-08-31: Inf; 2025-09-01: Inf; 2025-09-02: Inf; 2025-09-03: Inf; 2025-09-04: Inf; 2025-09-05: Inf; 2025-09-06: Inf; 2025-09-07: Inf; 2025-09-08: Inf; 2025-09-09: ExtA; 2025-09-10: ExtA; 2025-09-11: ExtA; 2025-09-12: ExtA; 2025-09-13: ExtA; 2025-09-14: ExtA; 2025-09-15: ExtA; 2025-09-16: ExtA; 2025-09-17: ExtA; 2025-09-18: ExtA; 2025-09-19: ExtA; 2025-09-20: ExtG; 2025-09-21: ExtG; 2025-09-22: ExtG; 2025-09-23: ExtG; 2025-09-24: ExtG; 2025-09-25: ExtG; 2025-09-26: ExtG; 2025-09-27: ExtG; 2025-09-28: ExtG; 2025-09-29: ExtG; 2025-09-30: ExtG
FALSE | 3421 | 3135 | Drilling | DD HQ | Predicted | [61 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
|  |  | DR38 |  | Actual | 2025-07-08: 26.6; 2025-07-09: 37.1; 2025-07-10: 36; 2025-07-11: 35.5; 2025-07-12: 44.1; 2025-07-13: 40.5; 2025-07-14: 40.1; 2025-07-15: 60.1; 2025-07-16: 40.8; 2025-07-17: 53.9; 2025-07-18: 20.9; 2025-07-19: 60.7; 2025-07-20: 25.8; 2025-07-21: 43.4; 2025-07-22: 27.4; 2025-07-23: 35; 2025-07-24: 46; 2025-07-25: 7.8; 2025-07-26: 14.2; 2025-07-27: 21.3; 2025-07-28: 57.4; 2025-07-29: 29; 2025-07-30: 24; 2025-07-31: 20.2; 2025-08-01: 34.5; 2025-08-02: 45.7; 2025-08-03: 60; 2025-08-04: 22.1; 2025-08-05: 38; 2025-08-06: 34; 2025-08-07: 10.7; 2025-08-08: 23; 2025-08-09: 62.6; 2025-08-10: 27.7; 2025-08-11: 72; 2025-08-12: 22.7; 2025-08-13: 57.2; 2025-08-14: 46; 2025-08-15: 59.6; 2025-08-16: 24.5; 2025-08-17: 71.6; 2025-08-18: 37; 2025-08-19: 60.5; 2025-08-20: 48.6; 2025-08-21: 40.6; 2025-08-22: 64.5; 2025-08-23: 63.5; 2025-08-24: 62.2; 2025-08-25: 30.9; 2025-08-26: 71.9; 2025-08-27: 62.4; 2025-08-28: 39.8; 2025-08-29: 66; 2025-08-30: 22.3; 2025-08-31: DEMOB
[5 empty] | Difference | 2025-07-08: 1.6; 2025-07-09: 7.1; 2025-07-10: 11; 2025-07-11: 10.5; 2025-07-12: 19.1; 2025-07-13: 15.5; 2025-07-14: 15.1; 2025-07-15: 35.1; 2025-07-16: 10.8; 2025-07-17: 23.9; 2025-07-18: -9.1; 2025-07-19: 30.7; 2025-07-20: -4.2; 2025-07-21: 13.4; 2025-07-22: -2.6; 2025-07-23: 5; 2025-07-24: 16; 2025-07-25: -22.2; 2025-07-26: -15.8; 2025-07-27: -8.7; 2025-07-28: 27.4; 2025-07-29: -1; 2025-07-30: -6; 2025-07-31: -9.8; 2025-08-01: 4.5; 2025-08-02: 15.7; 2025-08-03: 30; 2025-08-04: -7.9; 2025-08-05: 8; 2025-08-06: 4; 2025-08-07: -19.3; 2025-08-08: -7; 2025-08-09: 32.6; 2025-08-10: -2.3; 2025-08-11: 42; 2025-08-12: -7.3; 2025-08-13: 27.2; 2025-08-14: 16; 2025-08-15: 29.6; 2025-08-16: -5.5; 2025-08-17: 41.6; 2025-08-18: 7; 2025-08-19: 30.5; 2025-08-20: 18.6; 2025-08-21: 10.6; 2025-08-22: 34.5; 2025-08-23: 33.5; 2025-08-24: 32.2; 2025-08-25: 0.9; 2025-08-26: 41.9; 2025-08-27: 32.4; 2025-08-28: 9.8; 2025-08-29: 36; 2025-08-30: -7.7; 2025-08-31: #VALUE!
[5 empty] | Cumulative Difference | 2025-07-08: 1.6; 2025-07-09: 8.7; 2025-07-10: 19.7; 2025-07-11: 30.2; 2025-07-12: 49.3; 2025-07-13: 64.8; 2025-07-14: 79.9; 2025-07-15: 115; 2025-07-16: 125.8; 2025-07-17: 149.7; 2025-07-18: 140.6; 2025-07-19: 171.3; 2025-07-20: 167.1; 2025-07-21: 180.5; 2025-07-22: 177.9; 2025-07-23: 182.9; 2025-07-24: 198.9; 2025-07-25: 176.7; 2025-07-26: 160.9; 2025-07-27: 152.2; 2025-07-28: 179.6; 2025-07-29: 178.6; 2025-07-30: 172.6; 2025-07-31: 162.8; 2025-08-01: 167.3; 2025-08-02: 183; 2025-08-03: 213; 2025-08-04: 205.1; 2025-08-05: 213.1; 2025-08-06: 217.1; 2025-08-07: 197.8; 2025-08-08: 190.8; 2025-08-09: 223.4; 2025-08-10: 221.1; 2025-08-11: 263.1; 2025-08-12: 255.8; 2025-08-13: 283; 2025-08-14: 299; 2025-08-15: 328.6; 2025-08-16: 323.1; 2025-08-17: 364.7; 2025-08-18: 371.7; 2025-08-19: 402.2; 2025-08-20: 420.8; 2025-08-21: 431.4; 2025-08-22: 465.9; 2025-08-23: 499.4; 2025-08-24: 531.6; 2025-08-25: 532.5; 2025-08-26: 574.4; 2025-08-27: 606.8; 2025-08-28: 616.6; 2025-08-29: 652.6; 2025-08-30: 644.9
[73 empty] | 37.1286 | [6 empty] | 43.6571 | [6 empty] | 29.8714
Enabling Earthwork's Task | [5 empty] | 2025-05-27: Task 4.1 - Prelim Pad Prep; 2025-05-28: Task 4.1 - Prelim Pad Prep; 2025-05-29: Task 4.1 - Prelim Pad Prep; 2025-06-09: Task 4.2 - Complete Pad Prep; 2025-06-10: Task 4.2 - Complete Pad Prep
TRUE | 29 | 33 | Earthworks |  |  | 2025-05-27: 2.5; 2025-05-28: 2.5; 2025-05-29: 2.5; 2025-06-09: 8.5; 2025-06-10: 8.5; 2025-07-07: 8.5
|  |  | RCD1 |  | Drilling Phase | 2025-06-24: ExtA; 2025-06-25: ExtA; 2025-06-26: ExtA; 2025-06-27: ExtA; 2025-06-28: ExtA; 2025-06-29: ExtA; 2025-06-30: ExtA; 2025-07-01: ExtA; 2025-07-02: ExtA; 2025-07-03: ExtA; 2025-07-04: ExtA; 2025-07-05: ExtA; 2025-07-06: ExtA; 2025-07-07: ExtA; 2025-07-08: ExtA; 2025-07-09: ExtA; 2025-07-10: ExtG; 2025-07-11: ExtG; 2025-07-12: ExtG; 2025-07-13: ExtG; 2025-07-14: ExtG; 2025-07-15: ExtG; 2025-07-16: ExtG; 2025-07-17: ExtG; 2025-07-18: ExtG; 2025-07-19: ExtG; 2025-07-20: ExtG; 2025-07-21: ExtG; 2025-07-22: ExtG; 2025-07-23: ExtG; 2025-07-24: ExtG; 2025-07-25: ExtG; 2025-07-26: ExtG; 2025-07-27: Inf; 2025-07-28: Inf; 2025-07-29: Inf; 2025-07-30: Inf; 2025-07-31: Inf; 2025-08-01: Inf; 2025-08-02: Inf; 2025-08-03: Inf; 2025-08-04: Inf; 2025-08-05: Inf; 2025-08-06: Inf; 2025-08-07: Inf; 2025-08-08: Inf; 2025-08-09: Inf; 2025-08-10: Inf; 2025-08-11: Inf; 2025-08-12: Inf; 2025-08-13: Inf; 2025-08-14: Inf; 2025-08-15: Inf; 2025-08-16: Inf; 2025-08-17: Inf; 2025-08-18: Inf; 2025-08-19: Inf; 2025-08-20: Inf; 2025-08-21: Inf; 2025-08-22: Inf; 2025-08-23: Inf; 2025-08-24: Inf; 2025-08-25: Inf; 2025-08-26: Inf; 2025-08-27: Inf; 2025-08-28: Inf; 2025-08-29: Inf; 2025-08-30: Inf; 2025-08-31: Inf; 2025-09-01: Inf; 2025-09-02: Inf; 2025-09-03: Inf; 2025-09-04: Inf; 2025-09-05: Inf; 2025-09-06: Inf; 2025-09-07: Inf; 2025-09-08: Inf; 2025-09-09: Inf; 2025-09-10: Inf; 2025-09-11: Inf; 2025-09-12: Inf; 2025-09-13: Inf; 2025-09-14: Inf; 2025-09-15: Inf; 2025-09-16: Inf; 2025-09-17: Inf; 2025-09-18: Inf; 2025-09-19: Inf; 2025-09-20: Inf; 2025-09-21: Inf; 2025-09-22: Dingo; 2025-09-23: Dingo; 2025-09-24: Dingo; 2025-09-25: Dingo; 2025-09-26: Dingo
#REF! | #REF! | 14250 | Drilling | RC 1 | Predicted | 2025-06-24: 150; 2025-06-25: 150; 2025-06-26: 150; 2025-06-27: 150; 2025-06-28: 150; 2025-06-29: 150; 2025-06-30: 150; 2025-07-01: 150; 2025-07-02: 150; 2025-07-03: 150; 2025-07-04: 150; 2025-07-05: 150; 2025-07-06: 150; 2025-07-07: 150; 2025-07-08: 150; 2025-07-09: 150; 2025-07-10: 150; 2025-07-11: 150; 2025-07-12: 150; 2025-07-13: 150; 2025-07-14: 150; 2025-07-15: 150; 2025-07-16: 150; 2025-07-17: 150; 2025-07-18: 150; 2025-07-19: 150; 2025-07-20: 150; 2025-07-21: 150; 2025-07-22: 150; 2025-07-23: 150; 2025-07-24: 150; 2025-07-25: 150; 2025-07-26: 150; 2025-07-27: 150; 2025-07-28: 150; 2025-07-29: 150; 2025-07-30: 150; 2025-07-31: 150; 2025-08-01: 150; 2025-08-02: 150; 2025-08-03: 150; 2025-08-04: 150; 2025-08-05: 150; 2025-08-06: 150; 2025-08-07: 150; 2025-08-08: 150; 2025-08-09: 150; 2025-08-10: 150; 2025-08-11: 150; 2025-08-12: 150; 2025-08-13: 150; 2025-08-14: 150; 2025-08-15: 150; 2025-08-16: 150; 2025-08-17: 150; 2025-08-18: 150; 2025-08-19: 150; 2025-08-20: 150; 2025-08-21: 150; 2025-08-22: 150; 2025-08-23: 150; 2025-08-24: 150; 2025-08-25: 150; 2025-08-26: 150; 2025-08-27: 150; 2025-08-28: 150; 2025-08-29: 150; 2025-08-30: 150; 2025-08-31: 150; 2025-09-01: 150; 2025-09-02: 150; 2025-09-03: 150; 2025-09-04: 150; 2025-09-05: 150; 2025-09-06: 150; 2025-09-07: 150; 2025-09-08: 150; 2025-09-09: 150; 2025-09-10: 150; 2025-09-11: 150; 2025-09-12: 150; 2025-09-13: 150; 2025-09-14: 150; 2025-09-15: 150; 2025-09-16: 150; 2025-09-17: 150; 2025-09-18: 150; 2025-09-19: 150; 2025-09-20: 150; 2025-09-21: 150; 2025-09-22: 150; 2025-09-23: 150; 2025-09-24: 150; 2025-09-25: 150; 2025-09-26: 150
[5 empty] | Actual | 2025-06-24: 46; 2025-06-25: 100; 2025-06-26: 160; 2025-06-27: 206; 2025-06-28: 188; 2025-06-29: 212; 2025-06-30: 181; 2025-07-01: 148; 2025-07-02: 187; 2025-07-03: 200; 2025-07-04: 72; 2025-07-05: 118; 2025-07-06: 242; 2025-07-07: 190; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 152; 2025-07-12: 146; 2025-07-13: 154; 2025-07-14: 140; 2025-07-15: 124; 2025-07-16: 46; 2025-07-17: 150; 2025-07-18: 200; 2025-07-19: 216; 2025-07-20: 284; 2025-07-21: 212; 2025-07-22: 202; 2025-07-23: 176; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 194; 2025-07-27: 242; 2025-07-28: 220; 2025-07-29: 136; 2025-07-30: 46; 2025-07-31: 190; 2025-08-01: 214; 2025-08-02: 184; 2025-08-03: 96; 2025-08-04: 194; 2025-08-05: 180; 2025-08-06: 202; 2025-08-07: 52; 2025-08-08: 226; 2025-08-09: 242; 2025-08-10: 300; 2025-08-11: 224; 2025-08-12: 302; 2025-08-13: 260; 2025-08-14: 252; 2025-08-15: 258; 2025-08-16: 252; 2025-08-17: 260; 2025-08-18: 254; 2025-08-19: 302; 2025-08-20: 308; 2025-08-21: 256; 2025-08-22: 280; 2025-08-23: 210; 2025-08-24: 258; 2025-08-25: 220; 2025-08-26: 300; 2025-08-27: 302; 2025-08-28: 238; 2025-08-29: 250; 2025-08-30: 236; 2025-08-31: 202; 2025-09-01: 218; 2025-09-02: 214; 2025-09-03: 206; 2025-09-04: 102; 2025-09-05: 176; 2025-09-06: 224; 2025-09-07: 160; 2025-09-08: DEMOB
[5 empty] | Difference | 2025-06-24: -104; 2025-06-25: -50; 2025-06-26: 10; 2025-06-27: 56; 2025-06-28: 38; 2025-06-29: 62; 2025-06-30: 31; 2025-07-01: -2; 2025-07-02: 37; 2025-07-03: 50; 2025-07-04: -78; 2025-07-05: -32; 2025-07-06: 92; 2025-07-07: 40; 2025-07-08: -150; 2025-07-09: -150; 2025-07-10: -150; 2025-07-11: 2; 2025-07-12: -4; 2025-07-13: 4; 2025-07-14: -10; 2025-07-15: -26; 2025-07-16: -104; 2025-07-17: 0; 2025-07-18: 50; 2025-07-19: 66; 2025-07-20: 134; 2025-07-21: 62; 2025-07-22: 52; 2025-07-23: 26; 2025-07-24: -150; 2025-07-25: -150; 2025-07-26: 44; 2025-07-27: 92; 2025-07-28: 70; 2025-07-29: -14; 2025-07-30: -104; 2025-07-31: 40; 2025-08-01: 64; 2025-08-02: 34; 2025-08-03: -54; 2025-08-04: 44; 2025-08-05: 30; 2025-08-06: 52; 2025-08-07: -98; 2025-08-08: 76; 2025-08-09: 92; 2025-08-10: 150; 2025-08-11: 74; 2025-08-12: 152; 2025-08-13: 110; 2025-08-14: 102; 2025-08-15: 108; 2025-08-16: 102; 2025-08-17: 110; 2025-08-18: 104; 2025-08-19: 152; 2025-08-20: 158; 2025-08-21: 106; 2025-08-22: 130; 2025-08-23: 60; 2025-08-24: 108; 2025-08-25: 70; 2025-08-26: 150; 2025-08-27: 152; 2025-08-28: 88; 2025-08-29: 100; 2025-08-30: 86; 2025-08-31: 52; 2025-09-01: 68; 2025-09-02: 64; 2025-09-03: 56; 2025-09-04: -48; 2025-09-05: 26; 2025-09-06: 74; 2025-09-07: 10; 2025-09-08: #VALUE!
[5 empty] | Cumulative Difference | 2025-06-24: -104; 2025-06-25: -154; 2025-06-26: -144; 2025-06-27: -88; 2025-06-28: -50; 2025-06-29: 12; 2025-06-30: 43; 2025-07-01: 41; 2025-07-02: 78; 2025-07-03: 128; 2025-07-04: 50; 2025-07-05: 18; 2025-07-06: 110; 2025-07-07: 150; 2025-07-08: 0; 2025-07-09: -150; 2025-07-10: -300; 2025-07-11: -298; 2025-07-12: -302; 2025-07-13: -298; 2025-07-14: -308; 2025-07-15: -334; 2025-07-16: -438; 2025-07-17: -438; 2025-07-18: -388; 2025-07-19: -322; 2025-07-20: -188; 2025-07-21: -126; 2025-07-22: -74; 2025-07-23: -48; 2025-07-24: -198; 2025-07-25: -348; 2025-07-26: -304; 2025-07-27: -212; 2025-07-28: -142; 2025-07-29: -156; 2025-07-30: -260; 2025-07-31: -220; 2025-08-01: -156; 2025-08-02: -122; 2025-08-03: -176; 2025-08-04: -132; 2025-08-05: -102; 2025-08-06: -50; 2025-08-07: -148; 2025-08-08: -72; 2025-08-09: 20; 2025-08-10: 170; 2025-08-11: 244; 2025-08-12: 396; 2025-08-13: 506; 2025-08-14: 608; 2025-08-15: 716; 2025-08-16: 818; 2025-08-17: 928; 2025-08-18: 1032; 2025-08-19: 1184; 2025-08-20: 1342; 2025-08-21: 1448; 2025-08-22: 1578; 2025-08-23: 1638; 2025-08-24: 1746; 2025-08-25: 1816; 2025-08-26: 1966; 2025-08-27: 2118; 2025-08-28: 2206; 2025-08-29: 2306; 2025-08-30: 2392; 2025-08-31: 2444; 2025-09-01: 2512; 2025-09-02: 2576; 2025-09-03: 2632; 2025-09-04: 2584; 2025-09-05: 2610; 2025-09-06: 2684; 2025-09-07: 2694
[5 empty] | 7 Day rolling average | 2025-06-29: 152; 2025-07-06: 164; 2025-07-13: 91.7143; 2025-07-20: 165.7143; 2025-07-27: 146.5714; 2025-08-03: 155.1429; 2025-08-04: 151.4286; 2025-08-11: 203.7143; 2025-08-18: 262.5714; 2025-08-25: 262; 2025-09-01: 249.4286; 2025-09-08: 180.3333
Enabling Earthwork's Task | [5 empty] | 2025-05-29: Task 4.1 - Prelim Pad Prep; 2025-05-30: Task 4.1 - Prelim Pad Prep; 2025-05-31: Task 4.1 - Prelim Pad Prep; 2025-06-02: Task 4.1 - Prelim Pad Prep; 2025-06-03: Task 4.1 - Prelim Pad Prep; 2025-06-04: Task 4.1 - Prelim Pad Prep; 2025-06-05: Task 4.1 - Prelim Pad Prep; 2025-06-06: Task 4.1 - Prelim Pad Prep; 2025-06-11: Task 4.2 - Complete Pad Prep; 2025-06-12: Task 4.2 - Complete Pad Prep; 2025-06-13: Task 4.2 - Complete Pad Prep; 2025-06-14: Task 4.2 - Complete Pad Prep; 2025-06-15: Task 4.2 - Complete Pad Prep; 2025-06-16: Task 4.2 - Complete Pad Prep; 2025-06-17: Task 4.2 - Complete Pad Prep; 2025-06-27: Task 4.2 - Complete Pad Prep; 2025-06-28: Task 4.2 - Complete Pad Prep; 2025-06-29: Task 4.2 - Complete Pad Prep; 2025-06-30: Task 4.2 - Complete Pad Prep; 2025-07-01: Task 4.2 - Complete Pad Prep
TRUE | 116.5 | 123 | Earthworks |  |  | 2025-05-29: 2.5; 2025-05-30: 2.5; 2025-05-31: 2.5; 2025-06-02: 2.5; 2025-06-03: 2.5; 2025-06-04: 2.5; 2025-06-05: 2.5; 2025-06-06: 2.5; 2025-06-11: 8.5; 2025-06-12: 8.5; 2025-06-13: 8.5; 2025-06-14: 8.5; 2025-06-15: 8.5; 2025-06-16: 8.5; 2025-06-17: 8.5; 2025-06-27: 8.5; 2025-06-28: 8.5; 2025-06-29: 8.5; 2025-06-30: 8.5; 2025-07-01: 9.5
|  |  | RCD2 |  | Drilling Phase | 2025-06-30: ExtA; 2025-07-01: ExtA; 2025-07-02: ExtA; 2025-07-03: ExtA; 2025-07-04: ExtA; 2025-07-05: ExtA; 2025-07-06: ExtA; 2025-07-07: ExtA; 2025-07-08: ExtA; 2025-07-09: ExtG; 2025-07-10: ExtG; 2025-07-11: ExtG; 2025-07-12: ExtG; 2025-07-13: ExtG; 2025-07-14: ExtG; 2025-07-15: ExtG; 2025-07-16: ExtG; 2025-07-17: ExtG; 2025-07-18: ExtG; 2025-07-19: ExtG; 2025-07-20: ExtG; 2025-07-21: ExtG; 2025-07-22: ExtG; 2025-07-23: ExtG; 2025-07-24: ExtG; 2025-07-25: Inf; 2025-07-26: Inf; 2025-07-27: Inf; 2025-07-28: Inf; 2025-07-29: Inf; 2025-07-30: Inf; 2025-07-31: Inf; 2025-08-01: Inf; 2025-08-02: Inf; 2025-08-03: Inf; 2025-08-04: Inf; 2025-08-05: Inf; 2025-08-06: Inf; 2025-08-07: Inf; 2025-08-08: Inf; 2025-08-09: Inf; 2025-08-10: Inf; 2025-08-11: Inf; 2025-08-12: Inf; 2025-08-13: Inf; 2025-08-14: Inf; 2025-08-15: Inf; 2025-08-16: Inf; 2025-08-17: Inf; 2025-08-18: Inf; 2025-08-19: Inf; 2025-08-20: Inf; 2025-08-21: Inf; 2025-08-22: Inf; 2025-08-23: Inf; 2025-08-24: Inf; 2025-08-25: Inf; 2025-08-26: Inf; 2025-08-27: Inf; 2025-08-28: Inf; 2025-08-29: Inf; 2025-08-30: Inf; 2025-08-31: Inf; 2025-09-01: Inf; 2025-09-02: Inf; 2025-09-03: Inf; 2025-09-04: Inf; 2025-09-05: Inf; 2025-09-06: Inf; 2025-09-07: Inf; 2025-09-08: Inf; 2025-09-09: Inf; 2025-09-10: Inf; 2025-09-11: Inf; 2025-09-12: Inf; 2025-09-13: Inf; 2025-09-14: Inf; 2025-09-15: Inf; 2025-09-16: Inf; 2025-09-17: Inf; 2025-09-18: Inf; 2025-09-19: Inf; 2025-09-20: Inf; 2025-09-21: Inf; 2025-09-22: Inf; 2025-09-23: Inf; 2025-09-24: Inf; 2025-09-25: South; 2025-09-26: South; 2025-09-27: South; 2025-09-28: South
#REF! | #REF! | 13850 | Drilling | RC 2 | Predicted | 2025-06-30: 150; 2025-07-01: 150; 2025-07-02: 150; 2025-07-03: 150; 2025-07-04: 150; 2025-07-05: 150; 2025-07-06: 150; 2025-07-07: 150; 2025-07-08: 150; 2025-07-09: 150; 2025-07-10: 150; 2025-07-11: 150; 2025-07-12: 150; 2025-07-13: 150; 2025-07-14: 150; 2025-07-15: 150; 2025-07-16: 150; 2025-07-17: 150; 2025-07-18: 150; 2025-07-19: 150; 2025-07-20: 150; 2025-07-21: 150; 2025-07-22: 150; 2025-07-23: 150; 2025-07-24: 150; 2025-07-25: 150; 2025-07-26: 150; 2025-07-27: 150; 2025-07-28: 150; 2025-07-29: 150; 2025-07-30: 150; 2025-07-31: 150; 2025-08-01: 150; 2025-08-02: 150; 2025-08-03: 150; 2025-08-04: 150; 2025-08-05: 150; 2025-08-06: 150; 2025-08-07: 150; 2025-08-08: 150; 2025-08-09: 150; 2025-08-10: 150; 2025-08-11: 150; 2025-08-12: 150; 2025-08-13: 150; 2025-08-14: 150; 2025-08-15: 150; 2025-08-16: 150; 2025-08-17: 150; 2025-08-18: 150; 2025-08-19: 150; 2025-08-20: 150; 2025-08-21: 150; 2025-08-22: 150; 2025-08-23: 150; 2025-08-24: 150; 2025-08-25: 150; 2025-08-26: 150; 2025-08-27: 150; 2025-08-28: 150; 2025-08-29: 150; 2025-08-30: 150; 2025-08-31: 150; 2025-09-01: 150; 2025-09-02: 150; 2025-09-03: 150; 2025-09-04: 150; 2025-09-05: 150; 2025-09-06: 150; 2025-09-07: 150; 2025-09-08: 150; 2025-09-09: 150; 2025-09-10: 150; 2025-09-11: 150; 2025-09-12: 150; 2025-09-13: 150; 2025-09-14: 150; 2025-09-15: 150; 2025-09-16: 150; 2025-09-17: 150; 2025-09-18: 150; 2025-09-19: 150; 2025-09-20: 150; 2025-09-21: 150; 2025-09-22: 150; 2025-09-23: 150; 2025-09-24: 150; 2025-09-25: 200; 2025-09-26: 200; 2025-09-27: 200; 2025-09-28: 200
Actual
Difference
Cumulative Difference
Enabling Earthwork's Task | [5 empty] | 2025-05-31: Task 4.1 - Prelim Pad Prep; 2025-06-01: Task 4.1 - Prelim Pad Prep; 2025-06-02: Task 4.1 - Prelim Pad Prep; 2025-06-18: Task 4.2 - Complete Pad Prep; 2025-06-19: Task 4.2 - Complete Pad Prep; 2025-06-20: Task 4.2 - Complete Pad Prep; 2025-06-21: Task 4.2 - Complete Pad Prep; 2025-06-22: Task 4.2 - Complete Pad Prep; 2025-06-23: Task 4.2 - Complete Pad Prep; 2025-06-24: Task 4.2 - Complete Pad Prep; 2025-06-25: Task 4.2 - Complete Pad Prep; 2025-06-26: Task 4.2 - Complete Pad Prep; 2025-07-02: Task 4.2 - Complete Pad Prep; 2025-07-03: Task 4.2 - Complete Pad Prep; 2025-07-04: Task 4.2 - Complete Pad Prep; 2025-07-05: Task 4.2 - Complete Pad Prep
TRUE | 117.5 | 118 | Earthworks |  |  | 2025-05-31: 2.5; 2025-06-01: 2.5; 2025-06-02: 2.5; 2025-06-18: 8.5; 2025-06-19: 8.5; 2025-06-20: 8.5; 2025-06-21: 8.5; 2025-06-22: 8.5; 2025-06-23: 8.5; 2025-06-24: 8.5; 2025-06-25: 8.5; 2025-06-26: 8.5; 2025-07-02: 8.5; 2025-07-03: 8.5; 2025-07-04: 8.5; 2025-07-05: 8.5
|  |  | HYD1 |  | Drilling Phase | 2025-07-10: Bores; 2025-07-11: Bores; 2025-07-12: Bores; 2025-07-13: Bores; 2025-07-14: Bores; 2025-07-15: Bores; 2025-07-16: Bores; 2025-07-17: Bores; 2025-07-18: Bores; 2025-07-19: Bores; 2025-07-20: Bores; 2025-07-21: Bores; 2025-07-22: Bores; 2025-07-23: Bores; 2025-07-24: Bores; 2025-07-25: Bores; 2025-07-26: Bores; 2025-07-27: Bores; 2025-07-28: Bores; 2025-07-29: Bores; 2025-07-30: Bores; 2025-07-31: Bores; 2025-08-01: Bores; 2025-08-02: Bores; 2025-08-03: Bores; 2025-08-04: Bores; 2025-08-05: Bores; 2025-08-06: Bores; 2025-08-07: Bores; 2025-08-08: Bores; 2025-08-09: Bores; 2025-08-10: Bores; 2025-08-11: Bores; 2025-08-12: Bores; 2025-08-13: Bores; 2025-08-14: Bores; 2025-08-15: Bores; 2025-08-16: Bores; 2025-08-17: Bores
|  |  | Rig 18 | Drilling | Predicted | 2025-07-10: 22; 2025-07-11: 22; 2025-07-12: 22; 2025-07-13: 22; 2025-07-14: 22; 2025-07-15: 22; 2025-07-16: 22; 2025-07-17: 22; 2025-07-18: 22; 2025-07-19: 22; 2025-07-20: 22; 2025-07-21: 22; 2025-07-22: 22; 2025-07-23: 22; 2025-07-24: 22; 2025-07-25: 22; 2025-07-26: 22; 2025-07-27: 22; 2025-07-28: 22; 2025-07-29: 22; 2025-07-30: 22; 2025-07-31: 22; 2025-08-01: 22; 2025-08-02: 22; 2025-08-03: 22; 2025-08-04: 22; 2025-08-05: 22; 2025-08-06: 22; 2025-08-07: 22; 2025-08-08: 22; 2025-08-09: 22; 2025-08-10: 22; 2025-08-11: 22; 2025-08-12: 22; 2025-08-13: 22; 2025-08-14: 22; 2025-08-15: 22; 2025-08-16: 22; 2025-08-17: 22
[5 empty] | Actual | 2025-07-10: 78; 2025-07-11: 36; 2025-07-12: 6; 2025-07-13: 90; 2025-07-14: 30; 2025-07-15: 125; 2025-07-16: 96; 2025-07-17: 63; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 3; 2025-07-26: 27; 2025-07-27: 70; 2025-07-28: 24; 2025-07-29: 46; 2025-07-30: 34; 2025-07-31: 74; 2025-08-01: 28; 2025-08-02: 30; 2025-08-03: 18
[5 empty] | Difference | 2025-07-10: 56; 2025-07-11: 14; 2025-07-12: -16; 2025-07-13: 68; 2025-07-14: 8; 2025-07-15: 103; 2025-07-16: 74; 2025-07-17: 41; 2025-07-18: -22; 2025-07-19: -22; 2025-07-20: -22; 2025-07-21: -22; 2025-07-22: -22; 2025-07-23: -22; 2025-07-24: -22; 2025-07-25: -19; 2025-07-26: 5; 2025-07-27: 48; 2025-07-28: 2; 2025-07-29: 24; 2025-07-30: 12; 2025-07-31: 52; 2025-08-01: 6; 2025-08-02: 8; 2025-08-03: -4
[5 empty] | Cumulative Difference | 2025-07-10: 56; 2025-07-11: 70; 2025-07-12: 54; 2025-07-13: 122; 2025-07-14: 130; 2025-07-15: 233; 2025-07-16: 307; 2025-07-17: 348; 2025-07-18: 326; 2025-07-19: 304; 2025-07-20: 282; 2025-07-21: 260; 2025-07-22: 238; 2025-07-23: 216; 2025-07-24: 194; 2025-07-25: 175; 2025-07-26: 180; 2025-07-27: 228; 2025-07-28: 230; 2025-07-29: 254; 2025-07-30: 266; 2025-07-31: 318; 2025-08-01: 324; 2025-08-02: 332; 2025-08-03: 328
[5 empty] | 7 day rolling average | 2025-07-14: 48; 2025-07-21: 40.5714; 2025-07-28: 17.7143; 2025-08-04: 38.3333
FALSE | 1934 | 13 |  |  | Predicted | bar: 2025-07-12; 2025-07-15; 2025-07-18; 2025-07-21; 2025-07-24; 2025-07-27; 2025-07-30; 2025-08-02; 2025-08-05; 2025-08-08; 2025-08-11; 2025-08-14; 2025-08-17
|  |  |  | Building | Actual | 2025-07-11: 1; 2025-07-12: 0; 2025-07-13: 0
[5 empty] | Difference | 2025-07-11: 1; 2025-07-12: -1; 2025-07-13: 0
Cumulative Difference
|  |  | HYD1 |  | Drilling Phase | 2025-07-21: Bores; 2025-07-22: Bores; 2025-07-23: Bores; 2025-07-24: Bores; 2025-07-25: Bores; 2025-07-26: Bores; 2025-07-27: Bores; 2025-07-28: Bores; 2025-07-29: Bores; 2025-07-30: Bores; 2025-07-31: Bores; 2025-08-01: Bores; 2025-08-02: Bores; 2025-08-03: Bores; 2025-08-04: Bores; 2025-08-05: Bores; 2025-08-06: Bores; 2025-08-07: Bores; 2025-08-08: Bores; 2025-08-09: Bores; 2025-08-10: Bores; 2025-08-11: Bores; 2025-08-12: Bores; 2025-08-13: Bores; 2025-08-14: Bores; 2025-08-15: Bores; 2025-08-16: Bores; 2025-08-17: Bores; 2025-08-18: Bores; 2025-08-19: Bores; 2025-08-20: Bores; 2025-08-21: Bores; 2025-08-22: Bores; 2025-08-23: Bores; 2025-08-24: Bores; 2025-08-25: Bores; 2025-08-26: Bores; 2025-08-27: Bores; 2025-08-28: Bores
|  |  | Rig 16 | Drilling | Predicted | 2025-07-21: 22; 2025-07-22: 22; 2025-07-23: 22; 2025-07-24: 22; 2025-07-25: 22; 2025-07-26: 22; 2025-07-27: 22; 2025-07-28: 22; 2025-07-29: 22; 2025-07-30: 22; 2025-07-31: 22; 2025-08-01: 22; 2025-08-02: 22; 2025-08-03: 22; 2025-08-04: 22; 2025-08-05: 22; 2025-08-06: 22; 2025-08-07: 22; 2025-08-08: 22; 2025-08-09: 22; 2025-08-10: 22; 2025-08-11: 22; 2025-08-12: 22; 2025-08-13: 22; 2025-08-14: 22; 2025-08-15: 22; 2025-08-16: 22; 2025-08-17: 22; 2025-08-18: 22; 2025-08-19: 22; 2025-08-20: 22; 2025-08-21: 22; 2025-08-22: 22; 2025-08-23: 22; 2025-08-24: 22; 2025-08-25: 22; 2025-08-26: 22; 2025-08-27: 22; 2025-08-28: 22
[5 empty] | Actual | 2025-07-21: 0; 2025-07-22: 40; 2025-07-23: 0; 2025-07-24: 19; 2025-07-25: 17; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 8
[5 empty] | Difference | 2025-07-21: -22; 2025-07-22: 18; 2025-07-23: -22; 2025-07-24: -3; 2025-07-25: -5; 2025-07-26: -22; 2025-07-27: -22; 2025-07-28: -22; 2025-07-29: -22; 2025-07-30: -22; 2025-07-31: -22; 2025-08-01: -22; 2025-08-02: -22; 2025-08-03: -14
|  |  |  | Building | Cumulative Difference | 2025-07-21: -22; 2025-07-22: -4; 2025-07-23: -26; 2025-07-24: -29; 2025-07-25: -34; 2025-07-26: -56; 2025-07-27: -78; 2025-07-28: -100; 2025-07-29: -122; 2025-07-30: -144; 2025-07-31: -166; 2025-08-01: -188; 2025-08-02: -210; 2025-08-03: -224
FALSE | 1934 | 12 |  |  | Predicted | bar: 2025-07-21; 2025-07-24; 2025-07-27; 2025-07-30; 2025-08-02; 2025-08-05; 2025-08-08; 2025-08-11; 2025-08-14; 2025-08-17; 2025-08-20; 2025-08-23
Actual
Difference
Cumulative Difference
Enabling Earthwork's Task | [5 empty] | 2025-07-06: Task 4.2 - Complete Pad Prep
#VALUE! | 7 | #VALUE! | Earthworks |  |  | 2025-06-09: #VALUE!; 2025-07-06: 8.5
Sample Dispatch | [5 empty] | 2025-06-20: Pick up; 2025-06-27: Pick up; 2025-07-04: Pick up; 2025-07-11: Pick up; 2025-07-18: Pick up; 2025-07-25: Pick up; 2025-08-01: Pick up; 2025-08-08: Pick up; 2025-08-15: Pick up; 2025-08-22: Pick up; 2025-08-29: Pick up; 2025-09-05: Pick up; 2025-09-12: Pick up; 2025-09-19: Pick up
|  |  | Predicted |  | Weight | [40 empty] | 0 | 382.5 | 382.5 | 382.5 | 382.5 | 382.5 | 382.5 | 795 | 795 | 795 | 795 | 795 | 795 | 1207.5 | 1207.5 | 1207.5 | 1207.5 | 1207.5 | 1207.5 | 1207.5 | 1207.5 | 1422.5 | 1465.5 | 1422.5 | 1422.5 | 1422.5 | 1422.5 | 1422.5 | 1422.5 | 1465.5 | 1465.5 | 1465.5 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1542 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1312.5 | 1312.5 | 1312.5 | 1312.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1465.5 | 1603 | 1603 | 1190.5 | 1190.5 | 640.5 | 640.5
[5 empty] | Number of Pallets | [40 empty] | 0 | 0.34722 | 0.34722 | 0.34722 | 0.34722 | 0.34722 | 0.34722 | 0.77579 | 0.77579 | 0.77579 | 0.77579 | 0.77579 | 0.77579 | 1.2044 | 1.2044 | 1.2044 | 1.2044 | 1.2044 | 1.2044 | 1.2044 | 1.2044 | 1.5516 | 1.621 | 1.5516 | 1.5516 | 1.5516 | 1.5516 | 1.5516 | 1.5516 | 1.621 | 1.621 | 1.621 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.621 | 1.621 | 1.621 | 1.621 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.6905 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.4821 | 1.4821 | 1.4821 | 1.4821 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.621 | 1.7639 | 1.7639 | 1.3353 | 1.3353 | 0.76389 | 0.76389
[5 empty] | Total Weight (t) | 2025-06-20: 0.765; 2025-06-27: 3.915; 2025-07-04: 7.215; 2025-07-11: 9.1405; 2025-07-18: 10.0435; 2025-07-25: 10.7175; 2025-08-01: 10.488; 2025-08-08: 10.488; 2025-08-15: 10.641; 2025-08-22: 10.641; 2025-08-29: 10.794; 2025-09-05: 10.335; 2025-09-12: 9.9525
[5 empty] | Total Pallets | 2025-06-20: 0.69444; 2025-06-27: 3.7163; 2025-07-04: 7.1448; 2025-07-11: 9.5417; 2025-07-18: 11; 2025-07-25: 11.7639; 2025-08-01: 11.5556; 2025-08-08: 11.5556; 2025-08-15: 11.6944; 2025-08-22: 11.6944; 2025-08-29: 11.8333; 2025-09-05: 11.4167; 2025-09-12: 11.0694
|  |  | Actual |  | Weight | [40 empty] | 0 | 787.95 | 856.8 | 803.25 | 327.42 | 896.58 | 459 | 625.28 | 626.9 | 1436.03 | 1238.17 | 1069.33 | 1277.62 | 819.05 | 722.18 | 1040.57 | 791.74 | 663.12 | 913.55 | 1066.36 | 1085.54 | 727.54 | 640.36 | 730.35 | 1154.76 | 1267.3 | 1039.55 | 1291.37 | 1226.59 | 982.28 | 1368.7 | 1246.88 | 2043.2 | 1758.7 | 1883.42 | 1546.96 | 1433.72 | 1313.6 | 619.41 | 1573.62 | 1636.63 | 1698.4 | 877.38 | 642.94 | #REF! | 1535.42 | 1275.4 | 1540.41 | 1179.5 | 1193.59 | 1822.51 | 674.13 | 1810.74 | 1903.07 | 1970.51 | 1922.17 | 1700.45 | 1317.08 | 1767.92 | 1681.06 | 1374.94 | 2346.68 | 2026.5 | 2406.5 | 1769.86 | 1932.91 | 1577.15 | 2235.91 | 1960.46 | 1911.14 | 2223.64 | 1826.14 | 1546.05 | 2367.41 | 1168.2 | #VALUE! | 1364.5 | 1353.5 | 1331.5 | 1045.5 | 1249 | 1381 | 1205 | #VALUE! | 497.25 | 7.65 | 504.9 | 208.08 | 468.18 | 423.81 | 408.51 | 237.15 | 459 | 339.66 | 440.64 | 359.55 | 192.78 | 454.41 | 371.79 | 367.2 | 449.82 | 90.27 | 192.78 | 413.1 | 734.4 | 740.52
[5 empty] | Number of Pallets | [40 empty] | 0 | 0.71528 | 0.77778 | 0.72917 | 0.29722 | 0.81389 | 0.41667 | 0.58421 | 0.60516 | 1.3613 | 1.1983 | 1.0385 | 1.2363 | 0.80881 | 0.70897 | 1.0121 | 0.79087 | 0.62794 | 0.87187 | 1.0553 | 1.054 | 0.82222 | 0.80694 | 0.88194 | 1.319 | 1.4713 | 1.2456 | 1.4667 | 1.5237 | 1.1564 | 1.6244 | 1.3312 | 2.3019 | 1.8559 | 2.0502 | 1.6438 | 1.5779 | 1.4722 | 0.60972 | 1.5848 | 1.7025 | 1.9702 | 1.0219 | 0.7231 | #REF! | 1.617 | 1.5021 | 1.7979 | 1.2751 | 1.3796 | 1.9341 | 0.69579 | 1.8652 | 2.1956 | 2.0655 | 2.2636 | 1.7906 | 1.6373 | 1.9756 | 1.9816 | 1.4881 | 2.6595 | 2.1563 | 2.6615 | 2.0133 | 2.0939 | 1.925 | 2.4917 | 2.251 | 2.0022 | 2.5641 | 2.1462 | 1.7314 | 2.6407 | 1.2812 | #VALUE! | 1.3173 | 1.3059 | 1.283 | 0.98587 | 1.1973 | 1.3344 | 1.1516 | #VALUE! | 0.45139 | 0.0069444 | 0.45833 | 0.18889 | 0.425 | 0.38472 | 0.37083 | 0.21528 | 0.41667 | 0.30833 | 0.4 | 0.32639 | 0.175 | 0.4125 | 0.3375 | 0.33333 | 0.40833 | 0.081944 | 0.175 | 0.375 | 0.66667 | 0.67222
[5 empty] | Total Weight (t) | 2025-06-20: 1.6447; 2025-06-27: 5.1745
[5 empty] | Total Pallets | 2025-06-20: 1.4931; 2025-06-27: 4.8076
|  |  | Logged and Processed |  | Metres RC | bar: 2025-05-10 to 2025-05-13
Pad build rate | Task 4.1 | 2.4667 |  |  | Metres PQ3 | bar: 2025-05-10 to 2025-05-13
| Task 4.2 | 8.5714 |  |  | Metres HQ3
Weight
Number of Pallets
Total Weight (t)
Total Pallets
[9 empty] | Predicted | Planned | [27 empty] | * | Geotech core will need to have a special packaging protocol
[7 empty] | DD | Met | 1425 | 2045
[7 empty] | DD | GeoT * | 300 | 1040
[7 empty] | DD | Inf | 900 | 1260
[7 empty] | DD | ExtA | 540 | 540
[7 empty] | DD | ExtG | 540 | 581
[7 empty] | RC | Bores | 1716 | 1934 | [5 empty] | Target | Meters
[7 empty] | RC | Inf | 17850 | 17945 | [5 empty] | Met Drilling (DFS) | 2045
[7 empty] | RC | ExtA | 3750 | 3645
[7 empty] | RC | ExtG | 4950 | 4495.1
[7 empty] | RC | Dingo | 750 | 630
[7 empty] | RC | South | 800 | 900
[16 empty] | Infill Drilling | 19205
[16 empty] | Dingo Vein 1st Pass | 630
[16 empty] | Southern Extension Exploration | 900
218
214
206
[69 empty] | 0 | [55 empty] | 102
[69 empty] | 40 | [55 empty] | 176
[69 empty] | 0 | [55 empty] | 224
[69 empty] | 19 | [55 empty] | 160
17
0
0
0
0
0
0
0
0
0
0
3
27
70
24
[125 empty] | asda | asda
[125 empty] | 7.4 | 15.1
7.7
[125 empty] | 21.1 | 28.2
7.1
[125 empty] | 5.9 | 15.7
9.8
[125 empty] | 12.4 | 20.4
8
[125 empty] | 8.5 | 14.2
5.7
[125 empty] | 3.8 | 26.2
22.4
[125 empty] | 10.6 | 10.6
0
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New Tab adapted from other sheet, please fill out.
Note on EC6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Single shifting
Note on BA7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text and formulas are a bad mix. This affects the calculations at the bottom of the sheet. I have added a macro to outline todays date to help user narrow in on column of interest.
Note on BC15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text and formulas are a bad mix. This affects the calculations at the bottom of the sheet. I have added a macro to outline todays date to help user narrow in on column of interest.
Note on BD15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text and formulas are a bad mix. This affects the calculations at the bottom of the sheet. I have added a macro to outline todays date to help user narrow in on column of interest.
Note on BI31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Text and formulas are a bad mix. This affects the calculations at the bottom of the sheet. I have added a macro to outline todays date to help user narrow in on column of interest.

## Pivot_Rig38 (hidden)
RIG38
Row Labels | Sum of Completed Holes | Sum of Total Length PQ | Sum of Total Length HQ | Sum of Charged Drilling Cost | Sum of Active Hours total Cost | Sum of Standby & Inactive Total Cost | Sum of Tool Hire Cost | Sum of Total Activity Hours Cost | Sum of ***Insert Total Consumable Costs*** | Sum of Total Costs
|  | 0 | 0 | 0 | 0 | 3780 | 0 | 3780 |  | 3780
DDRD | 1 | 0 | 84.6 | 13623 | 6900 | 45.625 | 1500 | 12750 | 7504.06 | 35767.06
GT | 7 | 10.1 | 333.9 | 67505 | 29440 | 12871 | 7425 | 44650 | 10934.64 | 130514.64
MET | 9 | 749 | 2.3 | 143015 | 54280 | 7471.5 | 12200 | 63910 | 37761.28 | 256886.28
(blank) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Grand Total | 17 | 759.1 | 420.8 | 224143 | 90620 | 24168.125 | 21125 | 125090 | 56199.98 | 426947.98
Row Labels | Sum of Planned Holes | Sum of Planned Metres
A-Vein Resource Extension | 47 | 4185
RD | 47 | 4185
DD | 5 | 450
RC | 42 | 3735
DFS Met Sample collection (24 no. Holes, 2,045m) | 24 | 2045
MET | 24 | 2045
DD | 24 | 2045
Dingo Vein Exploration | 7 | 630
EXP | 7 | 630
RC | 7 | 630
Geotechnical drilling (12 no. HQ Holes, 1040m) | 12 | 1040
GT | 12 | 1040
DD | 12 | 1040
G-Vein Resource Extension | 44 | 5516
RD | 44 | 5516
DD | 5 | 581
RC | 39 | 4935
Infill Drilling | 163 | 19285
INF | 163 | 19285
DD | 8 | 1260
RC | 155 | 18025
Southern Veins Exploration | 10 | 900
EXP | 10 | 900
RC | 10 | 900
(blank)
Grand Total | 307 | 33601
Timeline: Works in Excel 2013 or higher. Do not move or resize.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DDH1 RIG 38_Data
RIG 38 | [5 empty] | Rate | 130 | Hole 1 |  | 175 |  |  | 135 | Hole 2 |  | 175 |  |  | 135 | [5 empty] | 175 | 155 | 420 |  |  | 460 | 460 |  | 360 | 360
|  |  |  | Hole 1 | Hole 2 |  |  | PQ3 |  |  | HQ3 |  |  | PQ3 |  |  | HQ3 | [6 empty] | Slow Pen rate Normalised | [11 empty] | 0 | 0
Hole Type | Completion | Date | Shift | Hole ID | Hole ID2 | Personel (incl driller) | Accom Cost | Depth From | Depth To | Length | Depth From3 | Depth To4 | Length5 | Depth From6 | Depth To7 | Length8 | Depth From9 | Depth To10 | Length11 | Total Length PQ | Total Length HQ | Total Length | Drilling Cost | Charged Drilling Cost | PQ Ori Tool | HQ Ori Tool | Gyro Tool | Tool ID | Tool Hire Cost | Drill Time | Active hours (Other than drilling) | Active Hours total Cost | Inactive Hours (Other than client standby) | Standby Total Hours | Standby & Inactive Total Cost | Uncharged Hours | Maintenance | Total Daily Hours | Total Activity Hours Cost | ***Insert Total Consumable Costs*** | Total Consumables Cost (-accom) | Total Costs | Plod Cost (Comparison) | Cummulative Cost | Month | Day | Shift Shorthand
|  | 2025-07-05 05:02 | DS 5am | [9 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 1 | 1 |  |  | 0 | 0 | 0 | 3.5 |  | 1260 | 8.5 |  | 12 | 1260 |  |  | 1260 |  | 3780 | 07 | 5 | D
|  | 2025-07-05 | NS 5pm | [9 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [8 empty] | 0 | 0 | 0 | 3.5 |  | 1260 | 7.5 |  | 11 | 1260 |  |  | 1260 |  | 2520 | 07 | 5 | N
|  | 2025-07-06 05:02 | DS 5am | [9 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 1 | 1 |  |  | 0 | 0 | 0 | 3.5 |  | 1260 | 8.5 |  | 12 | 1260 |  |  | 1260 | 1260 | 1260 | 07 | 6 | D
|  | 2025-07-06 17:02 | NS 5pm | [9 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | 1260 | 07 | 6 | N
MET |  | 2025-07-07 05:02 | DS 5am | SF25_DMET023 |  | 6 | 780 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 13170 | 575 | 0 | 8.25 | 3795 | 2 |  | 720 | 1.75 |  | 12 | 4515 | 1541 | 761 | 6631 | 6631 | 7891 | 07 | 7 | D
|  | 2025-07-07 17:02 | NS 5pm | [9 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | 7891 | 07 | 7 | N
MET |  | 2025-07-08 05:02 | DS 5am | SF25_DMET023 |  | 3 | 390 | 0 | 11 | 11 |  |  | 0 |  |  | 0 |  |  | 0 | 11 | 0 | 11 | 1925 | 1955 |  | 1 | 1 | 13170 | 575 | 4.25 | 7 | 3220 | 0.75 |  | 270 |  |  | 12 | 3490 | 1076.34 | 686.34 | 7096.34 | 7096.34 | 14987.34 | 07 | 8 | D
MET |  | 2025-07-08 17:02 | NS 5pm | SF25_DMET023 |  | 3 | 390 | 11 | 26.6 | 15.6 |  |  | 0 |  |  | 0 |  |  | 0 | 15.6 | 0 | 15.6 | 2730 | 3335 |  |  |  |  | 0 | 7.25 | 1.5 | 690 | 0.25 |  | 90 | 3 |  | 12 | 780 | 507.93 | 117.93 | 4622.93 | 4622.93 | 19610.27 | 07 | 8 | N
MET |  | 2025-07-09 05:02 | DS 5am | SF25_DMET023 |  | 3 | 390 | 26.6 | 33.7 | 7.1 |  |  | 0 |  |  | 0 |  |  | 0 | 7.1 | 0 | 7.1 | 1242.5 | 1380 |  | 1 | 1 | 13170 | 575 | 3 | 0.25 | 115 | 0.25 |  | 90 | 8.5 |  | 12 | 205 | 390 | 0 | 2550 | 2550 | 22160.27 | 07 | 9 | D
MET |  | 2025-07-09 17:02 | NS 5pm | SF25_DMET023 |  | 3 | 390 | 33.7 | 63.7 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10.75 | 0.75 | 345 | 0.5 |  | 180 |  |  | 12 | 525 | 507.93 | 117.93 | 6282.93 | 6282.93 | 28443.2 | 07 | 9 | N
MET |  | 2025-07-10 05:02 | DS 5am | SF25_DMET023 |  | 3 | 390 | 63.7 | 84.1 | 20.4 |  |  | 0 |  |  | 0 |  |  | 0 | 20.4 | 0 | 20.4 | 3570 | 5060 |  | 1 | 1 | 13170 | 575 | 11 | 0.5 | 230 | 0.5 |  | 180 |  |  | 12 | 410 | 817.99 | 427.99 | 6862.99 | 6862.99 | 35306.19 | 07 | 10 | D
MET |  | 2025-07-10 17:02 | NS 5pm | SF25_DMET023 |  | 3 | 390 | 84.1 | 99.7 | 15.6 |  |  | 0 |  |  | 0 |  |  | 0 | 15.6 | 0 | 15.6 | 2730 | 3105 |  |  |  |  | 0 | 6.75 | 4.75 | 2185 | 0.5 |  | 180 |  |  | 12 | 2365 | 1166.68 | 776.68 | 6636.68 | 6636.68 | 41942.87 | 07 | 10 | N
MET | 1 | 2025-07-11 05:02 | DS 5am | SF25_DMET023 |  | 3 | 390 | 99.7 | 118.7 | 19 |  |  | 0 |  |  | 0 |  |  | 0 | 19 | 0 | 19 | 3325 | 3910 |  | 1 | 1 | 13170 | 575 | 8.5 | 3 | 1380 | 0.5 |  | 180 |  |  | 12 | 1560 | 390 |  | 6435 | 6435 | 48377.87 | 07 | 11 | D
MET |  | 2025-07-11 17:02 | NS 5pm | SF25_DMET022 |  | 3 | 390 | 0 | 16.5 | 16.5 |  |  | 0 |  |  | 0 |  |  | 0 | 16.5 | 0 | 16.5 | 2887.5 | 3335 |  |  |  |  | 0 | 7.25 | 4.25 | 1955 | 0.5 |  | 180 |  |  | 12 | 2135 | 786.12 | 396.12 | 6256.12 | 6256.12 | 54633.99 | 07 | 11 | N
MET |  | 2025-07-12 05:02 | DS 5am | SF25_DMET022 |  | 3 | 390 | 16.5 | 39.4 | 22.9 |  |  | 0 |  |  | 0 |  |  | 0 | 22.9 | 0 | 22.9 | 4007.5 | 4945 |  | 1 | 1 | 13170 | 575 | 10.75 | 0.25 | 115 | 0.5 |  | 180 | 0.5 |  | 12 | 295 | 541.79 | 151.79 | 6356.79 | 6356.79 | 60990.78 | 07 | 12 | D
MET |  | 2025-07-12 17:02 | NS 5pm | SF25_DMET022 |  | 3 | 390 | 39.4 | 60.6 | 21.2 |  |  | 0 |  |  | 0 |  |  | 0 | 21.2 | 0 | 21.2 | 3710 | 3910 |  |  |  |  | 0 | 8.5 | 2.5 | 1150 | 0.5 |  | 180 | 0.5 |  | 12 | 1330 | 507.93 | 117.93 | 5747.93 | 5747.93 | 66738.71 | 07 | 12 | N
MET |  | 2025-07-13 05:02 | DS 5am | SF25_DMET022 |  | 3 | 390 | 60.6 | 73.8 | 13.2 |  |  | 0 |  |  | 0 |  |  | 0 | 13.2 | 0 | 13.2 | 2310 | 4025 |  | 1 | 1 | 13170 | 575 | 8.75 | 2.75 | 1265 | 0.5 |  | 180 |  |  | 12 | 1445 | 443.23 | 53.23 | 6488.23 | 6488.23 | 73226.94 | 07 | 13 | D
MET |  | 2025-07-13 17:02 | NS 5pm | SF25_DMET022 |  | 3 | 390 | 73.8 | 101.1 | 27.3 |  |  | 0 |  |  | 0 |  |  | 0 | 27.3 | 0 | 27.3 | 4777.5 | 5060 |  |  |  |  | 0 | 11 | 0.5 | 230 | 0.5 |  | 180 |  |  | 12 | 410 | 507.93 | 117.93 | 5977.93 | 5977.93 | 79204.87 | 07 | 13 | N
MET | 1 | 2025-07-14 05:02 | DS 5am | SF25_DMET022 |  | 3 | 390 | 101.1 | 120.7 | 19.6 |  |  | 0 |  |  | 0 |  |  | 0 | 19.6 | 0 | 19.6 | 3430 | 3680 |  | 1 | 1 | 13170 | 575 | 8 | 3.5 | 1610 | 0.5 |  | 180 |  |  | 12 | 1790 | 390 |  | 6435 | 6435 | 85639.87 | 07 | 14 | D
MET |  | 2025-07-14 17:02 | NS 5pm | SF25_DMET021 |  | 3 | 390 | 0 | 20.5 | 20.5 |  |  | 0 |  |  | 0 |  |  | 0 | 20.5 | 0 | 20.5 | 3587.5 | 3795 |  |  |  |  | 0 | 8.25 | 3.25 | 1495 | 0.5 |  | 180 |  |  | 12 | 1675 | 625.86 | 235.86 | 6095.86 | 6095.86 | 91735.73 | 07 | 14 | N
MET |  | 2025-07-15 05:02 | DS 5am | SF25_DMET021 |  | 3 | 390 | 20.5 | 50.5 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 0 | 30 | 5250 | 5250 |  | 1 | 1 | 13170 | 575 | 10.5 | 1 | 460 | 0.5 |  | 180 |  |  | 12 | 640 | 1269.56 | 879.56 | 7734.56 | 7734.56 | 99470.29 | 07 | 15 | D
MET |  | 2025-07-15 17:02 | NS 5pm | SF25_DMET021 |  | 3 | 390 | 50.5 | 80.6 | 30.1 |  |  | 0 |  |  | 0 |  |  | 0 | 30.1 | 0 | 30.1 | 5267.5 | 5267.5 |  |  |  |  | 0 | 10.25 | 1.25 | 575 | 0.5 |  | 180 |  |  | 12 | 755 | 626.49 | 236.49 | 6648.99 | 6648.99 | 106119.28 | 07 | 15 | N
MET | 1 | 2025-07-16 05:02 | DS 5am | SF25_DMET021 | SF25_DMET020 | 3 | 390 | 80.6 | 90.6 | 10 |  |  | 0 | 0 | 9 | 9 |  |  | 0 | 19 | 0 | 19 | 3325 | 3325 |  | 1 | 1 | 13170 | 575 | 6.5 | 4.5 | 2070 | 1 |  | 360 |  |  | 12 | 2430 | 390 |  | 6720 | 6720 | 112839.28 | 07 | 16 | D
MET |  | 2025-07-16 17:02 | NS 5pm | SF25_DMET020 |  | 3 | 390 | 9 | 30.8 | 21.8 |  |  | 0 |  |  | 0 |  |  | 0 | 21.8 | 0 | 21.8 | 3815 | 4025 |  |  |  |  | 0 | 8.75 | 2.75 | 1265 | 0.5 |  | 180 |  |  | 12 | 1445 | 786.12 | 396.12 | 6256.12 | 6256.12 | 119095.4 | 07 | 16 | N
MET |  | 2025-07-17 05:02 | DS 5am | SF25_DMET020 |  | 3 | 390 | 30.8 | 57 | 26.2 |  |  | 0 |  |  | 0 |  |  | 0 | 26.2 | 0 | 26.2 | 4585 | 4715 |  | 1 | 1 | 13170 | 575 | 10.25 | 1.25 | 575 | 0.5 |  | 180 |  |  | 12 | 755 | 390 |  | 6435 | 6435 | 125530.4 | 07 | 17 | D
MET |  | 2025-07-17 17:02 | NS 5pm | SF25_DMET020 |  | 3 | 390 | 57 | 84.7 | 27.7 |  |  | 0 |  |  | 0 |  |  | 0 | 27.7 | 0 | 27.7 | 4847.5 | 4847.5 |  |  |  |  | 0 | 10 | 1.5 | 690 | 0.5 |  | 180 |  |  | 12 | 870 | 507.93 | 117.93 | 6225.43 | 6225.43 | 131755.83 | 07 | 17 | N
MET | 1 | 2025-07-18 05:02 | DS 5am | SF25_DMET020 |  | 3 | 390 | 84.7 | 90.7 | 6 |  |  | 0 |  |  | 0 |  |  | 0 | 6 | 0 | 6 | 1050 | 1610 |  | 1 | 1 | 13170 | 575 | 3.5 | 7.5 | 3450 | 1 |  | 360 |  |  | 12 | 3810 | 390 |  | 6385 | 6385 | 138140.83 | 07 | 18 | D
MET |  | 2025-07-18 17:02 | NS 5pm | SF25_DMET010 |  | 3 | 390 | 0 | 14.9 | 14.9 |  |  | 0 |  |  | 0 |  |  | 0 | 14.9 | 0 | 14.9 | 2607.5 | 2607.5 |  |  |  |  | 0 | 5.25 | 3.75 | 1725 | 0.5 | 2.5 | 1080 |  |  | 12 | 2805 | 904.05 | 514.05 | 6316.55 | 6316.55 | 144457.38 | 07 | 18 | N
MET |  | 2025-07-19 05:02 | DS 5am | SF25_DMET010 |  | 3 | 390 | 14.9 | 45.6 | 30.7 |  |  | 0 |  |  | 0 |  |  | 0 | 30.7 | 0 | 30.7 | 5372.5 | 5372.5 |  | 1 | 1 | 13170 | 575 | 10.75 | 0.75 | 345 | 0.5 |  | 180 |  |  | 12 | 525 | 390 |  | 6862.5 | 6862.5 | 151319.88 | 07 | 19 | D
MET |  | 2025-07-19 17:02 | NS 5pm | SF25_DMET010 |  | 3 | 390 | 45.6 | 75.6 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10.5 | 1 | 460 | 0.5 |  | 180 |  |  | 12 | 640 | 507.93 | 117.93 | 6397.93 | 6397.93 | 157717.81 | 07 | 19 | N
MET | 1 | 2025-07-20 05:02 | DS 5am | SF25_DMET010 | SF25_DDGT012 | 3 | 390 | 75.6 | 81.6 | 6 | 0 | 2.3 | 2.3 |  |  | 0 |  |  | 0 | 6 | 2.3 | 8.3 | 1360.5 | 1495 |  | 1 | 1 | 13170 | 575 | 3.25 | 7.75 | 3565 | 0.5 |  | 180 | 0.5 |  | 12 | 3745 | 390 |  | 6205 | 6205 | 163922.81 | 07 | 20 | D
GT |  | 2025-07-20 17:02 | NS 5pm | SF25_DDGT012 |  | 3 | 390 |  |  | 0 | 2.3 | 19.8 | 17.5 |  |  | 0 |  |  | 0 | 0 | 17.5 | 17.5 | 2362.5 | 3335 |  |  |  |  | 0 | 7.25 | 3.75 | 1725 | 0.5 |  | 180 | 0.5 |  | 12 | 1905 | 904.05 | 514.05 | 6144.05 | 6144.05 | 170066.86 | 07 | 20 | N
GT |  | 2025-07-21 05:02 | DS 5am | SF25_DDGT012 |  | 3 | 390 |  |  | 0 | 19.8 | 41.3 | 21.5 |  |  | 0 |  |  | 0 | 0 | 21.5 | 21.5 | 2902.5 | 4945 |  | 1 | 1 | 13170 | 575 | 10.75 | 0.75 | 345 | 0.5 |  | 180 |  |  | 12 | 525 | 541.79 | 151.79 | 6586.79 | 6586.79 | 176653.65 | 07 | 21 | D
GT |  | 2025-07-21 17:02 | NS 5pm | SF25_DDGT012 |  | 3 | 390 |  |  | 0 | 41.3 | 63.2 | 21.9 |  |  | 0 |  |  | 0 | 0 | 21.9 | 21.9 | 2956.5 | 4945 |  |  |  |  | 0 | 10.75 | 0.75 | 345 | 0.5 |  | 180 |  |  | 12 | 525 | 507.93 | 117.93 | 5977.93 | 5977.93 | 182631.58 | 07 | 21 | N
GT | 1 | 2025-07-22 05:02 | DS 5am | SF25_DDGT012 | SF25_DMET024 | 3 | 390 | 0 | 3.7 | 3.7 | 63.2 | 70.5 | 7.3 |  |  | 0 |  |  | 0 | 3.7 | 7.3 | 11 | 1633 | 2875 |  | 1 | 1 | 13170 | 575 | 6.25 | 5.25 | 2415 | 0.5 |  | 180 |  |  | 12 | 2595 | 390 |  | 6435 | 6435 | 189066.58 | 07 | 22 | D
MET |  | 2025-07-22 17:02 | NS 5pm | SF25_DMET024 |  | 3 | 390 | 3.7 | 20.1 | 16.4 |  |  | 0 |  |  | 0 |  |  | 0 | 16.4 | 0 | 16.4 | 2870 | 2870 |  |  |  |  | 0 | 5.75 | 2.75 | 1265 | 0.5 |  | 180 | 3 |  | 12 | 1445 | 904.05 | 514.05 | 5219.05 | 5219.05 | 194285.63 | 07 | 22 | N
MET |  | 2025-07-23 05:02 | DS 5am | SF25_DMET024 |  | 3 | 390 | 20.1 | 27.7 | 7.6 |  |  | 0 |  |  | 0 |  |  | 0 | 7.6 | 0 | 7.6 | 1330 | 1610 |  | 1 | 1 | 13170 | 575 | 3.5 | 0.75 | 345 | 0.5 |  | 180 | 7.25 |  | 12 | 525 | 390 |  | 3100 | 3100 | 197385.63 | 07 | 23 | D
MET |  | 2025-07-23 17:02 | NS 5pm | SF25_DMET024 |  | 3 | 390 | 27.7 | 55.1 | 27.4 |  |  | 0 |  |  | 0 |  |  | 0 | 27.4 | 0 | 27.4 | 4795 | 4830 |  |  |  |  | 0 | 10.5 | 1 | 460 | 0.5 |  | 180 |  |  | 12 | 640 | 390 |  | 5860 | 5860 | 203245.63 | 07 | 23 | N
MET |  | 2025-07-24 05:02 | DS 5am | SF25_DMET024 |  | 3 | 390 | 55.1 | 84.7 | 29.6 |  |  | 0 |  |  | 0 |  |  | 0 | 29.6 | 0 | 29.6 | 5180 | 5180 |  | 1 | 1 | 13170 | 575 | 10.5 | 1 | 460 | 0.5 |  | 180 |  |  | 12 | 640 | 646.06 | 256.06 | 7041.06 | 7041.06 | 210286.69 | 07 | 24 | D
MET | 1 | 2025-07-24 17:02 | NS 5pm | SF25_DMET024 |  | 3 | 390 | 84.7 | 101.1 | 16.4 |  |  | 0 |  |  | 0 |  |  | 0 | 16.4 | 0 | 16.4 | 2870 | 3335 |  |  |  |  | 0 | 7.25 | 4.25 | 1955 | 0.5 |  | 180 |  |  | 12 | 2135 | 390 |  | 5860 | 5860 | 216146.69 | 07 | 24 | N
GT |  | 2025-07-25 05:02 | DS 5am | SF25_DDGT006 |  | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 13170 | 575 | 0 | 7.5 | 3450 | 4.5 |  | 1620 |  |  | 12 | 5070 | 646.06 | 256.06 | 6291.06 | 6291.06 | 222437.75 | 07 | 25 | D
GT |  | 2025-07-25 17:02 | NS 5pm | SF25_DDGT006 |  | 3 | 390 |  |  | 0 | 6 | 13.8 | 7.8 |  |  | 0 |  |  | 0 | 0 | 7.8 | 7.8 | 1053 | 1840 |  |  |  |  | 0 | 4 | 3 | 1380 | 5 |  | 1800 |  |  | 12 | 3180 | 390 |  | 5410 | 5410 | 227847.75 | 07 | 25 | N
GT | 1 | 2025-07-26 05:02 | DS 5am | SF25_DDGT006 | SF25_DDGT005 | 3 | 390 |  |  | 0 | 13.8 | 15 | 1.2 |  |  | 0 | 0 | 2 | 2 | 0 | 3.2 | 3.2 | 432 | 1265 |  | 1 | 1 | 13170 | 575 | 2.75 | 6.75 | 3105 | 2.5 |  | 900 |  |  | 12 | 4005 | 390 |  | 6235 | 6235 | 234082.75 | 07 | 26 | D
GT | 1 | 2025-07-26 17:02 | NS 5pm | SF25_DDGT005 |  | 3 | 390 |  |  | 0 | 2 | 15 | 13 |  |  | 0 |  |  | 0 | 0 | 13 | 13 | 1755 | 2300 |  |  |  |  | 0 | 5 | 2.5 | 1150 | 4.5 |  | 1620 |  |  | 12 | 2770 | 390 |  | 5460 | 5460 | 239542.75 | 07 | 26 | N
GT |  | 2025-07-27 05:02 | DS 5am | SF25_DDGT011 |  | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1 | 13170 | 575 | 0 | 6 | 2760 | 0.5 | 5 | 1980 | 0.5 |  | 12 | 4740 | 390 |  | 5705 | 5705 | 245247.75 | 07 | 27 | D
GT |  | 2025-07-27 17:02 | NS 5pm | SF25_DDGT011 |  | 3 | 390 |  |  | 0 | 0 | 21.3 | 21.3 |  |  | 0 |  |  | 0 | 0 | 21.3 | 21.3 | 2875.5 | 3335 |  |  |  |  | 0 | 7.25 | 3.75 | 1725 | 0.5 |  | 180 | 0.5 |  | 12 | 1905 | 1076.61 | 686.61 | 6316.61 | 6316.61 | 251564.36 | 07 | 27 | N
GT |  | 2025-07-28 05:02 | DS 5am | SF25_DDGT011 |  | 3 | 390 |  |  | 0 | 21.3 | 51.7 | 30.4 |  |  | 0 |  |  | 0 | 0 | 30.4 | 30.4 | 4104 | 5060 |  | 1 | 1 | 13170 | 575 | 11 | 0.5 | 230 | 0.5 |  | 180 |  |  | 12 | 410 | 390 |  | 6435 | 6435 | 257999.36 | 07 | 28 | D
GT |  | 2025-07-28 17:02 | NS 5pm | SF25_DDGT011 |  | 3 | 390 |  |  | 0 | 51.7 | 78.7 | 27 |  |  | 0 |  |  | 0 | 0 | 27 | 27 | 3645 | 4945 |  |  |  |  | 0 | 10.75 | 0.25 | 115 | 0.5 |  | 180 |  | 0.5 | 12 | 295 | 390 |  | 5630 | 5630 | 263629.36 | 07 | 28 | N
GT |  | 2025-07-29 05:02 | DS 5am | SF25_DDGT011 |  | 3 | 390 |  |  | 0 | 78.7 | 92.7 | 14 |  |  | 0 |  |  | 0 | 0 | 14 | 14 | 1890 | 2645 |  | 1 | 1 | 13170 | 575 | 5.75 | 0.25 | 115 | 0.5 |  | 180 |  | 5.5 | 12 | 295 | 390 |  | 3905 | 3905 | 267534.36 | 07 | 29 | D
GT |  | 2025-07-29 17:02 | NS 5pm | SF25_DDGT011 |  | 3 | 390 |  |  | 0 | 92.7 | 107.7 | 15 |  |  | 0 |  |  | 0 | 0 | 15 | 15 | 2025 | 3680 |  |  |  |  | 0 | 8 | 0.5 | 230 | 0.5 |  | 180 |  | 3 | 12 | 410 | 527.5 | 137.5 | 4617.5 | 4617.5 | 272151.86 | 07 | 29 | N
GT | 1 | 2025-07-30 05:02 | DS 5am | SF25_DDGT011 |  | 3 | 390 |  |  | 0 | 107.7 | 130 | 22.3 |  |  | 0 |  |  | 0 | 0 | 22.3 | 22.3 | 3010.5 | 4370 |  | 1 | 1 | 13170 | 575 | 9.5 | 1.5 | 690 | 1 |  | 360 |  |  | 12 | 1050 | 390 |  | 6385 | 6385 | 278536.86 | 07 | 30 | D
GT | 1 | 2025-07-30 17:02 | NS 5pm | SF25_DDGT011 | SF25_DDGT002 | 3 | 390 |  |  | 0 | 0 | 1.7 | 1.7 |  |  | 0 |  |  | 0 | 0 | 1.7 | 1.7 | 229.5 | 345 |  |  |  |  | 0 | 0.75 | 6.5 | 2990 | 4.75 |  | 1710 |  |  | 12 | 4700 | 390 |  | 5435 | 5435 | 283971.86 | 07 | 30 | N
GT | 1 | 2025-07-31 05:02 | DS 5am | SF25_DDGT006 |  | 3 | 390 | 0 | 6.4 | 6.4 |  |  | 0 |  |  | 0 |  |  | 0 | 6.4 | 0 | 6.4 | 1120 | 1840 |  | 1 | 1 | 13170 | 575 | 4 | 4.5 | 2070 | 3.5 |  | 1260 |  |  | 12 | 3330 | 390 |  | 6135 | 6135 | 290106.86 | 07 | 31 | D
MET |  | 2025-07-31 17:02 | NS 5pm | SF25_DMET018 |  | 3 | 390 | 1.2 | 15.5 | 14.3 |  |  | 0 |  |  | 0 |  |  | 0 | 14.3 | 0 | 14.3 | 2502.5 | 4255 |  |  |  |  | 0 | 9.25 | 2.25 | 1035 | 0.5 |  | 180 |  |  | 12 | 1215 | 14376.12 | 13986.12 | 19846.12 | 19846.12 | 309952.98 | 07 | 31 | N
MET |  | 2025-08-01 05:02 | DS 5am | SF25_DMET018 |  | 3 | 390 | 15.5 | 45.5 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 0 | 30 | 5250 | 5250 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 | 230 | 0.5 |  | 0 |  |  | 12 | 410 | 390 |  | 6800 | 6800 | 316752.98 | 08 | 1 | D
MET | 1 | 2025-08-01 17:02 | NS 5pm | SF25_DMET018 |  | 3 | 390 | 45.5 | 50 | 4.5 |  |  | 0 |  |  | 0 |  |  | 0 | 4.5 | 0 | 4.5 | 787.5 | 920 |  |  |  |  | 0 | 2 | 9.5 | 4370 | 0.5 |  | 0 |  |  | 12 | 4550 | 390 |  | 5860 | 5860 | 322612.98 | 08 | 1 | N
GT |  | 2025-08-02 05:02 | DS 5am | SF25_DDGT010 |  | 3 | 390 |  |  | 0 | 0 | 15.7 | 15.7 |  |  | 0 |  |  | 0 | 0 | 15.7 | 15.7 | 2119.5 | 2990 | 1 | 1 | 1 | 13170 | 750 | 6.5 | 2 | 920 | 1.5 | 2 | 0 |  |  | 12 | 2180 | 880.7 | 490.7 | 6800.7 | 6800.7 | 329413.68 | 08 | 2 | D
GT |  | 2025-08-02 17:02 | NS 5pm | SF25_DDGT010 |  | 3 | 390 |  |  | 0 | 15.7 | 45.7 | 30 |  |  | 0 |  |  | 0 | 0 | 30 | 30 | 4050 | 4945 |  |  |  |  | 0 | 10.75 | 0.75 | 345 | 0.5 |  | 0 |  |  | 12 | 525 | 390 | 0 | 5860 | 5860 | 335273.68 | 08 | 2 | N
GT |  | 2025-08-03 05:02 | DS 5am | SF25_DDGT010 |  | 3 | 390 |  |  | 0 | 45.7 | 75.5 | 29.8 |  |  | 0 |  |  | 0 | 0 | 29.8 | 29.8 | 4023 | 5060 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 | 230 | 0.5 |  | 0 |  |  | 12 | 410 | 390 | 0 | 6610 | 6610 | 341883.68 | 08 | 3 | D
GT |  | 2025-08-03 17:02 | NS 5pm | SF25_DDGT010 |  | 3 | 390 |  |  | 0 | 75.5 | 105.7 | 30.2 |  |  | 0 |  |  | 0 | 0 | 30.2 | 30.2 | 4077 | 4945 |  |  |  |  | 0 | 10.75 | 0.25 | 115 | 0.5 |  | 1 | 0.5 |  | 12 | 295 | 390 | 0 | 5630 | 5630 | 347513.68 | 08 | 3 | N
GT | 1 | 2025-08-04 05:02 | DS 5am | SF25_DDGT010 | SF25_DMET017 | 3 | 390 |  |  | 0 | 105.7 | 110 | 4.3 | 0 | 0 | 0 |  |  | 0 | 0 | 4.3 | 4.3 | 580.5 | 1840 | 1 | 1 | 1 | 13170 | 750 | 4 | 6.5 | 2990 | 0.5 | 1 | 0 |  |  | 12 | 3530 | 390 | 0 | 6510 | 6510 | 354023.68 | 08 | 4 | D
MET |  | 2025-08-04 17:02 | NS 5pm | SF25_DMET017 |  | 3 | 390 | 0 | 17.8 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 | 17.8 | 0 | 17.8 | 3115 | 3680 |  |  |  |  | 0 | 8 | 3.5 | 1610 | 0.5 |  | 0 |  |  | 12 | 1790 | 786.12 | 396.12 | 6256.12 | 6256.12 | 360279.8 | 08 | 4 | N
MET | 1 | 2025-08-05 05:02 | DS 5am | SF25_DMET017 |  | 3 | 390 | 17.8 | 50.1 | 32.3 |  |  | 0 |  |  | 0 |  |  | 0 | 32.3 | 0 | 32.3 | 5652.5 | 5652.5 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 | 345 | 0.5 |  | 0 |  |  | 12 | 525 | 390 | 0 | 7317.5 | 7317.5 | 367597.3 | 08 | 5 | D
MET |  | 2025-08-05 17:02 | NS 5pm | SF25_DMET019 |  | 3 | 390 | 0 | 5.7 | 5.7 |  |  | 0 |  |  | 0 |  |  | 0 | 5.7 | 0 | 5.7 | 997.5 | 997.5 |  |  |  |  | 0 | 2 | 6.5 | 2990 | 1.5 |  | 1.5 | 2 |  | 12 | 3530 | 390 | 0 | 4917.5 | 4917.5 | 372514.8 | 08 | 5 | N
MET |  | 2025-08-06 05:02 | DS 5am | SF25_DMET019 |  | 3 | 390 | 5.7 | 8.4 | 2.7 |  |  | 0 |  |  | 0 |  |  | 0 | 2.7 | 0 | 2.7 | 472.5 | 575 | 1 | 1 | 1 | 13170 | 750 | 1.25 | 1.25 | 575 | 0.5 | 1 | 0 | 8 |  | 12 | 1115 | 786.12 | 396.12 | 3226.12 | 3226.12 | 375740.92 | 08 | 6 | D
MET |  | 2025-08-06 17:02 | NS 5pm | SF25_DMET019 |  | 3 | 390 | 8.4 | 39.7 | 31.3 |  |  | 0 |  |  | 0 |  |  | 0 | 31.3 | 0 | 31.3 | 5477.5 | 5477.5 |  |  |  |  | 0 | 11 | 0.5 | 230 | 0.5 |  | 0 |  |  | 12 | 410 | 390 | 0 | 6277.5 | 6277.5 | 382018.42 | 08 | 6 | N
MET | 1 | 2025-08-07 05:02 | DS 5am | SF25_DMET019 | SF25_DDRD001 | 3 | 390 | 39.7 | 50.4 | 10.7 |  |  | 0 |  |  | 0 |  |  | 0 | 10.7 | 0 | 10.7 | 1872.5 | 1872.5 | 1 | 1 | 1 | 13170 | 750 | 4 | 7.5 | 3450 | 0.5 |  | 0 |  |  | 12 | 3630 | 390 | 0 | 6642.5 |  | 388660.92 | 08 | 7 | D
DDRD |  | 2025-08-07 17:02 | NS 5pm | SF25_DDRD001 |  | 3 | 390 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 11.5 | 5290 | 0.5 |  | 0.5 |  |  | 12 | 5470 | 390 | 0 | 5860 |  | 394520.92 | 08 | 7 | N
DDRD |  | 2025-08-08 05:02 | DS 5am | SF25_DDRD001 |  | 3 | 390 |  |  | 0 | 0 | 5 | 5 |  |  | 0 |  |  | 0 | 0 | 5 | 5 | 675 | 920 | 1 | 1 | 1 | 13170 | 750 | 2 | 0 | 0 | 0.5 | 9.5 | 0 |  |  | 12 | 3600 | 5458 | 5068 | 10728 | 10728 | 405248.92 | 08 | 8 | D
DDRD |  | 2025-08-08 17:02 | NS 5pm | SF25_DDRD001 |  | 3 | 390 |  |  | 0 | 5 | 22 | 17 |  |  | 0 |  |  | 0 | 0 | 17 | 17 | 2295 | 4025 |  |  |  |  | 0 | 8.75 | 2.75 | 1265 | 0.5 |  | 0 |  |  | 12 | 1445 | 738.56 | 348.56 | 6208.56 | 6208.56 | 411457.48 | 08 | 8 | N
DDRD |  | 2025-08-09 05:02 | DS 5am | SF25_DDRD001 |  | 3 | 390 |  |  | 0 | 22 | 57.8 | 35.8 |  |  | 0 |  |  | 0 | 0 | 35.8 | 35.8 | 4833 | 5060 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 | 230 | 0.5 |  | 0 |  |  | 12 | 410 | 390 | 0 | 6610 | 6610 | 418067.48 | 08 | 9 | D
DDRD |  | 2025-08-09 17:02 | NS 5pm | SF25_DDRD001 |  | 3 | 390 |  |  | 0 | 57.8 | 84.6 | 26.8 |  |  | 0 |  |  | 0 | 0 | 26.8 | 26.8 | 3618 | 3618 |  |  |  |  | 0 | 7 | 0.25 | 115 | 0.5 | 4.25 | 45.125 |  |  | 12 | 1825 | 527.5 | 137.5 | 5970.5 | 5970.5 | 424037.98 | 08 | 9 | N
DDRD | 1 | 2025-08-10 05:02 | DS 5am | SF25_DDRD001 | SF25_DDGT001 | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 390 |  | 424427.98 | 08 | 10 | D
|  | 2025-08-10 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 10 | N
|  | 2025-08-11 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 11 | D
|  | 2025-08-11 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 11 | N
|  | 2025-08-12 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 12 | D
|  | 2025-08-12 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 12 | N
|  | 2025-08-13 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 13 | D
|  | 2025-08-13 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 13 | N
|  | 2025-08-14 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 14 | D
|  | 2025-08-14 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 14 | N
|  | 2025-08-15 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 15 | D
|  | 2025-08-15 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 15 | N
|  | 2025-08-16 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 16 | D
|  | 2025-08-16 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 16 | N
|  | 2025-08-17 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 17 | D
|  | 2025-08-17 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 17 | N
|  | 2025-08-18 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 18 | D
|  | 2025-08-18 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 18 | N
|  | 2025-08-19 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 19 | D
|  | 2025-08-19 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 19 | N
|  | 2025-08-20 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 20 | D
|  | 2025-08-20 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 20 | N
|  | 2025-08-21 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 21 | D
|  | 2025-08-21 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 21 | N
|  | 2025-08-22 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 22 | D
|  | 2025-08-22 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 22 | N
|  | 2025-08-23 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 23 | D
|  | 2025-08-23 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 23 | N
|  | 2025-08-24 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 24 | D
|  | 2025-08-24 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 24 | N
|  | 2025-08-25 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 25 | D
|  | 2025-08-25 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 25 | N
|  | 2025-08-26 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 26 | D
|  | 2025-08-26 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 26 | N
|  | 2025-08-27 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 27 | D
|  | 2025-08-27 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 27 | N
|  | 2025-08-28 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 28 | D
|  | 2025-08-28 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 28 | N
|  | 2025-08-29 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 29 | D
|  | 2025-08-29 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 29 | N
|  | 2025-08-30 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 30 | D
|  | 2025-08-30 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 30 | N
|  | 2025-08-31 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 31 | D
|  | 2025-08-31 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 08 | 31 | N
|  | 2025-09-01 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 1 | D
|  | 2025-09-01 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 1 | N
|  | 2025-09-02 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 2 | D
|  | 2025-09-02 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 2 | N
|  | 2025-09-03 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 3 | D
|  | 2025-09-03 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 3 | N
|  | 2025-09-04 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 4 | D
|  | 2025-09-04 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 4 | N
|  | 2025-09-05 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 5 | D
|  | 2025-09-05 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 5 | N
|  | 2025-09-06 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 6 | D
|  | 2025-09-06 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 6 | N
|  | 2025-09-07 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 7 | D
|  | 2025-09-07 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 7 | N
|  | 2025-09-08 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 8 | D
|  | 2025-09-08 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 8 | N
|  | 2025-09-09 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 9 | D
|  | 2025-09-09 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 9 | N
|  | 2025-09-10 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 10 | D
|  | 2025-09-10 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 10 | N
|  | 2025-09-11 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 11 | D
|  | 2025-09-11 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 11 | N
|  | 2025-09-12 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 12 | D
|  | 2025-09-12 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 12 | N
|  | 2025-09-13 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 13 | D
|  | 2025-09-13 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 13 | N
|  | 2025-09-14 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 14 | D
|  | 2025-09-14 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 14 | N
|  | 2025-09-15 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 15 | D
|  | 2025-09-15 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 15 | N
|  | 2025-09-16 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 16 | D
|  | 2025-09-16 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 16 | N
|  | 2025-09-17 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 17 | D
|  | 2025-09-17 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 17 | N
|  | 2025-09-18 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 18 | D
|  | 2025-09-18 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 18 | N
|  | 2025-09-19 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 19 | D
|  | 2025-09-19 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 19 | N
|  | 2025-09-20 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 20 | D
|  | 2025-09-20 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 20 | N
|  | 2025-09-21 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 21 | D
|  | 2025-09-21 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 21 | N
|  | 2025-09-22 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 22 | D
|  | 2025-09-22 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 22 | N
|  | 2025-09-23 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 23 | D
|  | 2025-09-23 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 23 | N
|  | 2025-09-24 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 24 | D
|  | 2025-09-24 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 24 | N
|  | 2025-09-25 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 25 | D
|  | 2025-09-25 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 25 | N
|  | 2025-09-26 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 26 | D
|  | 2025-09-26 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 26 | N
|  | 2025-09-27 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 27 | D
|  | 2025-09-27 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 27 | N
|  | 2025-09-28 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 28 | D
|  | 2025-09-28 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 28 | N
|  | 2025-09-29 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 29 | D
|  | 2025-09-29 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 29 | N
|  | 2025-09-30 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 30 | D
|  | 2025-09-30 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 09 | 30 | N
|  | 2025-10-01 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 1 | D
|  | 2025-10-01 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 1 | N
|  | 2025-10-02 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 2 | D
|  | 2025-10-02 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 2 | N
|  | 2025-10-03 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 3 | D
|  | 2025-10-03 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 3 | N
|  | 2025-10-04 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 4 | D
|  | 2025-10-04 17:02 | NS 5pm | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 4 | N
|  | 2025-10-05 05:02 | DS 5am | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  | 424427.98 | 010 | 5 | D
|  | 2025-10-05 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-06 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-06 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-07 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-07 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-08 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-08 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-09 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-09 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-10 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-10 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-11 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-11 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-12 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-12 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-13 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-13 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-14 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-14 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-15 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-15 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-16 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-16 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-17 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-17 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-18 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-18 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-19 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-19 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-20 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-20 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-21 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-21 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-22 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-22 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-23 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-23 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-24 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-24 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-25 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-25 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-26 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-26 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-27 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-27 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-28 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-28 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-29 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-29 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-30 05:02 | DS 5am | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | 2025-10-30 17:02 | NS 5pm | [16 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0
|  | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | 0 | 0 |  |  | #VALUE! |  | END OF SHEET | END OF SHEET | END OF SHEET | 0 | END OF SHEET | END OF SHEET |  | END OF SHEET | END OF SHEET |  | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET |  | END OF SHEET | END OF SHEET |  | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET
Note on N1: Thomas Pilote: Won't charge us extra for the triple tube
Note on T1: Thomas Pilote: Won't charge us extra for the triple tube
Note on Y2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: make sure you fill down. check the cost against coreplan.

## DDH1 RIG 38
[5 empty] | Holes Completed: | 25 |  | Accom | 43680 |  | Sum PQ | 759.1 |  | Sum HQ | 1473.6 | [7 empty] | Drilling Cost | 382495.5 |  |  |  | Tool Cost | 37625 | [10 empty] | Total Activity Costs | 190655 | Total Consumable Costs | 47998.76 | 702454.26
|  | RIG 38 | [5 empty] | Rate | 130 | Hole 1 |  | 175 |  |  | 135 | Hole 2 |  | 175 |  |  | 135 |  |  |  | 175 | 155 | 420 |  |  | 460 | 460 |  | 360 | 360
[5 empty] | Hole 1 | Hole 2 |  |  |  | PQ3 |  |  | HQ3 |  |  | PQ3 |  |  | HQ3 |  |  |  |  | Slow Pen rate Normalised | [11 empty] | 0 | 0 | [12 empty] | 379.8888 | 421.0496
| Purpose | Hole Type | Date | Shift | Hole ID | Hole ID | Driller Name | Personel (incl driller) | Accom Cost | Depth From | Depth To | Length | Depth From | Depth To | Length | Depth From | Depth To | Length | Depth From | Depth To | Length | Total Length | Drilling Cost | Charged Drilling Cost | PQ Ori Tool | HQ Ori Tool | Gyro Tool | Tool ID | Tool Hire Cost | Drill Time | Active hours (Other than drilling) | Comment (IF less than 10hours EXPLAIN) | Inactive Hours (Other than client standby) | Standby Total Hours | Comment (IF more than 2 hours EXPLAIN) | Uncharged Hours | Maintenance | Comments | Total Daily Hours | Comments (IF not 12hrs EXPLAIN) | Total Activity Hours Cost | ***Insert Total Consumable Costs*** | Total Consumables Cost (-accom) | Total Costs | Plod Cost (Comparison) |  | 0.21377 | Cummulative Cost | EOM Cummulative Cost | All in Cost Per Metre | PLOD LINK | Comments | Stem | Year | Month | Day | Shift Shorthand
|  | Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 |  | 22 | 23 | 24 |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 |  | 33 | 34 | 35 |  | 36 | 37 |  |  |  | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71
#N/A |  |  | 2025-07-05 05:02 | DS 5am | [10 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 1 | 1 |  |  | 0 | 0 |  | 3.5 |  | Unpacking rig after mobilisation | 8.5 |  |  | 12 |  | 1260 |  |  | 1260 |  | 0 |  | Cummulative Cost 38: 3780; EOM Cummulative Cost 39: 3780; PLOD LINK 41: LINK; Comments 42: Mobilising from timber creek to doon doon road house, unload caravans and the road train at the road house, move gear to site, unload lay down at site, site inspections, travel back to doon doon for accommodation.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250706D; Shift Shorthand 49: 2025-07
#N/A |  |  | 2025-07-05 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [8 empty] | 0 | 0 |  | 3.5 |  | Unpacking rig after mobilisation | 7.5 |  |  | 11 |  | 1260 |  |  | 1260 |  | 0 |  | Cummulative Cost 38: 2520; EOM Cummulative Cost 39: 2520; PLOD LINK 41: LINK; Comments 42: Mobilising from timber creek to doon doon road house, unload caravans and the road train at the road house, move gear to site, unload lay down at site, site inspections, travel back to doon doon for accommodation.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250706N; Shift Shorthand 49: 2025-07
#N/A |  |  | 2025-07-06 05:02 | DS 5am | [10 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  |  | 1 | 1 |  |  | 0 | 0 |  | 3.5 |  | Unpacking rig after mobilisation | 8.5 |  |  | 12 |  | 1260 |  |  | 1260 | 1260 | 0 |  | Cummulative Cost 38: 1260; EOM Cummulative Cost 39: 1260; PLOD LINK 41: LINK; Comments 42: Mobilising from timber creek to doon doon road house, unload caravans and the road train at the road house, move gear to site, unload lay down at site, site inspections, travel back to doon doon for accommodation.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250707D; Shift Shorthand 49: 2025-07; Shift Shorthand 51: MET; Shift Shorthand 52: GT; Shift Shorthand 54: MET; Shift Shorthand 55: 1
#N/A |  |  | 2025-07-06 17:02 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [19 empty] | 0 |  |  | 0 | 0 | 0 |  | Cummulative Cost 38: 1260; All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: No NS; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250707N; Shift Shorthand 49: 2025-07; Shift Shorthand 51: 396.7388; Shift Shorthand 52: 426.6299; Shift Shorthand 54: GT; Shift Shorthand 55: 1
M 80/269 | Met | MET | 2025-07-07 05:02 | DS 5am | SF25_DMET023 |  | Melville, Dean | 6 | 780 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 13170 | 575 | 0 | 8.25 |  | 2 |  |  | 1.75 |  |  | 12 |  | 4515 |  | 761 | 6631 | 6631 | 2116 | 0.68089 | Cummulative Cost 38: 7891; EOM Cummulative Cost 39: 7891; PLOD LINK 41: LINK; Comments 42: travel to site from doon doon, unload trucks at laydown, brad meikle/ carl jonas travel to kununurra to pick up bed vans, pack gear for rig, move rig and gear onto drill pad, set up rig on azi, mast shot survey, start setting up drill site, run poly to drill pad, start filling sumps.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250708D; Shift Shorthand 49: 2025-07; Shift Shorthand 54: DDRD; Shift Shorthand 55: 1
#N/A |  |  | 2025-07-07 17:02 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 | [11 empty] | 0 |  |  | 0 | 0 | 0 |  | Cummulative Cost 38: 7891; All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250708N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-08 05:02 | DS 5am | SF25_DMET023 |  | Melville, Dean | 3 | 390 | 0 | 11 | 11 |  |  | 0 |  |  | 0 |  |  | 0 | 11 | 1925 | 1955 |  | 1 | 1 | 13170 | 575 | 4.25 | 7 |  | 0.75 | [5 empty] | 12 |  | 3490 |  | 686.34 | 7096.34 | 7096.34 | 3606.34 | 0.4918 | Cummulative Cost 38: 14987.34; EOM Cummulative Cost 39: 14987.34; All in Cost Per Metre 40: 645.1218; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250709D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-08 17:02 | NS 5pm | SF25_DMET023 |  | Zeke Shackelton | 3 | 390 | 11 | 26.6 | 15.6 |  |  | 0 |  |  | 0 |  |  | 0 | 15.6 | 2730 | 3335 |  |  |  |  | 0 | 7.25 | 1.5 |  | 0.25 |  |  | 3 |  |  | 12 |  | 780 |  | 117.93 | 4622.93 | 4622.93 | 3842.93 | 0.16872 | Cummulative Cost 38: 19610.27; EOM Cummulative Cost 39: 19610.27; All in Cost Per Metre 40: 296.3417; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250709N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-09 05:02 | DS 5am | SF25_DMET023 |  | Matthew Sing | 3 | 390 | 26.6 | 33.7 | 7.1 |  |  | 0 |  |  | 0 |  |  | 0 | 7.1 | 1242.5 | 1380 |  | 1 | 1 | 13170 | 575 | 3 | 0.25 |  | 0.25 |  |  | 8.5 |  |  | 12 |  | 205 |  | 0 | 2550 | 2550 | 2345 | 0.080392 | Cummulative Cost 38: 22160.27; EOM Cummulative Cost 39: 22160.27; All in Cost Per Metre 40: 359.1549; PLOD LINK 41: LINK; Comments 42: Crew change, Pre-shift meeting, Pre-start all equipment, continue to dill PQ3 through broken ground, condition hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250710D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-09 17:02 | NS 5pm | SF25_DMET023 |  | Ben Payton | 3 | 390 | 33.7 | 63.7 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 |  | 117.93 | 6282.93 | 6282.93 | 5757.93 | 0.08356 | Cummulative Cost 38: 28443.2; EOM Cummulative Cost 39: 28443.2; All in Cost Per Metre 40: 209.431; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250710N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-10 05:02 | DS 5am | SF25_DMET023 |  | Matthew Sing | 3 | 390 | 63.7 | 84.1 | 20.4 |  |  | 0 |  |  | 0 |  |  | 0 | 20.4 | 3570 | 5060 |  | 1 | 1 | 13170 | 575 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 |  | 427.99 | 6862.99 | 6862.99 | 6452.99 | 0.059741 | Cummulative Cost 38: 35306.19; EOM Cummulative Cost 39: 35306.19; All in Cost Per Metre 40: 336.4211; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250711D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-10 17:02 | NS 5pm | SF25_DMET023 |  | Ben Payton | 3 | 390 | 84.1 | 99.7 | 15.6 |  |  | 0 |  |  | 0 |  |  | 0 | 15.6 | 2730 | 3105 |  |  |  |  | 0 | 6.75 | 4.75 | Change bit - dropped PVC casing down hole. | 0.5 | [5 empty] | 12 |  | 2365 |  | 776.68 | 6636.68 | 6636.68 | 4271.68 | 0.35635 | Cummulative Cost 38: 41942.87; EOM Cummulative Cost 39: 41942.87; All in Cost Per Metre 40: 425.4282; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250711N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-11 05:02 | DS 5am | SF25_DMET023 |  | Matthew Sing | 3 | 390 | 99.7 | 118.7 | 19 |  |  | 0 |  |  | 0 |  |  | 0 | 19 | 3325 | 3910 |  | 1 | 1 | 13170 | 575 | 8.5 | 3 | Move hole | 0.5 | [5 empty] | 12 |  | 1560 |  |  | 6435 | 6435 | 4875 | 0.24242 | Cummulative Cost 38: 48377.87; EOM Cummulative Cost 39: 48377.87; All in Cost Per Metre 40: 338.6842; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250712D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-11 17:02 | NS 5pm | SF25_DMET022 |  | Ben Payton | 3 | 390 | 0 | 16.5 | 16.5 |  |  | 0 |  |  | 0 |  |  | 0 | 16.5 | 2887.5 | 3335 |  |  |  |  | 0 | 7.25 | 4.25 | Setting up pad | 0.5 | [5 empty] | 12 |  | 2135 |  | 396.12 | 6256.12 | 6256.12 | 4121.12 | 0.34127 | Cummulative Cost 38: 54633.99; EOM Cummulative Cost 39: 54633.99; All in Cost Per Metre 40: 379.1588; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250712N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-12 05:02 | DS 5am | SF25_DMET022 |  | Matthew Sing | 3 | 390 | 16.5 | 39.4 | 22.9 |  |  | 0 |  |  | 0 |  |  | 0 | 22.9 | 4007.5 | 4945 |  | 1 | 1 | 13170 | 575 | 10.75 | 0.25 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 295 |  | 151.79 | 6356.79 | 6356.79 | 6061.79 | 0.046407 | Cummulative Cost 38: 60990.78; EOM Cummulative Cost 39: 60990.78; All in Cost Per Metre 40: 277.5891; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250713D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-12 17:02 | NS 5pm | SF25_DMET022 |  | Ben Payton | 3 | 390 | 39.4 | 60.6 | 21.2 |  |  | 0 |  |  | 0 |  |  | 0 | 21.2 | 3710 | 3910 |  |  |  |  | 0 | 8.5 | 2.5 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 1330 |  | 117.93 | 5747.93 | 5747.93 | 4417.93 | 0.23139 | Cummulative Cost 38: 66738.71; EOM Cummulative Cost 39: 66738.71; All in Cost Per Metre 40: 271.1288; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250713N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-13 05:02 | DS 5am | SF25_DMET022 |  | Matthew Sing | 3 | 390 | 60.6 | 73.8 | 13.2 |  |  | 0 |  |  | 0 |  |  | 0 | 13.2 | 2310 | 4025 |  | 1 | 1 | 13170 | 575 | 8.75 | 2.75 |  | 0.5 | [5 empty] | 12 |  | 1445 |  | 53.23 | 6488.23 | 6488.23 | 5043.23 | 0.22271 | Cummulative Cost 38: 73226.94; EOM Cummulative Cost 39: 73226.94; All in Cost Per Metre 40: 491.5326; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250714D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-13 17:02 | NS 5pm | SF25_DMET022 |  | Ben Payton | 3 | 390 | 73.8 | 101.1 | 27.3 |  |  | 0 |  |  | 0 |  |  | 0 | 27.3 | 4777.5 | 5060 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 |  | 117.93 | 5977.93 | 5977.93 | 5567.93 | 0.068586 | Cummulative Cost 38: 79204.87; EOM Cummulative Cost 39: 79204.87; All in Cost Per Metre 40: 218.9718; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250714N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-14 05:02 | DS 5am | SF25_DMET022 |  | Matthew Sing | 3 | 390 | 101.1 | 120.7 | 19.6 |  |  | 0 |  |  | 0 |  |  | 0 | 19.6 | 3430 | 3680 |  | 1 | 1 | 13170 | 575 | 8 | 3.5 | rig move | 0.5 | [5 empty] | 12 |  | 1790 |  |  | 6435 | 6435 | 4645 | 0.27817 | Cummulative Cost 38: 85639.87; EOM Cummulative Cost 39: 85639.87; All in Cost Per Metre 40: 328.3163; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to drill PQ3, survey @ 108m and 117m, drill to EOH @ 120.7m, move equipment to bring in ST and pull out barrel, mast down, pack up site and move equipment to next hole, mast up and take mast shot, start setting up site; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250715D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-14 17:02 | NS 5pm | SF25_DMET021 |  | Ben Payton | 3 | 390 | 0 | 20.5 | 20.5 |  |  | 0 |  |  | 0 |  |  | 0 | 20.5 | 3587.5 | 3795 |  |  |  |  | 0 | 8.25 | 3.25 |  | 0.5 | [5 empty] | 12 |  | 1675 |  | 235.86 | 6095.86 | 6095.86 | 4420.86 | 0.27478 | Cummulative Cost 38: 91735.73; EOM Cummulative Cost 39: 91735.73; All in Cost Per Metre 40: 297.359; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Set up site / Drill PQ3 from surface / Ream 6.0m of PWT casing in hole as ground too hard from surface for Rock roller & PVC / Flush Hole clean / Drill on PQ3 DR38, RT38, LP10, ST25, LT95, DDH1 DL219; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250715N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-15 05:02 | DS 5am | SF25_DMET021 |  | Matthew Sing | 3 | 390 | 20.5 | 50.5 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 |  | 1 | 1 | 13170 | 575 | 10.5 | 1 |  | 0.5 | [5 empty] | 12 |  | 640 |  | 879.56 | 7734.56 | 7734.56 | 7094.56 | 0.082745 | Cummulative Cost 38: 99470.29; EOM Cummulative Cost 39: 99470.29; All in Cost Per Metre 40: 257.8187; PLOD LINK 41: LINK; Comments 42: Continue to drill PQ3, survey @ 18m & 36m, pull out and run in softer bit, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250716D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-15 17:02 | NS 5pm | SF25_DMET021 |  | Ben Payton | 3 | 390 | 50.5 | 80.6 | 30.1 |  |  | 0 |  |  | 0 |  |  | 0 | 30.1 | 5267.5 | 5267.5 |  |  |  |  | 0 | 10.25 | 1.25 |  | 0.5 | [5 empty] | 12 |  | 755 |  | 236.49 | 6648.99 | 6648.99 | 5893.99 | 0.11355 | Cummulative Cost 38: 106119.28; EOM Cummulative Cost 39: 106119.28; All in Cost Per Metre 40: 220.8967; PLOD LINK 41: LINK; Comments 42: Drill PQ3, 54m & 72m surveys of hole, bit change due to worn bit, run back in, Drill on PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250716N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-16 05:02 | DS 5am | SF25_DMET021 | SF25_DMET020 | Matthew Sing | 3 | 390 | 80.6 | 90.6 | 10 |  |  | 0 | 0 | 9 | 9 |  |  | 0 | 19 | 3325 | 3325 |  | 1 | 1 | 13170 | 575 | 6.5 | 4.5 |  | 1 | [5 empty] | 12 |  | 2430 |  |  | 6720 | 6720 | 4290 | 0.36161 | Cummulative Cost 38: 112839.28; EOM Cummulative Cost 39: 112839.28; All in Cost Per Metre 40: 353.6842; PLOD LINK 41: LINK; Comments 42: Continue to drill PQ3, survey @ 87m, drill to EOH, move equipment to bring in ST, pull out barrel, pull out casing, mast down and move rig, mast up and take mast shot, commence drilling PQ3 from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250717D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-16 17:02 | NS 5pm | SF25_DMET020 |  | Ben Payton | 3 | 390 | 9 | 30.8 | 21.8 |  |  | 0 |  |  | 0 |  |  | 0 | 21.8 | 3815 | 4025 |  |  |  |  | 0 | 8.75 | 2.75 |  | 0.5 | [5 empty] | 12 |  | 1445 |  | 396.12 | 6256.12 | 6256.12 | 4811.12 | 0.23097 | Cummulative Cost 38: 119095.4; EOM Cummulative Cost 39: 119095.4; All in Cost Per Metre 40: 286.978; PLOD LINK 41: LINK; Comments 42: Open out hole with rock roller. Grout 6.0m 150mm PVC in place. Wait on grout to cure. Flush back to bottom, Drill on PQ3, Change out worn bit and front reamer, Survey @ 18m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250717N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-17 05:02 | DS 5am | SF25_DMET020 |  | Matthew Sing | 3 | 390 | 30.8 | 57 | 26.2 |  |  | 0 |  |  | 0 |  |  | 0 | 26.2 | 4585 | 4715 |  | 1 | 1 | 13170 | 575 | 10.25 | 1.25 |  | 0.5 | [5 empty] | 12 |  | 755 |  |  | 6435 | 6435 | 5680 | 0.11733 | Cummulative Cost 38: 125530.4; EOM Cummulative Cost 39: 125530.4; All in Cost Per Metre 40: 245.6107; PLOD LINK 41: LINK; Comments 42: continue to drill PQ3, survey @ 36m, lost water return @ 51.4m, bombed hole with no success, condition hole throughout shift, replace torn poly twice during shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250718D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-17 17:02 | NS 5pm | SF25_DMET020 |  | Ben Payton | 3 | 390 | 57 | 84.7 | 27.7 |  |  | 0 |  |  | 0 |  |  | 0 | 27.7 | 4847.5 | 4847.5 |  |  |  |  | 0 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 |  | 117.93 | 6225.43 | 6225.43 | 5355.43 | 0.13975 | Cummulative Cost 38: 131755.83; EOM Cummulative Cost 39: 131755.83; All in Cost Per Metre 40: 224.7448; PLOD LINK 41: LINK; Comments 42: Pull Rods for dead bit, Change out worn bit and both reamer / Ream barrel back to bottom of hole / Drill on PQ3 / Survey @ 54 & 72m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250718N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-18 05:02 | DS 5am | SF25_DMET020 |  | Matthew Sing | 3 | 390 | 84.7 | 90.7 | 6 |  |  | 0 |  |  | 0 |  |  | 0 | 6 | 1050 | 1610 |  | 1 | 1 | 13170 | 575 | 3.5 | 7.5 | rig move | 1 | [5 empty] | 12 |  | 3810 |  |  | 6385 | 6385 | 2575 | 0.59671 | Cummulative Cost 38: 138140.83; EOM Cummulative Cost 39: 138140.83; PLOD LINK 41: LINK; Comments 42: continue to drill PQ3, drill to EOH, survey @ 87m, move equipment to bring in ST, pull out barrel, mast down, pack up site, inspect next pads with client, move rig and equipment to next pad, setup site.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250719D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-18 17:02 | NS 5pm | SF25_DMET010 |  | Ben Payton | 3 | 390 | 0 | 14.9 | 14.9 |  |  | 0 |  |  | 0 |  |  | 0 | 14.9 | 2607.5 | 2607.5 |  |  |  |  | 0 | 5.25 | 3.75 |  | 0.5 | 2.5 |  |  |  |  | 12 |  | 2805 |  | 514.05 | 6316.55 | 6316.55 | 3511.55 | 0.44407 | Cummulative Cost 38: 144457.38; EOM Cummulative Cost 39: 144457.38; All in Cost Per Metre 40: 423.9295; PLOD LINK 41: LINK; Comments 42: Finish setting up site on tight drill pad. Wait on water supply due to being in use already. Drill PQ3 from surface. Open out hole with rock roller, Grout 6.0m 150mm PVC in place. Wait on grout to cure, Flush back to bottom; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250719N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-19 05:02 | DS 5am | SF25_DMET010 |  | Matthew Sing | 3 | 390 | 14.9 | 45.6 | 30.7 |  |  | 0 |  |  | 0 |  |  | 0 | 30.7 | 5372.5 | 5372.5 |  | 1 | 1 | 13170 | 575 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 |  |  | 6862.5 | 6862.5 | 6337.5 | 0.076503 | Cummulative Cost 38: 151319.88; EOM Cummulative Cost 39: 151319.88; All in Cost Per Metre 40: 223.5342; PLOD LINK 41: LINK; Comments 42: continue to drill PQ3, survey @ 18m & 36m, condition hole throughout shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250720D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-19 17:02 | NS 5pm | SF25_DMET010 |  | Ben Payton | 3 | 390 | 45.6 | 75.6 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10.5 | 1 |  | 0.5 | [5 empty] | 12 |  | 640 |  | 117.93 | 6397.93 | 6397.93 | 5757.93 | 0.10003 | Cummulative Cost 38: 157717.81; EOM Cummulative Cost 39: 157717.81; All in Cost Per Metre 40: 213.2643; PLOD LINK 41: LINK; Comments 42: Drill on PQ3 / Survey hole @ 54m / Pull rods and change worn bit, Run back in / Drill on PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250720N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-20 05:02 | DS 5am | SF25_DMET010 | SF25_DDGT012 | Matthew Sing | 3 | 390 | 75.6 | 81.6 | 6 | 0 | 2.3 | 2.3 |  |  | 0 |  |  | 0 | 8.3 | 1360.5 | 1495 |  | 1 | 1 | 13170 | 575 | 3.25 | 7.75 | rig move | 0.5 |  |  | 0.5 |  |  | 12 |  | 3745 |  |  | 6205 | 6205 | 2460 | 0.60355 | Cummulative Cost 38: 163922.81; EOM Cummulative Cost 39: 163922.81; All in Cost Per Metre 40: 747.5904; PLOD LINK 41: LINK; Comments 42: Drill to EOH, survey @ 78m, pad to small to pull rods straight onto ST, pull out rods and manual handle rods to truck, pack up site, move equipment to next drill pad, mast up, mast shot, setup site, commence drilling HQ3 from surface, toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250721D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-20 17:02 | NS 5pm | SF25_DDGT012 |  | Ben Payton | 3 | 390 |  |  | 0 | 2.3 | 19.8 | 17.5 |  |  | 0 |  |  | 0 | 17.5 | 2362.5 | 3335 |  |  |  |  | 0 | 7.25 | 3.75 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 1905 |  | 514.05 | 6144.05 | 6144.05 | 4239.05 | 0.31006 | Cummulative Cost 38: 170066.86; EOM Cummulative Cost 39: 170066.86; All in Cost Per Metre 40: 351.0886; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 to competent ground / Open out hole with rock roller / Grout 6.0m 150mm PVC in place / Wait on grout to cure / Flush back to bottom with HQ3 barrel / Ream HWT over HQ to 15m / Flush hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250721N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-21 05:02 | DS 5am | SF25_DDGT012 |  | Matthew Sing | 3 | 390 |  |  | 0 | 19.8 | 41.3 | 21.5 |  |  | 0 |  |  | 0 | 21.5 | 2902.5 | 4945 |  | 1 | 1 | 13170 | 575 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 |  | 151.79 | 6586.79 | 6586.79 | 6061.79 | 0.079705 | Cummulative Cost 38: 176653.65; EOM Cummulative Cost 39: 176653.65; All in Cost Per Metre 40: 306.3623; PLOD LINK 41: LINK; Comments 42: Continue to drill HQ3 through broken ground/short runs, survey @ 18m and 36m, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250722D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-21 17:02 | NS 5pm | SF25_DDGT012 |  | Ben Payton | 3 | 390 |  |  | 0 | 41.3 | 63.2 | 21.9 |  |  | 0 |  |  | 0 | 21.9 | 2956.5 | 4945 |  |  |  |  | 0 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 |  | 117.93 | 5977.93 | 5977.93 | 5452.93 | 0.087823 | Cummulative Cost 38: 182631.58; EOM Cummulative Cost 39: 182631.58; All in Cost Per Metre 40: 272.9648; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 / Broken formation/Short runs with some soft sections / Survey hole @ 54m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250722N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-22 05:02 | DS 5am | SF25_DDGT012 | SF25_DMET024 | Matthew Sing | 3 | 390 | 0 | 3.7 | 3.7 | 63.2 | 70.5 | 7.3 |  |  | 0 |  |  | 0 | 11 | 1633 | 2875 |  | 1 | 1 | 13170 | 575 | 6.25 | 5.25 |  | 0.5 | [5 empty] | 12 |  | 2595 |  |  | 6435 | 6435 | 3840 | 0.40326 | Cummulative Cost 38: 189066.58; EOM Cummulative Cost 39: 189066.58; All in Cost Per Metre 40: 585; PLOD LINK 41: LINK; Comments 42: Continue to drill HQ3 through broken ground/short runs to EOH, survey @ 66m, move equipment to bring in ST, pull out barrel, hook up flush casing, work stuck casing, pull out casing, packup site, move to next pad, mast up, mast shot, setup site, commence drilling PQ3 from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250723D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-22 17:02 | NS 5pm | SF25_DMET024 |  | Ben Payton | 3 | 390 | 3.7 | 20.1 | 16.4 |  |  | 0 |  |  | 0 |  |  | 0 | 16.4 | 2870 | 2870 |  |  |  |  | 0 | 5.75 | 2.75 |  | 0.5 |  |  | 3 |  | Crew Change | 12 |  | 1445 |  | 514.05 | 5219.05 | 5219.05 | 3774.05 | 0.27687 | Cummulative Cost 38: 194285.63; EOM Cummulative Cost 39: 194285.63; All in Cost Per Metre 40: 318.2348; PLOD LINK 41: LINK; Comments 42: Drill on PQ3 / Open out hole with rock roller / Grout 6.0m 150mm PVC in place / Wait on grout to cure / Flush back to bottom / Drill on PQ3/ crew packed up early to fly out; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250723N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-23 05:02 | DS 5am | SF25_DMET024 |  | Zeke Shackelton | 3 | 390 | 20.1 | 27.7 | 7.6 |  |  | 0 |  |  | 0 |  |  | 0 | 7.6 | 1330 | 1610 |  | 1 | 1 | 13170 | 575 | 3.5 | 0.75 | crew change | 0.5 |  |  | 7.25 |  | Crew Change | 12 |  | 525 |  |  | 3100 | 3100 | 2575 | 0.16935 | Cummulative Cost 38: 197385.63; EOM Cummulative Cost 39: 197385.63; All in Cost Per Metre 40: 407.8947; PLOD LINK 41: LINK; Comments 42: Crew Change pick up stores/ dump rubbish/ pick up food order/Pre-shift meeting / Pre-start all equipment / Drill on PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250724D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-23 17:02 | NS 5pm | SF25_DMET024 |  | Matthew Sing | 3 | 390 | 27.7 | 55.1 | 27.4 |  |  | 0 |  |  | 0 |  |  | 0 | 27.4 | 4795 | 4830 |  |  |  |  | 0 | 10.5 | 1 |  | 0.5 | [5 empty] | 12 |  | 640 |  |  | 5860 | 5860 | 5220 | 0.10922 | Cummulative Cost 38: 203245.63; EOM Cummulative Cost 39: 203245.63; All in Cost Per Metre 40: 213.8686; PLOD LINK 41: LINK; Comments 42: continue to drill PQ3, survey @ 36m, pull out of hole for bit change, run back in and continue to drill PQ3, condition hole throughout shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250724N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-24 05:02 | DS 5am | SF25_DMET024 |  | Zeke Shackelton | 3 | 390 | 55.1 | 84.7 | 29.6 |  |  | 0 |  |  | 0 |  |  | 0 | 29.6 | 5180 | 5180 |  | 1 | 1 | 13170 | 575 | 10.5 | 1 |  | 0.5 | [5 empty] | 12 |  | 640 |  | 256.06 | 7041.06 | 7041.06 | 6401.06 | 0.090895 | Cummulative Cost 38: 210286.69; EOM Cummulative Cost 39: 210286.69; All in Cost Per Metre 40: 237.8736; PLOD LINK 41: LINK; Comments 42: Drill on PQ3 / lost water at 69m pumped three lc stop plugs with SureSeal still losing a lot of water / fixed key start on pump / survey hole at 54m 72 m / housekeeping and maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250725D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-24 17:02 | NS 5pm | SF25_DMET024 |  | Matthew Sing | 3 | 390 | 84.7 | 101.1 | 16.4 |  |  | 0 |  |  | 0 |  |  | 0 | 16.4 | 2870 | 3335 |  |  |  |  | 0 | 7.25 | 4.25 |  | 0.5 | [5 empty] | 12 |  | 2135 |  |  | 5860 | 5860 | 3725 | 0.36433 | Cummulative Cost 38: 216146.69; EOM Cummulative Cost 39: 216146.69; All in Cost Per Metre 40: 357.3171; PLOD LINK 41: LINK; Comments 42: continue to drill PQ3, survey @ 90m and 96m, drill to EOH, move equipment to bring in ST, pull out barrel, pack up site, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250725N; Shift Shorthand 49: 2025-07
E 80/2863-I | Geotech | GT | 2025-07-25 05:02 | DS 5am | SF25_DDGT006 |  | Zeke Shackelton | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 13170 | 575 | 0 | 7.5 | delay getting water to rig at TSF | 4.5 |  | delay getting water to rig at TSF |  |  |  | 12 |  | 5070 |  | 256.06 | 6291.06 | 6291.06 | 1221.06 | 0.80591 | Cummulative Cost 38: 222437.75; EOM Cummulative Cost 39: 222437.75; PLOD LINK 41: LINK; Comments 42: move to site, set up site, set up spt and Shelby sampling, standby for water delays due to no water supply close to pad.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250726D; Shift Shorthand 49: 2025-07
E 80/2863-I | Geotech | GT | 2025-07-25 17:02 | NS 5pm | SF25_DDGT006 |  | Matthew Sing | 3 | 390 |  |  | 0 | 6 | 13.8 | 7.8 |  |  | 0 |  |  | 0 | 7.8 | 1053 | 1840 |  |  |  |  | 0 | 4 | 3 | delay getting water to rig at TSF | 5 |  | delay getting water to rig at TSF |  |  |  | 12 |  | 3180 |  |  | 5410 | 5410 | 2230 | 0.5878 | Cummulative Cost 38: 227847.75; EOM Cummulative Cost 39: 227847.75; All in Cost Per Metre 40: 693.5897; PLOD LINK 41: LINK; Comments 42: continue with geo tech, shelby tube refusal at 6m, continue to drill HQ3 to 15m as per hole plan notes, broken ground/short runs, water delays throughout shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250726N; Shift Shorthand 49: 2025-07
E 80/2863-I | Geotech | GT | 2025-07-26 05:02 | DS 5am | SF25_DDGT006 | SF25_DDGT005 | Zeke Shackelton | 3 | 390 |  |  | 0 | 13.8 | 15 | 1.2 |  |  | 0 | 0 | 2 | 2 | 3.2 | 432 | 1265 |  | 1 | 1 | 13170 | 575 | 2.75 | 6.75 | delay getting water to rig at TSF | 2.5 |  | delay getting water to rig at TSF |  |  |  | 12 |  | 4005 |  |  | 6235 | 6235 | 2230 | 0.64234 | Cummulative Cost 38: 234082.75; EOM Cummulative Cost 39: 234082.75; PLOD LINK 41: LINK; Comments 42: Stuck rods due to water delay, reamed over barrel free up rods, continued drill hq3, pull out barrel, pull out casing, pack up site, move rig and equipment to next pad, mast up, Set up site for spt and Shelby sampling, commence sampling from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250727D; Shift Shorthand 49: 2025-07
E 80/2863-I | Geotech | GT | 2025-07-26 17:02 | NS 5pm | SF25_DDGT005 |  | Matthew Sing | 3 | 390 |  |  | 0 | 2 | 15 | 13 |  |  | 0 |  |  | 0 | 13 | 1755 | 2300 |  |  |  |  | 0 | 5 | 2.5 | delay getting water to rig at TSF | 4.5 |  | hydro rig in the way of moving to next pad |  |  |  | 12 |  | 2770 |  |  | 5460 | 5460 | 2690 | 0.50733 | Cummulative Cost 38: 239542.75; EOM Cummulative Cost 39: 239542.75; All in Cost Per Metre 40: 420; PLOD LINK 41: LINK; Comments 42: continue with geo tech sampling, Shelby tube refusal at 2m - 2.5m, continue to HQ3 coring to 15m as per hole plan, survey EOH, pull out barrel, pack up site, went to move rig and equipment to next pad however another rig blocking access.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250727N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-27 05:02 | DS 5am | SF25_DDGT011 |  | Zeke Shackelton | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 13170 | 575 | 0 | 6 | standby waiting for hydro rig to move off access point to next pad | 0.5 | 5 | hydro rig in the way of moving to next pad | 0.5 |  |  | 12 |  | 4740 |  |  | 5705 | 5705 | 965 | 0.83085 | Cummulative Cost 38: 245247.75; EOM Cummulative Cost 39: 245247.75; PLOD LINK 41: LINK; Comments 42: pull out barrel, pull out casing, pack up site, move rig and equipment to next pad, mast up, Set up site, toolbox at EOS; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250728D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-27 17:02 | NS 5pm | SF25_DDGT011 |  | Matthew Sing | 3 | 390 |  |  | 0 | 0 | 21.3 | 21.3 |  |  | 0 |  |  | 0 | 21.3 | 2875.5 | 3335 |  |  |  |  | 0 | 7.25 | 3.75 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 1905 | 1076.61 | 686.61 | 6316.61 | 6316.61 | 4411.61 | 0.30159 | Cummulative Cost 38: 251564.36; EOM Cummulative Cost 39: 251564.36; All in Cost Per Metre 40: 296.5545; PLOD LINK 41: LINK; Comments 42: Toolbox meeting at SOS, continue site setup, commence drilling HQ3 from surface, drilling shorter runs with basket lifters to reduce core loss, pull out barrel and run in rock roller, install PVC collar, run in 9m HWT casing, continue to drill HQ3, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250728N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-28 05:02 | DS 5am | SF25_DDGT011 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 21.3 | 51.7 | 30.4 |  |  | 0 |  |  | 0 | 30.4 | 4104 | 5060 |  | 1 | 1 | 13170 | 575 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 |  | 6435 | 6435 | 6025 | 0.063714 | Cummulative Cost 38: 257999.36; EOM Cummulative Cost 39: 257999.36; All in Cost Per Metre 40: 211.6776; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, drill hq3, survey 18m 36m, grease trucks and blew air filters, housekeeping; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250729D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-28 17:02 | NS 5pm | SF25_DDGT011 |  | Matthew Sing | 3 | 390 |  |  | 0 | 51.7 | 78.7 | 27 |  |  | 0 |  |  | 0 | 27 | 3645 | 4945 |  |  |  |  | 0 | 10.75 | 0.25 |  | 0.5 |  |  |  | 0.5 | Breakdown of hydraulic pump | 12 |  | 295 | 390 |  | 5630 | 5630 | 5335 | 0.052398 | Cummulative Cost 38: 263629.36; EOM Cummulative Cost 39: 263629.36; All in Cost Per Metre 40: 208.5185; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250729N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-29 05:02 | DS 5am | SF25_DDGT011 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 78.7 | 92.7 | 14 |  |  | 0 |  |  | 0 | 14 | 1890 | 2645 |  | 1 | 1 | 13170 | 575 | 5.75 | 0.25 | Breakdown - hydraulic pump not | 0.5 |  |  |  | 5.5 | Breakdown of hydraulic pump | 12 |  | 295 | 390 |  | 3905 | 3905 | 3610 | 0.075544 | Cummulative Cost 38: 267534.36; EOM Cummulative Cost 39: 267534.36; All in Cost Per Metre 40: 278.9286; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250730D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-29 17:02 | NS 5pm | SF25_DDGT011 |  | Matthew Sing | 3 | 390 |  |  | 0 | 92.7 | 107.7 | 15 |  |  | 0 |  |  | 0 | 15 | 2025 | 3680 |  |  |  |  | 0 | 8 | 0.5 | Breakdown - hydraulic pump not | 0.5 |  |  |  | 3 | Breakdown of hydraulic pump | 12 |  | 410 | 527.5 | 137.5 | 4617.5 | 4617.5 | 4207.5 | 0.088793 | Cummulative Cost 38: 272151.86; EOM Cummulative Cost 39: 272151.86; All in Cost Per Metre 40: 307.8333; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to drill HQ3, maintenance - replace pumps and test, continue to drill HQ3 through broken ground, lost water return @ 99.3m, bombed hole twice, regained water return; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250730N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-30 05:02 | DS 5am | SF25_DDGT011 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 107.7 | 130 | 22.3 |  |  | 0 |  |  | 0 | 22.3 | 3010.5 | 4370 |  | 1 | 1 | 13170 | 575 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 390 |  | 6385 | 6385 | 5335 | 0.16445 | Cummulative Cost 38: 278536.86; EOM Cummulative Cost 39: 278536.86; All in Cost Per Metre 40: 286.3229; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 31; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250731D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-30 17:02 | NS 5pm | SF25_DDGT011 | SF25_DDGT002 | Matthew Sing | 3 | 390 |  |  | 0 | 0 | 1.7 | 1.7 |  |  | 0 |  |  | 0 | 1.7 | 229.5 | 345 |  |  |  |  | 0 | 0.75 | 6.5 |  | 4.75 | [5 empty] | 12 |  | 4700 | 390 |  | 5435 | 5435 | 735 | 0.86477 | Cummulative Cost 38: 283971.86; EOM Cummulative Cost 39: 283971.86; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 07; Day 46: 31; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250731N; Shift Shorthand 49: 2025-07
E 80/2863-I | Geotech | GT | 2025-07-31 05:02 | DS 5am | SF25_DDGT006 |  | Zeke Shackelton | 3 | 390 | 0 | 6.4 | 6.4 |  |  | 0 |  |  | 0 |  |  | 0 | 6.4 | 1120 | 1840 |  | 1 | 1 | 13170 | 575 | 4 | 4.5 | Slow drilling due to geotech shelby tubing and hole move | 3.5 | [5 empty] | 12 |  | 3330 | 390 |  | 6135 | 6135 | 2805 | 0.54279 | Cummulative Cost 38: 290106.86; EOM Cummulative Cost 39: 290106.86; All in Cost Per Metre 40: 958.5938; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250801D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-31 17:02 | NS 5pm | SF25_DMET018 |  | Matthew Sing | 3 | 390 | 1.2 | 15.5 | 14.3 |  |  | 0 |  |  | 0 |  |  | 0 | 14.3 | 2502.5 | 4255 |  |  |  |  | 0 | 9.25 | 2.25 |  | 0.5 | [5 empty] | 12 |  | 1215 | 14376.12 | 13986.12 | 19846.12 | 19846.12 | 18631.12 | 0.061221 | Cummulative Cost 38: 309952.98; EOM Cummulative Cost 39: 309952.98; All in Cost Per Metre 40: 1387.8406; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250801N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-08-01 05:02 | DS 5am | SF25_DMET018 |  | Zeke Shackelton | 3 | 390 | 15.5 | 45.5 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 |  | 6800 | 6800 | 6390 | 0.060294 | Cummulative Cost 38: 316752.98; EOM Cummulative Cost 39: 6800; All in Cost Per Metre 40: 226.6667; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, drilled PQ3, survey hole at 18m 36m, housekeeping and maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250802D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-01 17:02 | NS 5pm | SF25_DMET018 |  | Matthew Sing | 3 | 390 | 45.5 | 50 | 4.5 |  |  | 0 |  |  | 0 |  |  | 0 | 4.5 | 787.5 | 920 |  |  |  |  | 0 | 2 | 9.5 |  | 0.5 | [5 empty] | 12 |  | 4550 | 390 |  | 5860 | 5860 | 1310 | 0.77645 | Cummulative Cost 38: 322612.98; EOM Cummulative Cost 39: 12660; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to drill PQ3 to EOH and survey, move equipment, pull out barrel, onto rod bench and manual handle onto ST as pad too small to fit ST for EOH, pull out casing, mast down and pack up site, move rig and equipment to next pad, run poly to establish water supply, mast up, mast shot, setup site.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250802N; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-02 05:02 | DS 5am | SF25_DDGT010 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 0 | 15.7 | 15.7 |  |  | 0 |  |  | 0 | 15.7 | 2119.5 | 2990 | 1 | 1 | 1 | 13170 | 750 | 6.5 | 2 | Slow drilling in hard ground. | 1.5 | 2 | Cementing collar and waiting pre-drill inspection? |  |  |  | 12 |  | 2180 | 880.7 | 490.7 | 6800.7 | 6800.7 | 4620.7 | 0.32056 | Cummulative Cost 38: 329413.68; EOM Cummulative Cost 39: 19460.7; All in Cost Per Metre 40: 433.1656; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250803D; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-02 17:02 | NS 5pm | SF25_DDGT010 |  | Matthew Sing | 3 | 390 |  |  | 0 | 15.7 | 45.7 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4945 |  |  |  |  | 0 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 390 | 0 | 5860 | 5860 | 5335 | 0.08959 | Cummulative Cost 38: 335273.68; EOM Cummulative Cost 39: 25320.7; All in Cost Per Metre 40: 195.3333; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250803N; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-03 05:02 | DS 5am | SF25_DDGT010 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 45.7 | 75.5 | 29.8 |  |  | 0 |  |  | 0 | 29.8 | 4023 | 5060 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 6610 | 6610 | 6200 | 0.062027 | Cummulative Cost 38: 341883.68; EOM Cummulative Cost 39: 31930.7; All in Cost Per Metre 40: 221.8121; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250804D; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-03 17:02 | NS 5pm | SF25_DDGT010 |  | Matthew Sing | 3 | 390 |  |  | 0 | 75.5 | 105.7 | 30.2 |  |  | 0 |  |  | 0 | 30.2 | 4077 | 4945 |  |  |  |  | 0 | 10.75 | 0.25 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 295 | 390 | 0 | 5630 | 5630 | 5335 | 0.052398 | Cummulative Cost 38: 347513.68; EOM Cummulative Cost 39: 37560.7; All in Cost Per Metre 40: 186.4238; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250804N; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-04 05:02 | DS 5am | SF25_DDGT010 | SF25_DMET017 | Zeke Shackelton | 3 | 390 |  |  | 0 | 105.7 | 110 | 4.3 | 0 | 0 | 0 |  |  | 0 | 4.3 | 580.5 | 1840 | 1 | 1 | 1 | 13170 | 750 | 4 | 6.5 | Rig moves- water supply issues | 0.5 | 1 |  |  |  |  | 12 |  | 3530 | 390 | 0 | 6510 | 6510 | 2980 | 0.54224 | Cummulative Cost 38: 354023.68; EOM Cummulative Cost 39: 44070.7; All in Cost Per Metre 40: 1513.9535; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250805D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-04 17:02 | NS 5pm | SF25_DMET017 |  | Matthew Sing | 3 | 390 | 0 | 17.8 | 17.8 |  |  | 0 |  |  | 0 |  |  | 0 | 17.8 | 3115 | 3680 |  |  |  |  | 0 | 8 | 3.5 |  | 0.5 | [5 empty] | 12 |  | 1790 | 786.12 | 396.12 | 6256.12 | 6256.12 | 4466.12 | 0.28612 | Cummulative Cost 38: 360279.8; EOM Cummulative Cost 39: 50326.82; All in Cost Per Metre 40: 351.4674; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250805N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-05 05:02 | DS 5am | SF25_DMET017 |  | Zeke Shackelton | 3 | 390 | 17.8 | 50.1 | 32.3 |  |  | 0 |  |  | 0 |  |  | 0 | 32.3 | 5652.5 | 5652.5 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 390 | 0 | 7317.5 | 7317.5 | 6792.5 | 0.071746 | Cummulative Cost 38: 367597.3; EOM Cummulative Cost 39: 57644.32; All in Cost Per Metre 40: 226.548; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250806D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-05 17:02 | NS 5pm | SF25_DMET019 |  | Matthew Sing | 3 | 390 | 0 | 5.7 | 5.7 |  |  | 0 |  |  | 0 |  |  | 0 | 5.7 | 997.5 | 997.5 |  |  |  |  | 0 | 2 | 6.5 |  | 1.5 |  | Establish water supply | 2 |  |  | 12 |  | 3530 | 390 | 0 | 4917.5 | 4917.5 | 1387.5 | 0.71784 | Cummulative Cost 38: 372514.8; EOM Cummulative Cost 39: 62561.82; All in Cost Per Metre 40: 862.7193; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250806N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-06 05:02 | DS 5am | SF25_DMET019 |  | Ben Payton | 3 | 390 | 5.7 | 8.4 | 2.7 |  |  | 0 |  |  | 0 |  |  | 0 | 2.7 | 472.5 | 575 | 1 | 1 | 1 | 13170 | 750 | 1.25 | 1.25 |  | 0.5 | 1 |  | 8 |  |  | 12 |  | 1115 | 786.12 | 396.12 | 3226.12 | 3226.12 | 2111.12 | 0.34562 | Cummulative Cost 38: 375740.92; EOM Cummulative Cost 39: 65787.94; All in Cost Per Metre 40: 1194.8593; PLOD LINK 41: LINK; Comments 42: Crew change / Pre-shift meeting / Pre-start all equipment / Water delay / Drill onPQ3 / Open out hole with rock roller / Grout 6.0m 150mm PVC in place DR38, RT38, LP10, ST25, LT95, DDH1; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250807D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-06 17:02 | NS 5pm | SF25_DMET019 |  | Zeke Shackelton | 3 | 390 | 8.4 | 39.7 | 31.3 |  |  | 0 |  |  | 0 |  |  | 0 | 31.3 | 5477.5 | 5477.5 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 6277.5 | 6277.5 | 5867.5 | 0.065313 | Cummulative Cost 38: 382018.42; EOM Cummulative Cost 39: 72065.44; All in Cost Per Metre 40: 200.5591; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250807N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-07 05:02 | DS 5am | SF25_DMET019 | SF25_DDRD001 | Ben Payton | 3 | 390 | 39.7 | 50.4 | 10.7 |  |  | 0 |  |  | 0 |  |  | 0 | 10.7 | 1872.5 | 1872.5 | 1 | 1 | 1 | 13170 | 750 | 4 | 7.5 |  | 0.5 | [5 empty] | 12 |  | 3630 | 390 | 0 | 6642.5 | 6642.5 | 3012.5 | 0.54648 | Cummulative Cost 38: 388660.92; EOM Cummulative Cost 39: 78707.94; All in Cost Per Metre 40: 620.7944; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill on PQ3 / EOH survey @ 48m / Move rod bench and position ST / Pull rods and barrel out / Rig down / Pack up site / Move rig and equipment to new pad / Line up rig to hole requirements / Start to set up site; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250808D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-07 17:02 | NS 5pm | SF25_DDRD001 |  | Zeke Shackelton | 3 | 390 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 11.5 | Establishing water supply-polypipe | 0.5 | [5 empty] | 12 |  | 5470 | 390 | 0 | 5860 | 5860 | 390 | 0.93345 | Cummulative Cost 38: 394520.92; EOM Cummulative Cost 39: 84567.94; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, set up rig, helped rig 41 establish water then run poly as far as we could get it didn't have enough poly to make it to pad started to run water with two ibc; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250808N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-08 05:02 | DS 5am | SF25_DDRD001 |  | Ben Payton | 3 | 390 |  |  | 0 | 0 | 5 | 5 |  |  | 0 |  |  | 0 | 5 | 675 | 920 | 1 | 1 | 1 | 13170 | 750 | 2 | 0 | Establishing water supply-polypipe | 0.5 | 9.5 | Town trip for polypipe & fittings - running poly |  |  |  | 12 |  | 3600 | 5458 | 5068 | 10728 | 10728 | 7128 | 0.33557 | Cummulative Cost 38: 405248.92; EOM Cummulative Cost 39: 95295.94; All in Cost Per Metre 40: 2145.6; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250809D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-08 17:02 | NS 5pm | SF25_DDRD001 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 5 | 22 | 17 |  |  | 0 |  |  | 0 | 17 | 2295 | 4025 |  |  |  |  | 0 | 8.75 | 2.75 | Establishing water supply-polypipe | 0.5 | [5 empty] | 12 |  | 1445 | 738.56 | 348.56 | 6208.56 | 6208.56 | 4763.56 | 0.23274 | Cummulative Cost 38: 411457.48; EOM Cummulative Cost 39: 101504.5; All in Cost Per Metre 40: 365.2094; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250809N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-09 05:02 | DS 5am | SF25_DDRD001 |  | Ben Payton | 3 | 390 |  |  | 0 | 22 | 57.8 | 35.8 |  |  | 0 |  |  | 0 | 35.8 | 4833 | 5060 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 6610 | 6610 | 6200 | 0.062027 | Cummulative Cost 38: 418067.48; EOM Cummulative Cost 39: 108114.5; All in Cost Per Metre 40: 184.6369; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill on HQ3 / Survey hole x 2, 36m & 54m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250810D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-09 17:02 | NS 5pm | SF25_DDRD001 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 57.8 | 84.6 | 26.8 |  |  | 0 |  |  | 0 | 26.8 | 3618 | 3618 |  |  |  |  | 0 | 7 | 0.25 |  | 0.5 | 4.25 | lost water returns pumped 4 plugs down tried to get the water back no return, had to wait for sumps to fill two times |  |  |  | 12 |  | 1825 | 527.5 | 137.5 | 5970.5 | 5970.5 | 4145.5 | 0.30567 | Cummulative Cost 38: 424037.98; EOM Cummulative Cost 39: 114085; All in Cost Per Metre 40: 222.7799; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, drilled hq3, lost water returns pumped 4 plugs down tried to get the water back no return, had to wait for sumps to fill two times, survey at 72m housekeeping and maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250810N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-10 05:02 | DS 5am | SF25_DDRD001 | SF25_DDGT001 | Ben Payton | 3 | 390 |  |  | 0 | 84.6 | 90.6 | 6 |  |  | 0 | 0 | 0 | 0 | 6 | 810 | 810 | 1 | 1 | 1 | 13170 | 750 | 1.75 | 9.25 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 4435 | 390 | 0 | 6385 | 6385 | 1950 | 0.6946 | Cummulative Cost 38: 430422.98; EOM Cummulative Cost 39: 120470; All in Cost Per Metre 40: 1064.1667; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill on HQ3 / Survey hole @ 87m / Move rod bench and position ST / Pull rods, barrel & casing out / Rig down / Pack up site / Move rig and equipment to new pad / Line up rig to hole requirements / Set up drill site; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250811D; Shift Shorthand 49: 2025-08
M 80/268 | Geotech | GT | 2025-08-10 17:02 | NS 5pm | SF25_DDGT001 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 0 | 21.7 | 21.7 |  |  | 0 |  |  | 0 | 21.7 | 2929.5 | 4600 |  |  |  |  | 0 | 10 | 1 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 640 | 786.12 | 396.12 | 6026.12 | 6026.12 | 5386.12 | 0.1062 | Cummulative Cost 38: 436449.1; EOM Cummulative Cost 39: 126496.12; All in Cost Per Metre 40: 277.7014; PLOD LINK 41: LINK; Comments 42: Toolbox meeting, Pre-shift meeting, Pre-start all equipment, drilled HQ3 to pvc collar depth, PVC collar in hole and waited for collar to set, then continued to drill HQ3, housekeeping and maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250811N; Shift Shorthand 49: 2025-08
M 80/268 | Geotech | GT | 2025-08-11 05:02 | DS 5am | SF25_DDGT001 |  | Ben Payton | 3 | 390 |  |  | 0 | 21.7 | 57.7 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4945 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 1268.93 | 878.93 | 7488.93 | 7488.93 | 6963.93 | 0.070103 | Cummulative Cost 38: 443938.03; EOM Cummulative Cost 39: 133985.05; All in Cost Per Metre 40: 208.0258; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 / Survey hole @ 18m, 36m & 54m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250812D; Shift Shorthand 49: 2025-08
M 80/268 | Geotech | GT | 2025-08-11 17:02 | NS 5pm | SF25_DDGT001 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 57.7 | 93.7 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 5060 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 5860 | 5860 | 5450 | 0.069966 | Cummulative Cost 38: 449798.03; EOM Cummulative Cost 39: 139845.05; All in Cost Per Metre 40: 162.7778; PLOD LINK 41: LINK; Comments 42: drilled HQ3, survey at 72m 90m, housekeeping and maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250812N; Shift Shorthand 49: 2025-08
M 80/268 | Geotech | GT | 2025-08-12 05:02 | DS 5am | SF25_DDGT001 |  | Ben Payton | 3 | 390 |  |  | 0 | 93.7 | 100.2 | 6.5 |  |  | 0 |  |  | 0 | 6.5 | 877.5 | 1150 | 1 | 1 | 1 | 13170 | 750 | 2.5 | 8.5 |  | 1 | [5 empty] | 12 |  | 4270 | 390 | 0 | 6560 | 6560 | 2290 | 0.65091 | Cummulative Cost 38: 456358.03; EOM Cummulative Cost 39: 146405.05; All in Cost Per Metre 40: 1009.2308; PLOD LINK 41: LINK; Comments 42: Pull rods out for worn bit, Change bit & run back in / Drill to EOH @ 100.2m / Survey hole @ 96m / Pull rods & barrel out for EOH / Move rods from bench to ST / Rig down / Pack up site / Move rig and equipment to new pad, slower process due to tight pad & getting everything down off hill / Line up rig to hole requirements / Set up drill site ready to drill / Load full hole of core onto LT and unload at core farm due to no pad access while drilling hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250813D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-12 17:02 | NS 5pm | SF25_DDRD002 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 0 | 18.2 | 18.2 |  |  | 0 |  |  | 0 | 18.2 | 2457 | 3680 |  |  |  |  | 0 | 8 | 3.5 |  | 0.5 | [5 empty] | 12 |  | 1790 | 833.68 | 443.68 | 6303.68 | 6303.68 | 4513.68 | 0.28396 | Cummulative Cost 38: 462661.71; EOM Cummulative Cost 39: 152708.73; All in Cost Per Metre 40: 346.356; PLOD LINK 41: LINK; Comments 42: drilled HQ3 to pvc collar depth, PVC collar in hole and waited for collar to set, then continued to drill HQ3, housekeeping and maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250813N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-13 05:02 | DS 5am | SF25_DDRD002 |  | Ben Payton | 3 | 390 |  |  | 0 | 18.2 | 52 | 33.8 |  |  | 0 |  |  | 0 | 33.8 | 4563 | 5060 | 1 | 1 | 1 | 13170 | 750 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 507.93 | 117.93 | 6727.93 | 6727.93 | 6317.93 | 0.06094 | Cummulative Cost 38: 469389.64; EOM Cummulative Cost 39: 159436.66; All in Cost Per Metre 40: 199.0512; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 / Survey hole x 2 /; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250814D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-13 17:02 | NS 5pm | SF25_DDRD002 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 52 | 75.4 | 23.4 |  |  | 0 |  |  | 0 | 23.4 | 3159 | 4140 |  |  |  |  | 0 | 9 | 0.5 | repairing blown hose | 1.5 |  |  |  | 1 |  | 12 |  | 770 | 390 | 0 | 5300 | 5300 | 4530 | 0.14528 | Cummulative Cost 38: 474689.64; EOM Cummulative Cost 39: 164736.66; All in Cost Per Metre 40: 226.4957; PLOD LINK 41: LINK; Comments 42: had a hose burst at the end of the last shift, drilled HQ3, Survey at 54m 72m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250814N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-14 05:02 | DS 5am | SF25_DDRD002 | SF25_DDRD003 | Ben Payton | 3 | 390 |  |  | 0 | 75.4 | 90.6 | 15.2 |  |  | 0 | 0 | 3.8 | 3.8 | 19 | 2565 | 2645 | 1 | 1 | 1 | 13170 | 750 | 5.75 | 5.75 |  | 0.5 | [5 empty] | 12 |  | 2825 | 1268.93 | 878.93 | 7488.93 | 7488.93 | 4663.93 | 0.37722 | Cummulative Cost 38: 482178.57; EOM Cummulative Cost 39: 172225.59; All in Cost Per Metre 40: 394.1542; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 / Survey hole @ 87m EOH / Move rod bench & position ST / Pull rods & barrel out for EOH / Rig down / Pack up site / Move rig and equipment to new pad / Line up rig to hole requirements / Set up drill site / Drill HQ3 from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250815D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-14 17:02 | NS 5pm | SF25_DDRD003 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 3.8 | 30.8 | 27 |  |  | 0 |  |  | 0 | 27 | 3645 | 3795 |  |  |  |  | 0 | 8.25 | 3.25 |  | 0.5 | [5 empty] | 12 |  | 1675 | 833.68 | 443.68 | 6303.68 | 6303.68 | 4628.68 | 0.26572 | Cummulative Cost 38: 488482.25; EOM Cummulative Cost 39: 178529.27; All in Cost Per Metre 40: 233.4696; PLOD LINK 41: LINK; Comments 42: drilled HQ3 to pvc collar depth, PVC collar in hole and waited for collar to set, then continued to drill HQ3, Housekeeping and Maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250815N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-15 05:02 | DS 5am | SF25_DDRD003 |  | Ben Payton | 3 | 390 |  |  | 0 | 30.8 | 63.8 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 4830 | 1 | 1 | 1 | 13170 | 750 | 10.5 | 0.5 |  | 1 | [5 empty] | 12 |  | 590 | 390 | 0 | 6560 | 6560 | 5970 | 0.089939 | Cummulative Cost 38: 495042.25; EOM Cummulative Cost 39: 185089.27; All in Cost Per Metre 40: 198.7879; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 / Survey hole @ 36m & 54m / Client drill pad sign off inspection; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250816D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-15 17:02 | NS 5pm | SF25_DDRD003 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 63.8 | 90.2 | 26.4 |  |  | 0 |  |  | 0 | 26.4 | 3564 | 4600 |  |  |  |  | 0 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 | 3058.76 | 2668.76 | 8528.76 | 8528.76 | 7658.76 | 0.10201 | Cummulative Cost 38: 503571.01; EOM Cummulative Cost 39: 193618.03; All in Cost Per Metre 40: 323.0591; PLOD LINK 41: LINK; Comments 42: drilled HQ3, survey at 72m and E.O.H at 90m, Housekeeping and Maintenance . Collected freight delivery; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250816N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-16 05:02 | DS 5am | SF25_DDRD017 |  | Ben Payton | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 13170 | 750 | 0 | 7.75 | moving poly pipe to next hole | 4.25 |  | moving poly pipe to next hole |  |  |  | 12 |  | 5095 | 390 | 0 | 6235 | 6235 | 1140 | 0.81716 | Cummulative Cost 38: 509806.01; EOM Cummulative Cost 39: 199853.03; All in Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: Pull rods, barrel & casing out for EOH / Rig down / Pack up site / Move rig and equipment to new pad / Line up rig to hole requirements / Redirect poly line for water supply / Wait on water as in use by other rig / Set up drill site / Pull excess poly in from Northern holes to cental position while waiting on water; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250817D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-16 17:02 | NS 5pm | SF25_DDRD017 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 0 | 24.5 | 24.5 |  |  | 0 |  |  | 0 | 24.5 | 3307.5 | 3680 |  |  |  |  | 0 | 8 | 3.5 |  | 0.5 | [5 empty] | 12 |  | 1790 | 833.41 | 443.41 | 6303.41 | 6303.41 | 6303.41 | 0 | Cummulative Cost 38: 516109.42; EOM Cummulative Cost 39: 206156.44; All in Cost Per Metre 40: 257.282; PLOD LINK 41: LINK; Comments 42: drilled HQ3, drilled HQ3 to pvc collar depth, PVC collar in hole and waited for collar to set, ream PHD casing to 9m, survey at 18m, Housekeeping and Maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250817N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-17 05:02 | DS 5am | SF25_DDRD017 |  | Ben Payton | 3 | 390 |  |  | 0 | 24.5 | 60.8 | 36.3 |  |  | 0 |  |  | 0 | 36.3 | 4900.5 | 4900.5 | 1 | 1 | 1 | 13170 | 750 | 9.75 | 1.25 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 755 | 507.93 | 117.93 | 6913.43 | 6913.43 | 6913.43 | 0 | Cummulative Cost 38: 523022.85; EOM Cummulative Cost 39: 213069.87; All in Cost Per Metre 40: 190.4526; PLOD LINK 41: LINK; Comments 42: Drill on HQ3 / Reaming in another 6.0m PHD casing / Drill on HQ3 / Survey hole @ 36m / Toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250818D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-17 17:02 | NS 5pm | SF25_DDRD017 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 60.8 | 96.1 | 35.3 |  |  | 0 |  |  | 0 | 35.3 | 4765.5 | 4830 |  |  |  |  | 0 | 10.5 | 0.5 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 410 | 507.93 | 117.93 | 5747.93 | 5747.93 | 5747.93 | 0 | Cummulative Cost 38: 528770.78; EOM Cummulative Cost 39: 218817.8; All in Cost Per Metre 40: 162.8309; PLOD LINK 41: LINK; Comments 42: Drilled HQ3, survey at 72m and 90m, Housekeeping and Maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250818N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-18 05:02 | DS 5am | SF25_DDRD017 |  | Ben Payton | 3 | 390 |  |  | 0 | 96.1 | 111.8 | 15.7 |  |  | 0 |  |  | 0 | 15.7 | 2119.5 | 2119.5 | 1 | 1 | 1 | 13170 | 750 | 4.5 | 7 |  | 0.5 | [5 empty] | 12 |  | 3400 | 390 | 0 | 6659.5 | 6659.5 | 6659.5 | 0 | Cummulative Cost 38: 535430.28; EOM Cummulative Cost 39: 225477.3; All in Cost Per Metre 40: 424.172; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / EOH survey @ 108m / Pull rods, barrel & casing out for EOH / Rig down / Pack up site / Move rig and equipment to new pad / Line up rig to hole requirements / Set up drill site ready to drill; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250819D; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-18 17:02 | NS 5pm | SF25_DDRD010 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 0 | 21.3 | 21.3 |  |  | 0 |  |  | 0 | 21.3 | 2875.5 | 4370 |  |  |  |  | 0 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 984.93 | 594.93 | 6454.93 | 6454.93 | 6454.93 | 0 | Cummulative Cost 38: 541885.21; EOM Cummulative Cost 39: 231932.23; All in Cost Per Metre 40: 303.0484; PLOD LINK 41: LINK; Comments 42: drilled HQ3, drilled HQ3 to pvc collar depth, PVC collar in hole and waited for collar to set, ream PHD casing to 9m, survey at 18m, Housekeeping and Maintenance; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250819N; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-19 05:02 | DS 5am | SF25_DDRD010 |  | Ben Payton | 3 | 390 |  |  | 0 | 21.3 | 57.8 | 36.5 |  |  | 0 |  |  | 0 | 36.5 | 4927.5 | 4945 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 507.93 | 117.93 | 6727.93 | 6727.93 | 6727.93 | 0 | Cummulative Cost 38: 548613.14; EOM Cummulative Cost 39: 238660.16; All in Cost Per Metre 40: 184.3268; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey @ 18m, 36m & 54m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250820D; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-19 17:02 | NS 5pm | SF25_DDRD010 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 57.8 | 81.8 | 24 |  |  | 0 |  |  | 0 | 24 | 3240 | 3680 |  |  |  |  | 0 | 8 | 0.5 |  | 0.5 |  |  | 3 |  | Crew Change | 12 |  | 410 | 390 | 0 | 4480 | 4480 | 4480 | 0 | Cummulative Cost 38: 553093.14; EOM Cummulative Cost 39: 243140.16; All in Cost Per Metre 40: 186.6667; PLOD LINK 41: LINK; Comments 42: drilled HQ3, survey at 72m, packed up and left early for drive to airport; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250820N; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-20 05:02 | DS 5am | SF25_DDRD010 |  | Matthew Sing | 3 | 390 |  |  | 0 | 81.8 | 93.8 | 12 |  |  | 0 |  |  | 0 | 12 | 1620 | 1620 | 1 | 1 | 1 | 13170 | 750 | 3.25 | 0.25 | crew change | 0.5 |  |  | 8 |  | Crew Change | 12 |  | 295 | 390 | 0 | 3055 | 3055 | 3055 | 0 | Cummulative Cost 38: 556148.14; EOM Cummulative Cost 39: 246195.16; All in Cost Per Metre 40: 254.5833; PLOD LINK 41: LINK; Comments 42: Crew change, continue to drill HQ3, survey @ 90m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250821D; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-20 17:02 | NS 5pm | SF25_DDRD010 |  | Ben Payton | 3 | 390 |  |  | 0 | 93.8 | 130.4 | 36.6 |  |  | 0 |  |  | 0 | 36.6 | 4941 | 5060 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 507.93 | 117.93 | 5977.93 | 5977.93 | 5977.93 | 0 | Cummulative Cost 38: 562126.07; EOM Cummulative Cost 39: 252173.09; All in Cost Per Metre 40: 163.3314; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey @ 108m & 126m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250821N; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-21 05:02 | DS 5am | SF25_DDRD010 | SF25_DDRD013 | Matthew Sing | 3 | 390 |  |  | 0 | 130.4 | 135.7 | 5.3 |  |  | 0 | 0 | 6.5 | 6.5 | 11.8 | 1593 | 1725 | 1 | 1 | 1 | 13170 | 750 | 3.75 | 7.75 |  | 0.5 | [5 empty] | 12 |  | 3745 | 390 | 0 | 6610 | 6610 | 6610 | 0 | Cummulative Cost 38: 568736.07; EOM Cummulative Cost 39: 258783.09; All in Cost Per Metre 40: 560.1695; PLOD LINK 41: LINK; Comments 42: continue to drill HQ3 through broken ground, drill to EOH, EOH survey, pull rods onto bench and load onto ST due to small pad, pack up site, move all equipment to new pad, mast up, mast shot, setup site, commence drilling HQ3 from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250822D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-21 17:02 | NS 5pm | SF25_DDRD013 |  | Ben Payton | 3 | 390 |  |  | 0 | 6.5 | 35.3 | 28.8 |  |  | 0 |  |  | 0 | 28.8 | 3888 | 3910 |  |  |  |  | 0 | 8.5 | 3 |  | 0.5 | [5 empty] | 12 |  | 1560 | 951.61 | 561.61 | 6421.61 | 6421.61 | 6421.61 | 0 | Cummulative Cost 38: 575157.68; EOM Cummulative Cost 39: 265204.7; All in Cost Per Metre 40: 222.9726; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Open out hole with rock roller / Set 6m 150mm PVC in hole & wait for grout to cure / Flush HQ back in / Ream 12m PHD casing in / Drill on HQ3 / Survey @ 18m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250822N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-22 05:02 | DS 5am | SF25_DDRD013 |  | Matthew Sing | 3 | 390 |  |  | 0 | 35.3 | 66.8 | 31.5 |  |  | 0 |  |  | 0 | 31.5 | 4252.5 | 4945 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 390 | 0 | 6610 | 6610 | 6610 | 0 | Cummulative Cost 38: 581767.68; EOM Cummulative Cost 39: 271814.7; All in Cost Per Metre 40: 209.8413; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to drill HQ3, survey @ 36m & 54m, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250823D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-22 17:02 | NS 5pm | SF25_DDRD013 |  | Ben Payton | 3 | 390 |  |  | 0 | 66.8 | 99.8 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 4715 |  |  |  |  | 0 | 10.25 | 1.25 |  | 0.5 | [5 empty] | 12 |  | 755 | 390 | 0 | 5860 | 5860 | 5860 | 0 | Cummulative Cost 38: 587627.68; EOM Cummulative Cost 39: 277674.7; All in Cost Per Metre 40: 177.5758; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill HQ3 / Survey @ 72m & 90m / Pull rods for worn bit, Change bit and run back in / Drill on HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250823N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-23 05:02 | DS 5am | SF25_DDRD013 |  | Matthew Sing | 3 | 390 |  |  | 0 | 99.8 | 129.8 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4370 | 1 | 1 | 1 | 13170 | 750 | 9.5 | 0.5 |  | 0.5 | 1.5 | waiting for water |  |  |  | 12 |  | 950 | 527.5 | 137.5 | 6597.5 | 6597.5 | 6597.5 | 0 | Cummulative Cost 38: 594225.18; EOM Cummulative Cost 39: 284272.2; All in Cost Per Metre 40: 219.9167; PLOD LINK 41: LINK; Comments 42: continue to drill HQ3, standby for fuel tanker to fill tanks with water, survey @ 108m, lost water return at 118m, bombed hole twice to get return, continue to dril; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250824D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-23 17:02 | NS 5pm | SF25_DDRD013 |  | Ben Payton | 3 | 390 |  |  | 0 | 129.8 | 162.8 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 5060 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 5860 | 5860 | 5860 | 0 | Cummulative Cost 38: 600085.18; EOM Cummulative Cost 39: 290132.2; All in Cost Per Metre 40: 177.5758; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey @ 126m & 144m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250824N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-24 05:02 | DS 5am | SF25_DDRD013 |  | Matthew Sing | 3 | 390 |  |  | 0 | 162.8 | 196.9 | 34.1 |  |  | 0 |  |  | 0 | 34.1 | 4603.5 | 4830 | 1 | 1 | 1 | 13170 | 750 | 10.5 | 0.5 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 410 | 390 | 0 | 6380 | 6380 | 6380 | 0 | Cummulative Cost 38: 606465.18; EOM Cummulative Cost 39: 296512.2; All in Cost Per Metre 40: 187.0968; PLOD LINK 41: LINK; Comments 42: continue to drill HQ3, survey @ 162m & 180m,consult with client to continue drilling past EOH, toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250825D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-24 17:02 | NS 5pm | SF25_DDRD013 |  | Ben Payton | 3 | 390 |  |  | 0 | 196.9 | 225 | 28.1 |  |  | 0 |  |  | 0 | 28.1 | 3793.5 | 4255 |  |  |  |  | 0 | 9.25 | 0.5 |  | 0.5 | 1.25 | waiting for water | 0.5 |  | Toolbox | 12 |  | 860 | 507.93 | 117.93 | 5622.93 | 5622.93 | 5622.93 | 0 | Cummulative Cost 38: 612088.11; EOM Cummulative Cost 39: 302135.13; All in Cost Per Metre 40: 200.1043; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey @ 198m 7 216m / Wait on water to fill sumps throughout shift due to no water return from hole / EOH called at end of shift / Set up to pull rods out; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250825N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-25 05:02 | DS 5am | SF25_DDRD013 | SF25_DDRD012 | Matthew Sing | 3 | 390 |  |  | 0 | 225 | 225 | 0 |  |  | 0 | 0 | 6.7 | 6.7 | 6.7 | 904.5 | 1150 | 1 | 1 | 1 | 13170 | 750 | 2.5 | 9 |  | 0.5 | [5 empty] | 12 |  | 4320 | 390 | 0 | 6610 | 6610 | 6610 | 0 | Cummulative Cost 38: 618698.11; EOM Cummulative Cost 39: 308745.13; All in Cost Per Metre 40: 986.5672; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to pull rods,pull out casing, manual handle rods onto ST, packup site, move all equipment to new pad, mast up, mast shot, setup site, commence drilling HQ3 from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250826D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-25 17:02 | NS 5pm | SF25_DDRD012 |  | Ben Payton | 3 | 390 |  |  | 0 | 6.7 | 30.9 | 24.2 |  |  | 0 |  |  | 0 | 24.2 | 3267 | 3795 |  |  |  |  | 0 | 8.25 | 3.25 |  | 0.5 | [5 empty] | 12 |  | 1675 | 1089.11 | 699.11 | 6559.11 | 6559.11 | 6559.11 | 0 | Cummulative Cost 38: 625257.22; EOM Cummulative Cost 39: 315304.24; All in Cost Per Metre 40: 271.0376; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250826N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-26 05:02 | DS 5am | SF25_DDRD012 |  | Matthew Sing | 3 | 390 |  |  | 0 | 30.9 | 66.8 | 35.9 |  |  | 0 |  |  | 0 | 35.9 | 4846.5 | 4945 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 507.93 | 117.93 | 6727.93 | 6727.93 | 6727.93 | 0 | Cummulative Cost 38: 631985.15; EOM Cummulative Cost 39: 322032.17; All in Cost Per Metre 40: 187.4075; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to drill HQ3, survey @ 36m & 54m, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250827D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-26 17:02 | NS 5pm | SF25_DDRD012 |  | Ben Payton | 3 | 390 |  |  | 0 | 66.8 | 102.8 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 5060 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 5860 | 5860 | 5860 | 0 | Cummulative Cost 38: 637845.15; EOM Cummulative Cost 39: 327892.17; All in Cost Per Metre 40: 162.7778; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill HQ3 / Survey @ 72m & 90m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250827N; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-27 05:02 | DS 5am | SF25_DDRD012 |  | Matthew Sing | 3 | 390 |  |  | 0 | 102.8 | 135.8 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 4945 | 1 | 1 | 1 | 13170 | 750 | 10.75 | 0.75 |  | 0.5 | [5 empty] | 12 |  | 525 | 507.93 | 117.93 | 6727.93 | 6727.93 | 6727.93 | 0 | Cummulative Cost 38: 644573.08; EOM Cummulative Cost 39: 334620.1; All in Cost Per Metre 40: 203.8767; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250828D; Shift Shorthand 49: 2025-08
M 80/268 | Infill | DDRD | 2025-08-27 17:02 | NS 5pm | SF25_DDRD012 |  | Ben Payton | 3 | 390 |  |  | 0 | 135.8 | 165.2 | 29.4 |  |  | 0 |  |  | 0 | 29.4 | 3969 | 5175 |  |  |  |  | 0 | 11.25 | 0.25 |  | 0.5 | [5 empty] | 12 |  | 295 | 390 | 0 | 5860 | 5860 | 5860 | 0 | Cummulative Cost 38: 650433.08; EOM Cummulative Cost 39: 340480.1; All in Cost Per Metre 40: 199.3197; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill HQ3 / Survey @ 144m / Drilling harder broken formation 0.3m cavity 148.9-149.2m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250828N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-28 05:02 | DS 5am | SF25_DDRD019 |  | Matthew Sing | 3 | 390 |  |  | 0 | 0 | 9.3 | 9.3 |  |  | 0 |  |  | 0 | 9.3 | 1255.5 | 1380 | 1 | 1 | 1 | 13170 | 750 | 3 | 8.5 |  | 0.5 | [5 empty] | 12 |  | 4090 | 390 | 0 | 6610 | 6610 | 6610 | 0 | Cummulative Cost 38: 657043.08; EOM Cummulative Cost 39: 347090.1; All in Cost Per Metre 40: 710.7527; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250829D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-28 17:02 | NS 5pm | SF25_DDRD019 |  | Ben Payton | 3 | 390 |  |  | 0 | 9.3 | 39.8 | 30.5 |  |  | 0 |  |  | 0 | 30.5 | 4117.5 | 4117.5 |  |  |  |  | 0 | 8.25 | 3.25 |  | 0.5 | [5 empty] | 12 |  | 1675 | 833.68 | 443.68 | 6626.18 | 6626.18 | 6626.18 | -1.3726e-16 | Cummulative Cost 38: 663669.26; EOM Cummulative Cost 39: 353716.28; All in Cost Per Metre 40: 217.2518; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250829N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-29 05:02 | DS 5am | SF25_DDRD019 |  | Matthew Sing | 3 | 390 |  |  | 0 | 39.8 | 69.8 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 5175 | 1 | 1 | 1 | 13170 | 750 | 11.25 | 0.25 |  | 0.5 | [5 empty] | 12 |  | 295 | 390 | 0 | 6610 | 6610 | 6610 | 0 | Cummulative Cost 38: 670279.26; EOM Cummulative Cost 39: 360326.28; All in Cost Per Metre 40: 220.3333; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250830D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-29 17:02 | NS 5pm | SF25_DDRD019 |  | Ben Payton | 3 | 390 |  |  | 0 | 69.8 | 105.8 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 5060 |  |  |  |  | 0 | 11 | 0.5 |  | 0.5 | [5 empty] | 12 |  | 410 | 390 | 0 | 5860 | 5860 | 5860 | 0 | Cummulative Cost 38: 676139.26; EOM Cummulative Cost 39: 366186.28; All in Cost Per Metre 40: 162.7778; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250830N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-30 05:02 | DS 5am | SF25_DDRD019 |  | Matthew Sing | 3 | 390 |  |  | 0 | 105.8 | 128.1 | 22.3 |  |  | 0 |  |  | 0 | 22.3 | 3010.5 | 3220 | 1 | 1 | 1 | 13170 | 750 | 7 | 4.5 |  | 0.5 | [5 empty] | 12 |  | 2250 | 390 | 0 | 6610 | 6610 | 6610 | 0 | Cummulative Cost 38: 682749.26; EOM Cummulative Cost 39: 372796.28; All in Cost Per Metre 40: 296.4126; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to drill HQ3, survey @ 108m, drill to EOH and confirm with client, survey @ 123m, pull barrel, pull casing, pack up site and begin demobilisation; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 31; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250831D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-30 17:02 | NS 5pm | SF25_DDRD019 |  | Ben Payton | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 6 |  |  | 6 |  |  | 12 |  | 2160 | 390 | 0 | 2550 | 2550 | 2550 | 0 | Cummulative Cost 38: 685299.26; EOM Cummulative Cost 39: 375346.28; All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 08; Day 46: 31; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250831N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-31 05:02 | DS 5am | SF25_DDRD019 |  | Matthew Sing | 6 | 780 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 13170 | 750 |  |  |  | 12 | [5 empty] | 12 |  | 4320 | 9565 | 8785 | 14635 | 14635 | 14635 | 0 | Cummulative Cost 38: 699934.26; EOM Cummulative Cost 39: 389981.28; All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: MONTHLY FLIGHTS $7740 FREIGHT $1045; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250901D; Shift Shorthand 49: 2025-08
#N/A | #N/A |  | 2025-08-31 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250901N; Shift Shorthand 49: 2025-08
#N/A | #N/A |  | 2025-09-01 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250902D; Shift Shorthand 49: 2025-09
#N/A | #N/A |  | 2025-09-01 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250902N; Shift Shorthand 49: 2025-09
#N/A | #N/A |  | 2025-09-02 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250903D; Shift Shorthand 49: 2025-09
#N/A | #N/A |  | 2025-09-02 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250903N; Shift Shorthand 49: 2025-09
#N/A | #N/A |  | 2025-09-03 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250904D; Shift Shorthand 49: 2025-09
#N/A | #N/A |  | 2025-09-03 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250904N; Shift Shorthand 49: 2025-09
#N/A | #N/A |  | 2025-09-04 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250905D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-04 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250905N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-05 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250906D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-05 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250906N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-06 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250907D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-06 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250907N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-07 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250908D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-07 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250908N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-08 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250909D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-08 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250909N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-09 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250910D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-09 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250910N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-10 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250911D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-10 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250911N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-11 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250912D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-11 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250912N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-12 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250913D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-12 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250913N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-13 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250914D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-13 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250914N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-14 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250915D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-14 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250915N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-15 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250916D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-15 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250916N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-16 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250917D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-16 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250917N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-17 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250918D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-17 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250918N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-18 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250919D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-18 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250919N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-19 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250920D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-19 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250920N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-20 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250921D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-20 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250921N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-21 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250922D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-21 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250922N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-22 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250923D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-22 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250923N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-23 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250924D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-23 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250924N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-24 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250925D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-24 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250925N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-25 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250926D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-25 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250926N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-26 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250927D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-26 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250927N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-27 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250928D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-27 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250928N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-28 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250929D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-28 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250929N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-29 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250930D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-29 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 09; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250930N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-30 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251001D; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-09-30 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251001N; Shift Shorthand 49: 2025-09
#N/A |  |  | 2025-10-01 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251002D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-01 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251002N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-02 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251003D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-02 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251003N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-03 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251004D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-03 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251004N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-04 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251005D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-04 17:02 | NS 5pm | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251005N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-05 05:02 | DS 5am | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | [5 empty] | 0 | [11 empty] | 0 |  |  | 0 |  | 0 |  | All in Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251006D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-05 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251006N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-06 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251007D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-06 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251007N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-07 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251008D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-07 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251008N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-08 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251009D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-08 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251009N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-09 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251010D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-09 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251010N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-10 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251011D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-10 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251011N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-11 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251012D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-11 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251012N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-12 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251013D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-12 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251013N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-13 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251014D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-13 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251014N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-14 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251015D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-14 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251015N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-15 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251016D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-15 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251016N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-16 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251017D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-16 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251017N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-17 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251018D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-17 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251018N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-18 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251019D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-18 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251019N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-19 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251020D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-19 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251020N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-20 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251021D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-20 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251021N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-21 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251022D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-21 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251022N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-22 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251023D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-22 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251023N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-23 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251024D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-23 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251024N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-24 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251025D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-24 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251025N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-25 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251026D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-25 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251026N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-26 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251027D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-26 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251027N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-27 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251028D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-27 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251028N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-28 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251029D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-28 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251029N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-29 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251030D; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-29 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 10; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-251030N; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-30 05:02 | DS 5am | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: #VALUE!; Day 46: #VALUE!; Shift Shorthand 47: D; Shift Shorthand 48: #VALUE!; Shift Shorthand 49: 2025-10
#N/A |  |  | 2025-10-30 17:02 | NS 5pm | [17 empty] | 0 | 0 | [5 empty] | 0 | [16 empty] | 0 |  | Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-; Year 44: 25; Month 45: 01; Day 46: 00; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1663-250100N; Shift Shorthand 49: 2025-10
#N/A |  |  | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET |  |  | #VALUE! |  | END OF SHEET | END OF SHEET | END OF SHEET | 0 | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET |  | END OF SHEET | END OF SHEET | END OF SHEET |  | END OF SHEET | END OF SHEET |  | #VALUE! |  | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET | END OF SHEET
Note on P2: Thomas Pilote: Won't charge us extra for the triple tube
Note on V2: Thomas Pilote: Won't charge us extra for the triple tube
Note on AO2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NEW Column, please fill
Note on Y3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: make sure you fill down. check the cost against coreplan.
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just enter hole type on the row when the hole is finished drilling. We want them to equal the amount of completed holes of that type.

## Sheet3
Resource Drilling
Drilling
Row Labels | Sum of Total Costs
M 80/269 | 201985.63
07-Jul | 6631
08-Jul | 11719.27
09-Jul | 8832.93
10-Jul | 13499.67
11-Jul | 12691.12
12-Jul | 12104.72
13-Jul | 12466.16
14-Jul | 12530.86
15-Jul | 14383.55
16-Jul | 12976.12
17-Jul | 12660.43
18-Jul | 12701.55
19-Jul | 13260.43
20-Jul | 12349.05
21-Jul | 12564.72
22-Jul | 11654.05
23-Jul | 8960
MOB\DEMOB | 3780
05-Jul | 2520
06-Jul | 1260
(blank) | 0
<05/07/2025
07-Jul | 0
Grand Total | 205765.63

## Sheet2
Tenement ID | Date | Total Costs | Drill rig
M 80/268 | 2025-06-18 05:02 | 7425.14 | DDH41
M 80/268 | 2025-06-18 17:02 | 6098.98 | DDH41
M 80/268 | 2025-06-19 05:02 | 8376.43 | DDH41
M 80/268 | 2025-06-19 17:02 | 7243.5 | DDH41
M 80/268 | 2025-06-20 05:02 | 8300.72 | DDH41
M 80/268 | 2025-06-20 17:02 | 6130.43 | DDH41
M 80/268 | 2025-06-21 05:02 | 6315 | DDH41
M 80/268 | 2025-06-21 17:02 | 6582.65 | DDH41
MOB\DEMOB | 2025-06-22 | 6182.5 | ST18
M 80/268 | 2025-06-22 05:02 | 6955 | DDH41
M 80/268 | 2025-06-22 17:02 | 6102.93 | DDH41
MOB\DEMOB | 2025-06-23 | 4846.25 | ST18
M 80/268 | 2025-06-23 05:02 | 6765 | DDH41
M 80/268 | 2025-06-23 17:02 | 5817 | DDH41
M 80/268 | 2025-06-24 | 8518.72 | ST18
M 80/268 | 2025-06-24 05:02 | 7165.08 | DDH41
M 80/268 | 2025-06-24 17:02 | 6567 | DDH41
M 80/268 | 2025-06-25 | 8467.47 | ST18
M 80/268 | 2025-06-25 05:02 | 2985 | DDH41
M 80/268 | 2025-06-25 17:02 | 5885 | DDH41
M 80/268 | 2025-06-26 | 12779.32 | ST18
M 80/268 | 2025-06-26 05:02 | 7643.93 | DDH41
M 80/268 | 2025-06-26 17:02 | 5885 | DDH41
M 80/268 | 2025-06-27 | 14215.87 | ST18
M 80/268 | 2025-06-27 05:02 | 7223.35 | DDH41
M 80/268 | 2025-06-27 17:02 | 6292.22 | DDH41
M 80/268 | 2025-06-28 | 13713.07 | ST18
M 80/268 | 2025-06-28 05:02 | 7220.43 | DDH41
M 80/268 | 2025-06-28 17:02 | 5402.93 | DDH41
M 80/268 | 2025-06-29 | 72410.94 | ST18
M 80/268 | 2025-06-29 05:02 | 7341.12 | DDH41
M 80/268 | 2025-06-29 17:02 | 6190 | DDH41
M 80/268 | 2025-06-30 | 13179.93 | ST18
M 80/268 | 2025-06-30 05:02 | 7541.68 | DDH41
M 80/268 | 2025-06-30 17:02 | 5135 | DDH41
M 80/268 | 2025-07-01 | 9943.37 | ST18
M 80/268 | 2025-07-01 05:02 | 4961 | DDH41
M 80/268 | 2025-07-01 17:02 | 6280 | DDH41
M 80/268 | 2025-07-02 | 13952.12 | ST18
M 80/268 | 2025-07-02 05:02 | 6585 | DDH41
M 80/268 | 2025-07-02 17:02 | 5885 | DDH41
M 80/268 | 2025-07-03 | 14014.62 | ST18
M 80/268 | 2025-07-03 05:02 | 7116 | DDH41
M 80/268 | 2025-07-03 17:02 | 5935 | DDH41
M 80/268 | 2025-07-04 | 5672.72 | ST18
M 80/268 | 2025-07-04 05:02 | 6925.49 | DDH41
M 80/268 | 2025-07-04 17:02 | 5902.93 | DDH41
MOB\DEMOB | 2025-07-05 | 1260 | DDH38
M 80/268 | 2025-07-05 | 11038.68 | ST18
MOB\DEMOB | 2025-07-05 05:02 | 1260 | DDH38
M 80/268 | 2025-07-05 05:02 | 6752.93 | DDH41
M 80/268 | 2025-07-05 17:02 | 5772.93 | DDH41
M 80/268 | 2025-07-06 | 16075.87 | ST18
MOB\DEMOB | 2025-07-06 05:02 | 1260 | DDH38
M 80/268 | 2025-07-06 05:02 | 7283.93 | DDH41
MOB\DEMOB | 2025-07-06 17:02 | 0 | DDH38
M 80/268 | 2025-07-06 17:02 | 5472.93 | DDH41
M 80/268 | 2025-07-07 | 13284.93 | ST18
M 80/269 | 2025-07-07 05:02 | 6631 | DDH38
M 80/268 | 2025-07-07 05:02 | 6907.05 | DDH41
M 80/269 | 2025-07-07 17:02 | 5952.93 | DDH41
M 80/268 | 2025-07-08 | 2422.5 | ST18
M 80/269 | 2025-07-08 05:02 | 7096.34 | DDH38
M 80/269 | 2025-07-08 05:02 | 6870.86 | DDH41
M 80/269 | 2025-07-08 17:02 | 4622.93 | DDH38
M 80/269 | 2025-07-08 17:02 | 5972.93 | DDH41
M 80/268 | 2025-07-09 | 1452.5 | ST18
M 80/269 | 2025-07-09 05:02 | 2550 | DDH38
M 80/269 | 2025-07-09 05:02 | 3885.86 | DDH41
M 80/269 | 2025-07-09 17:02 | 6282.93 | DDH38
M 80/269 | 2025-07-09 17:02 | 5871.49 | DDH41
M 80/268 | 2025-07-10 | 1272.5 | ST18
M 80/269 | 2025-07-10 05:02 | 6862.99 | DDH38
M 80/269 | 2025-07-10 05:02 | 6190.72 | DDH41
M 80/269 | 2025-07-10 17:02 | 6636.68 | DDH38
M 80/269 | 2025-07-10 17:02 | 6300.8 | DDH41
M 80/268 | 2025-07-11 | 11762.12 | ST18
M 80/269 | 2025-07-11 05:02 | 6435 | DDH38
M 80/269 | 2025-07-11 05:02 | 7009.72 | DDH41
M 80/269 | 2025-07-11 17:02 | 6256.12 | DDH38
M 80/269 | 2025-07-11 17:02 | 5977.93 | DDH41
M 80/268 | 2025-07-12 | 12387.12 | ST18
M 80/269 | 2025-07-12 05:02 | 6356.79 | DDH38
M 80/269 | 2025-07-12 05:02 | 6894.72 | DDH41
M 80/269 | 2025-07-12 17:02 | 5747.93 | DDH38
M 80/269 | 2025-07-12 17:02 | 5747.93 | DDH41
M 80/268 | 2025-07-13 | 12688.67 | ST18
M 80/269 | 2025-07-13 05:02 | 6488.23 | DDH38
M 80/269 | 2025-07-13 05:02 | 6805 | DDH41
M 80/269 | 2025-07-13 17:02 | 5977.93 | DDH38
M 80/268 | 2025-07-13 17:02 | 5952.93 | DDH41
M 80/268 | 2025-07-14 | 11780.87 | ST18
M 80/269 | 2025-07-14 05:02 | 6435 | DDH38
M 80/268 | 2025-07-14 05:02 | 6830 | DDH41
M 80/269 | 2025-07-14 17:02 | 6095.86 | DDH38
M 80/268 | 2025-07-14 17:02 | 6071.49 | DDH41
M 80/268 | 2025-07-15 | 16039.4 | ST18
M 80/269 | 2025-07-15 05:02 | 7734.56 | DDH38
M 80/268 | 2025-07-15 05:02 | 6887.4 | DDH41
M 80/269 | 2025-07-15 17:02 | 6648.99 | DDH38
M 80/268 | 2025-07-15 17:02 | 7360.93 | DDH41
M 80/268 | 2025-07-16 | 5986.12 | ST18
M 80/269 | 2025-07-16 05:02 | 6720 | DDH38
M 80/268 | 2025-07-16 05:02 | 1465 | DDH41
M 80/269 | 2025-07-16 17:02 | 6256.12 | DDH38
M 80/268 | 2025-07-16 17:02 | 7267.93 | DDH41
M 80/268 | 2025-07-17 | 12352.06 | ST18
M 80/269 | 2025-07-17 05:02 | 6435 | DDH38
M 80/268 | 2025-07-17 05:02 | 6410 | DDH41
M 80/269 | 2025-07-17 17:02 | 6225.43 | DDH38
M 80/268 | 2025-07-17 17:02 | 6197.93 | DDH41
M 80/268 | 2025-07-18 | 13839.05 | ST18
M 80/269 | 2025-07-18 05:02 | 6385 | DDH38
M 80/268 | 2025-07-18 05:02 | 6527.93 | DDH41
M 80/269 | 2025-07-18 17:02 | 6316.55 | DDH38
M 80/268 | 2025-07-18 17:02 | 6467.93 | DDH41
M 80/268 | 2025-07-19 | 16096.7 | ST18
M 80/269 | 2025-07-19 05:02 | 6862.5 | DDH38
M 80/268 | 2025-07-19 05:02 | 6360 | DDH41
M 80/269 | 2025-07-19 17:02 | 6397.93 | DDH38
M 80/268 | 2025-07-19 17:02 | 5977.93 | DDH41
M 80/268 | 2025-07-20 | 17916.03 | ST18
M 80/269 | 2025-07-20 05:02 | 6205 | DDH38
M 80/268 | 2025-07-20 05:02 | 6180 | DDH41
M 80/269 | 2025-07-20 17:02 | 6144.05 | DDH38
M 80/268 | 2025-07-20 17:02 | 5747.93 | DDH41
M 80/268 | 2025-07-21 | 14888.17 | ST18
M 80/269 | 2025-07-21 05:02 | 6586.79 | DDH38
M 80/268 | 2025-07-21 05:02 | 6410 | DDH41
M 80/269 | 2025-07-21 17:02 | 5977.93 | DDH38
M 80/268 | 2025-07-21 17:02 | 5977.93 | DDH41
M 80/268 | 2025-07-22 | 15143.17 | ST18
M 80/269 | 2025-07-22 05:02 | 6435 | DDH38
M 80/268 | 2025-07-22 05:02 | 6410 | DDH41
M 80/269 | 2025-07-22 17:02 | 5219.05 | DDH38
M 80/268 | 2025-07-22 17:02 | 5977.93 | DDH41
M 80/268 | 2025-07-23 | 13268.27 | ST18
M 80/269 | 2025-07-23 05:02 | 3100 | DDH38
M 80/268 | 2025-07-23 05:02 | 6410 | DDH41
M 80/269 | 2025-07-23 17:02 | 5860 | DDH38
M 80/268 | 2025-07-23 17:02 | 5998.7 | DDH41
M 80/268 | 2025-07-24 | 702.12 | ST18
M 80/269 | 2025-07-24 05:02 | 7041.06 | DDH38
M 80/268 | 2025-07-24 05:02 | 6410 | DDH41
M 80/269 | 2025-07-24 17:02 | 5860 | DDH38
M 80/268 | 2025-07-24 17:02 | 5998.7 | DDH41
M 80/268 | 2025-07-25 | 520 | ST18
E 80/2863-I | 2025-07-25 05:02 | 6291.06 | DDH38
M 80/268 | 2025-07-25 05:02 | 6946 | DDH41
E 80/2863-I | 2025-07-25 17:02 | 5410 | DDH38
M 80/269 | 2025-07-25 17:02 | 5998.7 | DDH41
M 80/268 | 2025-07-26 | 15185.68 | ST18
E 80/2863-I | 2025-07-26 05:02 | 6235 | DDH38
M 80/269 | 2025-07-26 05:02 | 6410 | DDH41
E 80/2863-I | 2025-07-26 17:02 | 5460 | DDH38
M 80/269 | 2025-07-26 17:02 | 5860 | DDH41
M 80/268 | 2025-07-27 | 15742.27 | ST18
M 80/269 | 2025-07-27 05:02 | 5705 | DDH38
M 80/269 | 2025-07-27 05:02 | 6180 | DDH41
M 80/269 | 2025-07-27 17:02 | 6316.61 | DDH38
M 80/269 | 2025-07-27 17:02 | 5772.5 | DDH41
M 80/269 | 2025-07-28 | 16888.28 | ST18
M 80/269 | 2025-07-28 05:02 | 6435 | DDH38
M 80/269 | 2025-07-28 05:02 | 7091.12 | DDH41
M 80/269 | 2025-07-28 17:02 | 5630 | DDH38
M 80/269 | 2025-07-28 17:02 | 6217.5 | DDH41
M 80/269 | 2025-07-29 | 13369.53 | ST18
M 80/269 | 2025-07-29 05:02 | 3905 | DDH38
M 80/269 | 2025-07-29 05:02 | 7181.2 | DDH41
M 80/269 | 2025-07-29 17:02 | 4617.5 | DDH38
M 80/269 | 2025-07-29 17:02 | 4137.93 | DDH41
M 80/269 | 2025-07-30 | 9469.88 | ST18
M 80/269 | 2025-07-30 05:02 | 6385 | DDH38
M 80/269 | 2025-07-30 05:02 | 1350 | DDH41
M 80/269 | 2025-07-30 17:02 | 5435 | DDH38
M 80/269 | 2025-07-30 17:02 | 5835 | DDH41
M 80/268 | 2025-07-31 | 37276.89 | ST18
E 80/2863-I | 2025-07-31 05:02 | 6135 | DDH38
M 80/269 | 2025-07-31 05:02 | 6674.57 | DDH41
M 80/269 | 2025-07-31 17:02 | 19846.12 | DDH38
M 80/269 | 2025-07-31 17:02 | 28007.5 | DDH41
M 80/268 | 2025-08-01 | 14921.12 | ST18
M 80/269 | 2025-08-01 05:02 | 6800 | DDH38
M 80/269 | 2025-08-01 05:02 | 7855 | DDH41
M 80/269 | 2025-08-01 17:02 | 5860 | DDH38
M 80/269 | 2025-08-01 17:02 | 6055 | DDH41
M 80/268 | 2025-08-02 | 13967.38 | ST18
M 80/269 | 2025-08-02 05:02 | 6800.7 | DDH38
M 80/269 | 2025-08-02 05:02 | 6585 | DDH41
M 80/269 | 2025-08-02 17:02 | 5860 | DDH38
M 80/269 | 2025-08-02 17:02 | 6055 | DDH41
M 80/268 | 2025-08-03 | 10571.38 | ST18
M 80/269 | 2025-08-03 05:02 | 6610 | DDH38
M 80/269 | 2025-08-03 05:02 | 6752.93 | DDH41
M 80/269 | 2025-08-03 17:02 | 5630 | DDH38
M 80/269 | 2025-08-03 17:02 | 5605 | DDH41
M 80/268 | 2025-08-04 | 14851.13 | ST18
M 80/269 | 2025-08-04 05:02 | 6510 | DDH38
M 80/269 | 2025-08-04 05:02 | 6602.93 | DDH41
M 80/269 | 2025-08-04 17:02 | 6256.12 | DDH38
M 80/269 | 2025-08-04 17:02 | 6055 | DDH41
M 80/268 | 2025-08-05 | 14049.88 | ST18
M 80/269 | 2025-08-05 05:02 | 7317.5 | DDH38
M 80/269 | 2025-08-05 05:02 | 6723.7 | DDH41
M 80/269 | 2025-08-05 17:02 | 4917.5 | DDH38
M 80/269 | 2025-08-05 17:02 | 5835 | DDH41
M 80/268 | 2025-08-06 | 15278.63 | ST18
M 80/269 | 2025-08-06 05:02 | 3226.12 | DDH38
M 80/269 | 2025-08-06 05:02 | 6723.7 | DDH41
M 80/269 | 2025-08-06 17:02 | 6277.5 | DDH38
M 80/269 | 2025-08-06 17:02 | 5835 | DDH41
M 80/268 | 2025-08-07 | 4889.06 | ST18
M 80/269 | 2025-08-07 05:02 | 6642.5 | DDH38
M 80/269 | 2025-08-07 05:02 | 6853.7 | DDH41
M 80/268 | 2025-08-07 17:02 | 5860 | DDH38
M 80/268 | 2025-08-07 17:02 | 5899.5 | DDH41
M 80/268 | 2025-08-08 | 16060.31 | ST18
M 80/268 | 2025-08-08 05:02 | 10728 | DDH38
M 80/268 | 2025-08-08 05:02 | 7762.75 | DDH41
M 80/268 | 2025-08-08 17:02 | 6208.56 | DDH38
M 80/268 | 2025-08-08 17:02 | 5835 | DDH41
M 80/268 | 2025-08-09 | 17639.52 | ST18
M 80/268 | 2025-08-09 05:02 | 6610 | DDH38
M 80/268 | 2025-08-09 05:02 | 6793.7 | DDH41
M 80/268 | 2025-08-09 17:02 | 5970.5 | DDH38
M 80/268 | 2025-08-09 17:02 | 5839.5 | DDH41
M 80/268 | 2025-08-10 | 19097.27 | ST18
M 80/268 | 2025-08-10 05:02 | 6385 | DDH38
M 80/268 | 2025-08-10 05:02 | 6493.7 | DDH41
M 80/268 | 2025-08-10 17:02 | 6026.12 | DDH38
M 80/268 | 2025-08-10 17:02 | 5605 | DDH41
M 80/268 | 2025-08-11 | 15473.52 | ST18
M 80/268 | 2025-08-11 05:02 | 7488.93 | DDH38
M 80/268 | 2025-08-11 05:02 | 6661.5 | DDH41
M 80/268 | 2025-08-11 17:02 | 5860 | DDH38
M 80/268 | 2025-08-11 17:02 | 5835 | DDH41
M 80/268 | 2025-08-12 | 19601.02 | ST18
M 80/268 | 2025-08-12 05:02 | 6560 | DDH38
M 80/268 | 2025-08-12 05:02 | 6885 | DDH41
M 80/268 | 2025-08-12 17:02 | 6303.68 | DDH38
M 80/268 | 2025-08-12 17:02 | 5835 | DDH41
M 80/268 | 2025-08-13 | 17268.52 | ST18
M 80/268 | 2025-08-13 05:02 | 6727.93 | DDH38
M 80/269 | 2025-08-13 05:02 | 2180 | DDH41
M 80/268 | 2025-08-13 17:02 | 5300 | DDH38
M 80/269 | 2025-08-13 17:02 | 6723.7 | DDH41
M 80/269 | 2025-08-14 | 16282.02 | ST18
M 80/268 | 2025-08-14 05:02 | 7488.93 | DDH38
M 80/269 | 2025-08-14 05:02 | 6552.93 | DDH41
M 80/268 | 2025-08-14 17:02 | 6303.68 | DDH38
M 80/269 | 2025-08-14 17:02 | 6355 | DDH41
M 80/268 | 2025-08-15 | 16157.02 | ST18
M 80/268 | 2025-08-15 05:02 | 6560 | DDH38
M 80/269 | 2025-08-15 05:02 | 4825 | DDH41
M 80/268 | 2025-08-15 17:02 | 8528.76 | DDH38
M 80/269 | 2025-08-15 17:02 | 7569.56 | DDH41
M 80/268 | 2025-08-16 | 16737.03 | ST18
M 80/268 | 2025-08-16 05:02 | 6235 | DDH38
M 80/269 | 2025-08-16 05:02 | 6435 | DDH41
M 80/268 | 2025-08-16 17:02 | 6303.41 | DDH38
M 80/269 | 2025-08-16 17:02 | 6230 | DDH41
M 80/268 | 2025-08-17 | 17042.02 | ST18
M 80/268 | 2025-08-17 05:02 | 6913.43 | DDH38
M 80/269 | 2025-08-17 05:02 | 6205 | DDH41
M 80/268 | 2025-08-17 17:02 | 5747.93 | DDH38
M 80/269 | 2025-08-17 17:02 | 6273.56 | DDH41
M 80/269 | 2025-08-18 | 16730.77 | ST18
M 80/268 | 2025-08-18 05:02 | 6659.5 | DDH38
M 80/269 | 2025-08-18 05:02 | 6575 | DDH41
M 80/268 | 2025-08-18 17:02 | 6454.93 | DDH38
M 80/269 | 2025-08-18 17:02 | 6273.56 | DDH41
M 80/269 | 2025-08-19 | 19871.44 | ST18
M 80/268 | 2025-08-19 05:02 | 6727.93 | DDH38
M 80/269 | 2025-08-19 05:02 | 6552.93 | DDH41
M 80/268 | 2025-08-19 17:02 | 4480 | DDH38
M 80/269 | 2025-08-19 17:02 | 6598.49 | DDH41
M 80/269 | 2025-08-20 | 19834.52 | ST18
M 80/268 | 2025-08-20 05:02 | 3055 | DDH38
M 80/269 | 2025-08-20 05:02 | 6902.93 | DDH41
M 80/268 | 2025-08-20 17:02 | 5977.93 | DDH38
M 80/268 | 2025-08-20 17:02 | 6771 | DDH41
M 80/269 | 2025-08-21 | 18796.37 | ST18
M 80/268 | 2025-08-21 05:02 | 6610 | DDH38
M 80/268 | 2025-08-21 05:02 | 6843.42 | DDH41
M 80/268 | 2025-08-21 17:02 | 6421.61 | DDH38
M 80/268 | 2025-08-21 17:02 | 6421.79 | DDH41
M 80/269 | 2025-08-22 | 18212.28 | ST18
M 80/268 | 2025-08-22 05:02 | 6610 | DDH38
M 80/268 | 2025-08-22 05:02 | 6812.93 | DDH41
M 80/268 | 2025-08-22 17:02 | 5860 | DDH38
M 80/268 | 2025-08-22 17:02 | 6311 | DDH41
M 80/269 | 2025-08-23 | 13839.77 | ST18
M 80/268 | 2025-08-23 05:02 | 6597.5 | DDH38
M 80/269 | 2025-08-23 05:02 | 7137.43 | DDH41
M 80/268 | 2025-08-23 17:02 | 5860 | DDH38
M 80/269 | 2025-08-23 17:02 | 6293.7 | DDH41
M 80/269 | 2025-08-24 | 17628.52 | ST18
M 80/268 | 2025-08-24 05:02 | 6380 | DDH38
M 80/269 | 2025-08-24 05:02 | 6802.93 | DDH41
M 80/268 | 2025-08-24 17:02 | 5622.93 | DDH38
M 80/269 | 2025-08-24 17:02 | 6070.49 | DDH41
M 80/268 | 2025-08-25 | 16251.07 | ST18
M 80/268 | 2025-08-25 05:02 | 6610 | DDH38
M 80/269 | 2025-08-25 05:02 | 6552.93 | DDH41
M 80/268 | 2025-08-25 17:02 | 6559.11 | DDH38
M 80/269 | 2025-08-25 17:02 | 6127.93 | DDH41
M 80/268 | 2025-08-26 | 19934.17 | ST18
M 80/268 | 2025-08-26 05:02 | 6727.93 | DDH38
M 80/269 | 2025-08-26 05:02 | 7015.93 | DDH41
M 80/268 | 2025-08-26 17:02 | 5860 | DDH38
M 80/269 | 2025-08-26 17:02 | 4170 | DDH41
M 80/268 | 2025-08-27 | 20693.27 | ST18
M 80/268 | 2025-08-27 05:02 | 6727.93 | DDH38
M 80/269 | 2025-08-27 05:02 | 1145 | DDH41
M 80/268 | 2025-08-27 17:02 | 5860 | DDH38
M 80/269 | 2025-08-27 17:02 | 6117.93 | DDH41
M 80/268 | 2025-08-28 | 17126.07 | ST18
M 80/269 | 2025-08-28 05:02 | 6610 | DDH38
M 80/269 | 2025-08-28 05:02 | 6459.5 | DDH41
M 80/269 | 2025-08-28 17:02 | 6626.18 | DDH38
M 80/269 | 2025-08-28 17:02 | 6150.49 | DDH41
M 80/268 | 2025-08-29 | 17907.32 | ST18
M 80/269 | 2025-08-29 05:02 | 6610 | DDH38
M 80/269 | 2025-08-29 05:02 | 7145 | DDH41
M 80/269 | 2025-08-29 17:02 | 5860 | DDH38
M 80/269 | 2025-08-29 17:02 | 6034.93 | DDH41
M 80/268 | 2025-08-30 | 16978.17 | ST18
M 80/269 | 2025-08-30 05:02 | 6610 | DDH38
M 80/269 | 2025-08-30 05:02 | 6824 | DDH41
M 80/269 | 2025-08-30 17:02 | 2550 | DDH38
M 80/268 | 2025-08-30 17:02 | 6621 | DDH41
M 80/268 | 2025-08-31 | 37354.7 | ST18
M 80/269 | 2025-08-31 05:02 | 14635 | DDH38
M 80/268 | 2025-08-31 05:02 | 6299.85 | DDH41
M 80/268 | 2025-08-31 17:02 | 14825.43 | DDH41
M 80/269 | 2025-09-01 | 15322.02 | ST18
M 80/268 | 2025-09-01 05:02 | 6335 | DDH41
M 80/269 | 2025-09-01 17:02 | 6791.13 | DDH41
M 80/269 | 2025-09-02 | 15769.87 | ST18
M 80/269 | 2025-09-02 05:02 | 6990.49 | DDH41
M 80/269 | 2025-09-02 17:02 | 5977.93 | DDH41
M 80/269 | 2025-09-03 | 16253.63 | ST18
M 80/269 | 2025-09-03 05:02 | 6335 | DDH41
M 80/269 | 2025-09-03 17:02 | 6711.83 | DDH41
M 80/269 | 2025-09-04 | 12126.13 | ST18
M 80/269 | 2025-09-04 05:02 | 6435 | DDH41
M 80/269 | 2025-09-04 17:02 | 5977.93 | DDH41
M 80/269 | 2025-09-05 | 14974.64 | ST18
M 80/269 | 2025-09-05 05:02 | 6655 | DDH41
M 80/268 | 2025-09-05 17:02 | 6055.43 | DDH41
M 80/269 | 2025-09-06 | 16644.52 | ST18
M 80/268 | 2025-09-06 05:02 | 6830.85 | DDH41
M 80/268 | 2025-09-06 17:02 | 5977.93 | DDH41
M 80/269 | 2025-09-07 | 10901.25 | ST18
M 80/268 | 2025-09-07 05:02 | 6425 | DDH41
M 80/268 | 2025-09-07 17:02 | 5630 | DDH41
#N/A | 2025-09-08 | 4230 | ST18
M 80/268 | 2025-09-08 05:02 | 7334.12 | DDH41
M 80/268 | 2025-09-08 17:02 | 5762.85 | DDH41
#N/A | 2025-09-09 | 53618.6 | ST18
M 80/268 | 2025-09-09 05:02 | 6526.06 | DDH41
M 80/268 | 2025-09-09 17:02 | 3560 | DDH41
#N/A | 2025-09-10 | 0 | ST18
M 80/268 | 2025-09-10 05:02 | 2090 | DDH41
M 80/268 | 2025-09-10 17:02 | 0 | DDH41
M 80/268 | 2025-09-11 05:02 | 7865 | DDH41
M 80/268 | 2025-09-11 17:02 | 0 | DDH41
M 80/268 | 2025-09-12 05:02 | 6807.93 | DDH41
M 80/268 | 2025-09-12 17:02 | 0 | DDH41
M 80/268 | 2025-09-13 05:02 | 8198.42 | DDH41
M 80/268 | 2025-09-13 17:02 | 0 | DDH41
M 80/268 | 2025-09-14 05:02 | 8035.92 | DDH41
M 80/268 | 2025-09-14 17:02 | 0 | DDH41
M 80/268 | 2025-09-15 05:02 | 9502.31 | DDH41
M 80/268 | 2025-09-15 17:02 | 0 | DDH41
M 80/269 | 2025-09-16 05:02 | 7395.92 | DDH41
M 80/269 | 2025-09-16 17:02 | 0 | DDH41
M 80/269 | 2025-09-17 05:02 | 7457.93 | DDH41
M 80/269 | 2025-09-17 17:02 | 0 | DDH41
M 80/269 | 2025-09-18 05:02 | 6807.93 | DDH41
M 80/269 | 2025-09-18 17:02 | 0 | DDH41
M 80/269 | 2025-09-19 05:02 | 7477.93 | DDH41
M 80/269 | 2025-09-19 17:02 | 0 | DDH41
M 80/269 | 2025-09-20 05:02 | 6807.93 | DDH41
M 80/269 | 2025-09-20 17:02 | 0 | DDH41
M 80/269 | 2025-09-21 05:02 | 6577.93 | DDH41
M 80/269 | 2025-09-21 17:02 | 0 | DDH41
M 80/269 | 2025-09-22 05:02 | 7523.99 | DDH41
M 80/269 | 2025-09-22 17:02 | 0 | DDH41
M 80/269 | 2025-09-23 05:02 | 6807.93 | DDH41
M 80/269 | 2025-09-23 17:02 | 0 | DDH41
M 80/269 | 2025-09-24 05:02 | 6807.93 | DDH41
M 80/269 | 2025-09-24 17:02 | 0 | DDH41
M 80/269 | 2025-09-25 05:02 | 7698.98 | DDH41
M 80/269 | 2025-09-25 17:02 | 0 | DDH41
M 80/269 | 2025-09-26 05:02 | 7399.42 | DDH41
M 80/269 | 2025-09-26 17:02 | 0 | DDH41
M 80/269 | 2025-09-27 05:02 | 7098.42 | DDH41
M 80/269 | 2025-09-27 17:02 | 0 | DDH41
M 80/269 | 2025-09-28 05:02 | 7223.42 | DDH41
M 80/269 | 2025-09-28 17:02 | 0 | DDH41
M 80/269 | 2025-09-29 05:02 | 6798.93 | DDH41
M 80/269 | 2025-09-29 17:02 | 6577.93 | DDH41
M 80/269 | 2025-09-30 05:02 | 7956.49 | DDH41
M 80/269 | 2025-09-30 17:02 | 19480.84 | DDH41
M 80/269 | 2025-10-01 05:02 | 6690 | DDH41
M 80/269 | 2025-10-01 17:02 | 6147.93 | DDH41
M 80/269 | 2025-10-02 05:02 | 6690 | DDH41
M 80/269 | 2025-10-02 17:02 | 5927.93 | DDH41
M 80/269 | 2025-10-03 05:02 | 7042.5 | DDH41
M 80/269 | 2025-10-03 17:02 | 6066.63 | DDH41
M 80/269 | 2025-10-04 05:02 | 6690 | DDH41
M 80/269 | 2025-10-04 17:02 | 6066.63 | DDH41
M 80/269 | 2025-10-05 05:02 | 1370 | DDH41
M 80/269 | 2025-10-05 17:02 | 5580 | DDH41
M 80/269 | 2025-10-06 05:02 | 1370 | DDH41
M 80/269 | 2025-10-06 17:02 | 6250.7 | DDH41
M 80/269 | 2025-10-07 05:02 | 1370 | DDH41
M 80/269 | 2025-10-07 17:02 | 5120.7 | DDH41
M 80/269 | 2025-10-08 05:02 | 3815 | DDH41
M 80/269 | 2025-10-08 17:02 | 0 | DDH41
M 80/269 | 2025-10-09 05:02 | 9487.28 | DDH41
M 80/269 | 2025-10-09 17:02 | 0 | DDH41
M 80/269 | 2025-10-10 05:02 | 6637.93 | DDH41
M 80/269 | 2025-10-10 17:02 | 0 | DDH41
M 80/269 | 2025-10-11 05:02 | 6832.93 | DDH41
M 80/269 | 2025-10-11 17:02 | 0 | DDH41
M 80/269 | 2025-10-12 05:02 | 6522.93 | DDH41
M 80/269 | 2025-10-12 17:02 | 0 | DDH41
M 80/269 | 2025-10-13 05:02 | 7316.2 | DDH41
M 80/269 | 2025-10-13 17:02 | 0 | DDH41
M 80/269 | 2025-10-14 05:02 | 12181.25 | DDH41
M 80/269 | 2025-10-14 17:02 | 5537.93 | DDH41
M 80/269 | 2025-10-15 05:02 | 7299.46 | DDH41
M 80/269 | 2025-10-15 17:02 | 6875.49 | DDH41
M 80/269 | 2025-10-16 05:02 | 5850 | DDH41
M 80/269 | 2025-10-16 17:02 | 4320 | DDH41
M 80/269 | 2025-10-17 05:02 | 8949.13 | DDH41
M 80/269 | 2025-10-17 17:02 | 2821.2 | DDH41
M 80/269 | 2025-10-18 05:02 | 7314.13 | DDH41
M 80/269 | 2025-10-18 17:02 | 5916.2 | DDH41
M 80/269 | 2025-10-19 05:02 | 7091.63 | DDH41
M 80/269 | 2025-10-19 17:02 | 6204.7 | DDH41
M 80/269 | 2025-10-20 05:02 | 7349.04 | DDH41
M 80/269 | 2025-10-20 17:02 | 5706.2 | DDH41
M 80/269 | 2025-10-21 05:02 | 7562.68 | DDH41
M 80/269 | 2025-10-21 17:02 | 7312.29 | DDH41
M 80/269 | 2025-10-22 05:02 | 4318.7 | DDH41
M 80/269 | 2025-10-22 17:02 | 6371.63 | DDH41
M 80/269 | 2025-10-23 05:02 | 7266.63 | DDH41
M 80/269 | 2025-10-23 17:02 | 6254.71 | DDH41
M 80/269 | 2025-10-24 05:02 | 7183.55 | DDH41
M 80/269 | 2025-10-24 17:02 | 7135.49 | DDH41
M 80/269 | 2025-10-25 05:02 | 7098.7 | DDH41
M 80/269 | 2025-10-25 17:02 | 6141.2 | DDH41
M 80/269 | 2025-10-26 05:02 | 7193.7 | DDH41
M 80/269 | 2025-10-26 17:02 | 6917.5 | DDH41
M 80/269 | 2025-10-27 05:02 | 6838.7 | DDH41
M 80/269 | 2025-10-27 17:02 | 6094.63 | DDH41
M 80/269 | 2025-10-28 05:02 | 8322.6 | DDH41
M 80/269 | 2025-10-28 17:02 | 5866.06 | DDH41
M 80/269 | 2025-10-29 05:02 | 7419.93 | DDH41
M 80/269 | 2025-10-29 17:02 | 6208.7 | DDH41
M 80/269 | 2025-10-30 05:02 | 6917.93 | DDH41
M 80/269 | 2025-10-30 17:02 | 6028.7 | DDH41
M 80/269 | 2025-10-31 05:02 | 7067.93 | DDH41
M 80/269 | 2025-10-31 17:02 | 5258.08 | DDH41
M 80/269 | 2025-11-01 05:02 | 6500 | DDH41
M 80/269 | 2025-11-01 17:02 | 4320 | DDH41
M 80/269 | 2025-11-02 05:02 | 5070 | DDH41
M 80/269 | 2025-11-02 17:02 | 4320 | DDH41
M 80/269 | 2025-11-03 05:02 | 5070 | DDH41
M 80/269 | 2025-11-03 17:02 | 4320 | DDH41
M 80/269 | 2025-11-04 05:02 | 6761.05 | DDH41
M 80/269 | 2025-11-04 17:02 | 4320 | DDH41
M 80/269 | 2025-11-05 05:02 | 6830.43 | DDH41
M 80/269 | 2025-11-05 17:02 | 4320 | DDH41
M 80/269 | 2025-11-06 05:02 | 5070 | DDH41
M 80/269 | 2025-11-06 17:02 | 4830 | DDH41
M 80/268 | 2025-11-07 05:02 | 6177.93 | DDH41
M 80/268 | 2025-11-07 17:02 | 5365.85 | DDH41
M 80/268 | 2025-11-08 05:02 | 7790 | DDH41
M 80/268 | 2025-11-08 17:02 | 5237.93 | DDH41
M 80/268 | 2025-11-09 05:02 | 6720 | DDH41
M 80/268 | 2025-11-09 17:02 | 0 | DDH41
M 80/268 | 2025-11-10 05:02 | 5720 | DDH41
M 80/268 | 2025-11-10 17:02 | 0 | DDH41
M 80/268 | 2025-11-11 05:02 | 5720 | DDH41
M 80/268 | 2025-11-11 17:02 | 0 | DDH41
M 80/268 | 2025-11-12 05:02 | 5720 | DDH41
M 80/268 | 2025-11-12 17:02 | 0 | DDH41
M 80/268 | 2025-11-13 05:02 | 2840 | DDH41
M 80/268 | 2025-11-13 17:02 | 0 | DDH41
M 80/268 | 2025-11-14 05:02 | 5140 | DDH41
M 80/268 | 2025-11-14 17:02 | 0 | DDH41
MOB\DEMOB | 2025-11-15 05:02 | 4460 | DDH41
MOB\DEMOB | 2025-11-15 17:02 | 11077.31 | DDH41
MOB\DEMOB | 2025-11-16 05:02 | 4320 | DDH41
MOB\DEMOB | 2025-11-16 17:02 | 4320 | DDH41
MOB\DEMOB | 2025-11-17 05:02 | 4320 | DDH41
MOB\DEMOB | 2025-11-17 17:02 | 4320 | DDH41
MOB\DEMOB | 2025-11-18 05:02 | 5420 | DDH41
MOB\DEMOB | 2025-11-18 17:02 | 4960 | DDH41
MOB\DEMOB | 2025-11-19 05:02 | 10480.71 | DDH41

## DDH1 RIG 41
[5 empty] | Holes Completed: | 48 |  | Accom | 112190 |  | Sum PQ | 2892.3 |  | Sum HQ | 1758.9 | [7 empty] | Drilling Cost | 899384.5 |  |  |  | Tool Cost | 111000 | [10 empty] | Total Activity Costs | 558250 | Total Consumable Costs | 121436.47 | 1802260.97 |  |  | 376.5772
|  | RIG 41 | [5 empty] | Rate | 130 | Hole 1 |  | 175 |  |  | 135 | Hole 2 |  | 175 |  |  | 135 |  |  |  | 175 | 155 | 420 |  |  | 460 | 460 |  | 360 | 360
[5 empty] | Hole 1 | Hole 2 |  |  |  | PQ3 |  |  | HQ3 |  |  | PQ3 |  |  | HQ3 |  |  |  |  | Slow Pen rate Normalised | [11 empty] | 0 | 0 | [8 empty] | Accomodation Rate |  |  | 403.3789 | 317.7495
Tenement | Purpose | Hole Type | Date | Shift | Hole ID | Hole ID | Driller Name | Personel (incl driller) | Accom Cost | Depth From | Depth To | Length | Depth From | Depth To | Length | Depth From | Depth To | Length | Depth From | Depth To | Length | Total Length | Drilling Cost | Charged Drilling Cost | PQ Ori | HQ Ori | Gyro Tool | Tool ID | Total tool Cost | Drill Time | Active hours (Other than drilling) | Comment (IF less than 10hours EXPLAIN) | Inactive Hours (Other than client standby) | Standby Total Hours | Comment (IF more than 2 hours EXPLAIN) | Uncharged Hours | Maintenance | Comments | Total Daily Hours | Comments (IF not 12hrs EXPLAIN) | Total Activity Hours Cost | ***Insert Total Consumable Costs*** | Total Consumables Cost (-Accom) | Total Costs | Total Cost Charged (Plod) | 0.067988 | Cummulative Cost | EOM Cummulative Cost | Combined Cost Per Metre | PLOD LINK | Comments | Stem | Year | Month | Day | Shift Shorthand
|  | Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 |  | 20 | 21 |  | 22 | 23 | 24 |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 |  | 33 | 34 | 35 |  | 36 | 37 |  |  | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71
#N/A |  | MET | 2025-06-13 05:02 | DS 5am |  |  | Peter Gillespie | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 1 | 1 | 13122 | 750 | [9 empty] | 0 |  | 0 |  |  | 750 |  | 0 | Cummulative Cost 38: 750; EOM Cummulative Cost 39: 750; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Start mobilisation to site; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250613D; Shift Shorthand 49: 2025-06
#N/A |  | 2025-06-13 17:02 | 2025-06-13 17:02 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | EOM Cummulative Cost 39: 750; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: NO NIGHTSHIFT DURING MOB; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250613N; Shift Shorthand 49: 2025-06
#N/A |  | MET | 2025-06-14 05:02 | DS 5am |  |  | Peter Gillespie | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 1 | 1 | 13122 | 750 | [9 empty] | 0 |  | 0 |  |  | 750 |  | 0 | EOM Cummulative Cost 39: 1500; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Day 2 of mobilisation; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250614D; Shift Shorthand 49: 2025-06
#N/A |  | 2025-06-14 17:02 | 2025-06-14 17:02 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | EOM Cummulative Cost 39: 1500; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: NO NIGHTSHIFT DURING MOB; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250614N; Shift Shorthand 49: 2025-06
#N/A |  | MET | 2025-06-15 05:02 | DS 5am |  |  | Peter Gillespie | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 1 | 1 | 13122 | 750 |  |  |  |  | 7 |  | 5 |  |  | 12 |  | 2520 |  |  | 3270 | 3095 | 0 | EOM Cummulative Cost 39: 4770; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Completed mobilisation, started unloading at Speewah; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250615D; Shift Shorthand 49: 2025-06
#N/A |  | 2025-06-15 17:02 | 2025-06-15 17:02 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  | EOM Cummulative Cost 39: 4770; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: NO NIGHTSHIFT DURING MOB; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250615N; Shift Shorthand 49: 2025-06
#N/A |  | MET | 2025-06-16 05:02 | DS 5am |  |  | Peter Gillespie | 0 | 0 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 1 | 1 | 13122 | 750 |  | 4.75 |  | 4.75 |  |  | 2.5 |  |  | 12 |  | 3895 |  |  | 4645 | 4470 | 0 | EOM Cummulative Cost 39: 9415; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Inductions, welcome to country, establish water supply, set-up camp; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250616D; Shift Shorthand 49: 2025-06
#N/A |  | 2025-06-16 17:02 | 2025-06-16 17:02 | NS 5pm | [10 empty] | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  | EOM Cummulative Cost 39: 9415; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: NO NIGHTSHIFT DURING MOB; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250616N; Shift Shorthand 49: 2025-06
#N/A |  | MET | 2025-06-17 05:02 | DS 5am |  |  | Zeke Shackelton | 4 | 520 | [5 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 1 | 1 | 1 | 13122 | 750 |  | 10.75 |  |  | 1.25 |  |  |  |  | 12 |  | 5395 |  |  | 6665 | 6490 | 0.07802 | EOM Cummulative Cost 39: 16080; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Establish water supply, wait for sumps to get dug, set-up rig on 1st pad; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250617D; Shift Shorthand 49: 2025-06
#N/A |  | MET | 2025-06-17 17:02 | NS 5pm |  |  | Peter Gillespie | 3 | 390 | [5 empty] | 0 |  |  | 0 |  |  | 0 | [7 empty] | 0 |  | 7.25 |  | 3.25 | 1.5 |  |  |  |  | 12 |  | 5045 |  |  | 5435 | 5435 | 0.071757 | EOM Cummulative Cost 39: 21515; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Complete rig set-up on pad, run poly pipe to next pad, wait for pre drill inspection on DS before commencing drilling; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250617N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-18 05:02 | DS 5am | SF25_DMET006 |  | Zeke Shackelton | 4 | 520 | 0 | 24.5 | 24.5 |  |  | 0 |  |  | 0 |  |  | 0 | 24.5 | 4287.5 | 4287.5 | 1 | 1 | 1 | 13122 | 750 | 8.75 | 1.5 |  |  | 1.75 |  |  |  |  | 12 |  | 1320 |  | 547.64 | 7425.14 | 7250.14 | 0.070032 | Cummulative Cost 38: 28940.14; EOM Cummulative Cost 39: 28940.14; Combined Cost Per Metre 40: 303.0669; PLOD LINK 41: LINK; Comments 42: Standby on client for pre-drill checks and inductions, commence drilling PQ3 from surface, pull out barrel and run in rock roller, pull out rock roll and install PVC collar, run in barrel and continue coring PQ3, survey @ 18m, condition hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250618D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-18 17:02 | NS 5pm | SF25_DMET007 |  | Peter Gillespie | 3 | 390 | 24.5 | 51.5 | 27 |  |  | 0 |  |  | 0 |  |  | 0 | 27 | 4725 | 4725 |  |  |  |  | 0 | 10.25 | 1 |  |  | 0.75 |  |  |  |  | 12 |  | 730 |  | 253.98 | 6098.98 | 6098.98 | 0.063945 | Cummulative Cost 38: 35039.12; EOM Cummulative Cost 39: 35039.12; Combined Cost Per Metre 40: 225.8881; PLOD LINK 41: LINK; Comments 42: Continue to drill, pull rods due to tube not seating, remove dropped core from barrel, run rods in, survey, deliver core at E.O.S as per client request; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250618N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-19 05:02 | DS 5am | SF25_DMET008 |  | Zeke Shackelton | 4 | 520 | 51.5 | 80 | 28.5 |  |  | 0 |  |  | 0 |  |  | 0 | 28.5 | 4987.5 | 4987.5 | 1 | 1 | 1 | 13122 | 750 | 9.25 | 2.5 |  |  | 0.25 |  |  |  |  | 12 |  | 1240 |  | 878.93 | 8376.43 | 8201.43 | 0.062079 | Cummulative Cost 38: 43415.55; EOM Cummulative Cost 39: 43415.55; Combined Cost Per Metre 40: 293.9098; PLOD LINK 41: LINK; Comments 42: Continue to drill PQ3, survey @ 54m, 72m and EOH. EOH @ 80m, move equipment and move in ST to pull out rods, mast down, move rig, mast up, setup drill site; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250619D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-19 17:02 | NS 5pm | SF25_DMET007 |  | Peter Gillespie | 3 | 390 | 0 | 27.5 | 27.5 |  |  | 0 |  |  | 0 |  |  | 0 | 27.5 | 4812.5 | 4812.5 |  |  |  |  | 0 | 8 | 3 |  | 1 | [5 empty] | 12 |  | 1740 |  | 301 | 7243.5 | 7243.5 | 0.053841 | Cummulative Cost 38: 50659.05; EOM Cummulative Cost 39: 50659.05; Combined Cost Per Metre 40: 263.4; PLOD LINK 41: LINK; Comments 42: Continue to set up site, start PQ3 core from surface, open hole with 6 1/2" roller, run in 2.8m of PVC, run in 3m barrel, survey, bit change, drop core off @ E.O.S.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250619N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-20 05:02 | DS 5am | SF25_DMET008 |  | Zeke Shackelton | 4 | 520 | 27.5 | 59.3 | 31.8 |  |  | 0 |  |  | 0 |  |  | 0 | 31.8 | 5565 | 5565 | 1 | 1 | 1 | 13122 | 750 | 11 | 0.75 |  |  | 0.25 |  |  |  |  | 12 |  | 435 |  | 1030.72 | 8300.72 | 8125.72 | 0.062645 | Cummulative Cost 38: 58959.77; EOM Cummulative Cost 39: 58959.77; Combined Cost Per Metre 40: 261.0289; PLOD LINK 41: LINK; Comments 42: continue to drill PQ3, survey @ 36m & 54m, lost water return @ 42m, condition hole throughout shift. Lined sumps on next 2 pads; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250620D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-20 17:02 | NS 5pm | SF25_DMET009 |  | Peter Gillespie | 3 | 390 | 59.3 | 80 | 20.7 |  |  | 0 |  |  | 0 |  |  | 0 | 20.7 | 3622.5 | 3622.5 |  |  |  |  | 0 | 7 | 2 |  | 1 | 2 | Rig move at night? |  |  |  | 12 |  | 2000 |  | 117.93 | 6130.43 | 6130.43 | 0.063617 | Cummulative Cost 38: 65090.2; EOM Cummulative Cost 39: 65090.2; Combined Cost Per Metre 40: 296.156; PLOD LINK 41: LINK; Comments 42: Continue to drill / Drill to 80m / Survey / Set up to pull rods onto back of rod truck / Pull all rods out / Mast down / Drop core off @ E.O.S / Standby on client due to no rig moves on N/S.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250620N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-21 05:02 | DS 5am | SF25_DMET001 |  | Zeke Shackelton | 4 | 520 | 0 | 1.9 | 1.9 |  |  | 0 |  |  | 0 |  |  | 0 | 1.9 | 332.5 | 575 | 1 | 1 | 1 | 13122 | 750 | 1.25 | 6 |  | 0.25 | 4.5 |  |  |  |  | 12 |  | 4470 |  |  | 6315 | 6140 | 0.082344 | Cummulative Cost 38: 71405.2; EOM Cummulative Cost 39: 71405.2; PLOD LINK 41: LINK; Comments 42: Standby until sunrise to commence rig move, moved rig to site. Standby to flatten pad. Set up site, hard ground to dig. Started to drill pq3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250621D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-21 17:02 | NS 5pm | SF25_DMET001 |  | Peter Gillespie | 3 | 390 | 1.9 | 21.4 | 19.5 |  |  | 0 |  |  | 0 |  |  | 0 | 19.5 | 3412.5 | 4140 |  |  |  |  | 0 | 9 | 2 |  |  | 1 |  |  |  |  | 12 |  | 1280 |  | 772.65 | 6582.65 | 6582.65 | 0.059247 | Cummulative Cost 38: 77987.85; EOM Cummulative Cost 39: 77987.85; Combined Cost Per Metre 40: 337.5718; PLOD LINK 41: LINK; Comments 42: Continue to drill. Open hole up with 6 1/2" roller. Run in 6m 150mm PVC. Run in 3m PQ barrel, slow going due to sticky clays. Short runs all shift. Drop core off at E.O.S as per client's request.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250621N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-22 05:02 | DS 5am | SF25_DMET001 |  | Zeke Shackelton | 4 | 520 | 21.4 | 51.4 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 | 1 | 1 | 1 | 13122 | 750 | 10.5 | 0.75 |  |  | 0.25 |  | 0.5 |  |  | 12 |  | 435 |  |  | 6955 | 6780 | 0.074766 | Cummulative Cost 38: 84942.85; EOM Cummulative Cost 39: 84942.85; Combined Cost Per Metre 40: 231.8333; PLOD LINK 41: LINK; Comments 42: continued to drill PQ3. survey @ 18m & 36m, toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250622D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-22 17:02 | NS 5pm | SF25_DMET001 |  | Peter Gillespie | 3 | 390 | 51.4 | 80 | 28.6 |  |  | 0 |  |  | 0 |  |  | 0 | 28.6 | 5005 | 5005 |  |  |  |  | 0 | 10 | 0.5 |  |  | 1 |  | 0.5 |  |  | 12 |  | 590 |  | 117.93 | 6102.93 | 6102.93 | 0.063904 | Cummulative Cost 38: 91045.78; EOM Cummulative Cost 39: 91045.78; Combined Cost Per Metre 40: 213.3892; PLOD LINK 41: LINK; Comments 42: Continue to drill, Survey @ 54 & 72m. Drop core off at E.O.S as per client's request.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250622N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-23 05:02 | DS 5am | SF25_DMET001 |  | Zeke Shackelton | 4 | 520 | 80 | 104.2 | 24.2 |  |  | 0 |  |  | 0 |  |  | 0 | 24.2 | 4235 | 5175 | 1 | 1 | 1 | 13122 | 750 | 11.25 | 0.5 |  |  | 0.25 |  |  |  |  | 12 |  | 320 |  |  | 6765 | 6590 | 0.076866 | Cummulative Cost 38: 97810.78; EOM Cummulative Cost 39: 97810.78; Combined Cost Per Metre 40: 279.5455; PLOD LINK 41: LINK; Comments 42: continued to drill PQ3. survey @ 90m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250623D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-23 17:02 | NS 5pm | SF25_DMET001 |  | Peter Gillespie | 3 | 390 | 104.2 | 110 | 5.8 |  |  | 0 |  |  | 0 |  |  | 0 | 5.8 | 1015 | 1840 |  |  |  |  | 0 | 4 | 4.75 |  | 1 | 2.25 | Rig move at night? |  |  |  | 12 |  | 3355 |  | 232 | 5817 | 5817 | 0.067045 | Cummulative Cost 38: 103627.78; EOM Cummulative Cost 39: 103627.78; PLOD LINK 41: LINK; Comments 42: Continue to drill in broken ground with 20% water return, survey EOH. Pull rod out on to back of rod truck. Drop core off at E.O.S as per client's request.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250623N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-24 05:02 | DS 5am | SF25_DMET002 |  | Zeke Shackelton | 4 | 520 | 0 | 12 | 12 |  |  | 0 |  |  | 0 |  |  | 0 | 12 | 2100 | 2645 | 1 | 1 | 1 | 13122 | 750 | 5.75 | 5 |  |  | 1.25 |  |  |  |  | 12 |  | 2750 |  | 500.08 | 7165.08 | 6990.08 | 0.072574 | Cummulative Cost 38: 110792.86; EOM Cummulative Cost 39: 110792.86; Combined Cost Per Metre 40: 597.09; PLOD LINK 41: LINK; Comments 42: Standby until sunrise to begin rig move to next pad, move all equipment to new pad and setup site, commence drilling PQ3 from surface, pull out barrel, run in rock roller and ream open hole, pull out and install PVC collar, run in 3m barrel and continue to drill PQ3.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250624D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-24 17:02 | NS 5pm | SF25_DMET002 |  | Peter Gillespie | 3 | 390 | 12 | 42.6 | 30.6 |  |  | 0 |  |  | 0 |  |  | 0 | 30.6 | 5355 | 5355 |  |  |  |  | 0 | 10 | 0.5 |  |  | 1 |  | 0.5 |  |  | 12 |  | 590 |  | 232 | 6567 | 6567 | 0.059388 | Cummulative Cost 38: 117359.86; EOM Cummulative Cost 39: 117359.86; Combined Cost Per Metre 40: 214.6078; PLOD LINK 41: LINK; Comments 42: Continue to drill, Survey x2. Drop core off at E.O.S as per client's request. Crew change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250624N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-25 05:02 | DS 5am | SF25_DMET002 |  | Benjamin Payton | 4 | 520 | 42.6 | 48.6 | 6 |  |  | 0 |  |  | 0 |  |  | 0 | 6 | 1050 | 1265 | 1 | 1 | 1 | 13122 | 750 | 2.75 |  |  | 0.25 | 1 |  | 8 |  |  | 12 |  | 450 |  |  | 2985 | 2810 | 0.1742 | Cummulative Cost 38: 120344.86; EOM Cummulative Cost 39: 120344.86; Combined Cost Per Metre 40: 497.5; PLOD LINK 41: LINK; Comments 42: Crew change, smoking ceremony, Pre-shift meeting, Pre-Start all equipment, continue to drill PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250625D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-25 17:02 | NS 5pm | SF25_DMET002 |  | Zeke Shackelton | 3 | 390 | 48.6 | 51.8 | 3.2 | 51.8 | 65.6 | 13.8 |  |  | 0 |  |  | 0 | 17 | 2423 | 3105 |  |  |  |  | 0 | 6.75 | 5 |  | 0.25 | [5 empty] | 12 |  | 2390 |  |  | 5885 | 5885 | 0.06627 | Cummulative Cost 38: 126229.86; EOM Cummulative Cost 39: 126229.86; Combined Cost Per Metre 40: 346.1765; PLOD LINK 41: LINK; Comments 42: Continued to drill PQ3, ground too hard changed to a softer bit. Drilling became unsafe due to ground conditions so pulled out and cased off PQ. Ran in HQ barrel and drilled HQ for the rest of the shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250625N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-26 05:02 | DS 5am | SF25_DMET002 |  | Benjamin Payton | 4 | 520 |  |  | 0 | 65.6 | 99.6 | 34 |  |  | 0 |  |  | 0 | 34 | 4590 | 5175 | 1 | 1 | 1 | 13122 | 750 | 11.25 | 0.5 |  | 0.25 | [5 empty] | 12 |  | 320 |  | 878.93 | 7643.93 | 7468.93 | 0.068028 | Cummulative Cost 38: 133873.79; EOM Cummulative Cost 39: 133873.79; Combined Cost Per Metre 40: 224.8215; PLOD LINK 41: LINK; Comments 42: Continue to drill HQ3, hard broken formation-short runs from 65.6m to 75.6m, competent/hard ground from 75.6m to 99.6m, survey @ 72m & 90m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250626D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-26 17:02 | NS 5pm | SF25_DMET002 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 99.6 | 130.7 | 31.1 |  |  | 0 |  |  | 0 | 31.1 | 4198.5 | 5060 |  |  |  |  | 0 | 11 | 0.75 |  | 0.25 | [5 empty] | 12 |  | 435 |  |  | 5885 | 5885 | 0.06627 | Cummulative Cost 38: 139758.79; EOM Cummulative Cost 39: 139758.79; Combined Cost Per Metre 40: 189.2283; PLOD LINK 41: LINK; Comments 42: Continue to drill HQ3 to end of hole depth 130.7m.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250626N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-27 05:02 | DS 5am | SF25_DMET003 |  | Benjamin Payton | 4 | 520 | 0 | 18.1 | 18.1 |  |  | 0 |  |  | 0 |  |  | 0 | 18.1 | 3167.5 | 3167.5 | 1 | 1 | 1 | 13122 | 750 | 6.75 | 5 |  | 0.25 | [5 empty] | 12 |  | 2390 |  | 395.85 | 7223.35 | 7048.35 | 0.071989 | Cummulative Cost 38: 146982.14; EOM Cummulative Cost 39: 146982.14; Combined Cost Per Metre 40: 399.0801; PLOD LINK 41: LINK; Comments 42: move equipment for EOH to pull rods, Pull HQ rods and barrel, Free PHD casing, Pull PHD casing out, Change Mast dip to -55, Set up rod bench & site again, Drill PQ3 from surface, pull out barrel, run in rock roller and ream open hole, pull out and install PVC collar, run in 3m barrel and continue to drill PQ3.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250627D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-27 17:02 | NS 5pm | SF25_DMET003 |  | Zeke Shackelton | 3 | 390 | 18.1 | 43.9 | 25.8 |  |  | 0 |  |  | 0 |  |  | 0 | 25.8 | 4515 | 4945 |  |  |  |  | 0 | 10.75 | 1 |  | 0.25 | [5 empty] | 12 |  | 550 |  | 407.22 | 6292.22 | 6292.22 | 0.061981 | Cummulative Cost 38: 153274.36; EOM Cummulative Cost 39: 153274.36; Combined Cost Per Metre 40: 243.8845; PLOD LINK 41: LINK; Comments 42: Continued drilling PQ3, slowly lost water return throughout shift, bombed hole to get return back, drilled through sandy patch between 34m to 37m, mixed up thick muds to condition hole, continue to drill PQ3.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250627N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-28 05:02 | DS 5am | SF25_DMET003 |  | Benjamin Payton | 4 | 520 | 43.9 | 75.4 | 31.5 |  |  | 0 |  |  | 0 |  |  | 0 | 31.5 | 5512.5 | 5512.5 | 1 | 1 | 1 | 13122 | 750 | 11.25 | 0.5 |  | 0.25 | [5 empty] | 12 |  | 320 |  | 117.93 | 7220.43 | 7045.43 | 0.072018 | Cummulative Cost 38: 160494.79; EOM Cummulative Cost 39: 160494.79; Combined Cost Per Metre 40: 229.22; PLOD LINK 41: LINK; Comments 42: Continue to drill PQ3, Survey hole @ 54m and 72m, Minimal Water return-30% most of hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250628D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-28 17:02 | NS 5pm | SF25_DMET003 |  | Zeke Shackelton | 3 | 390 | 75.4 | 80 | 4.6 |  |  | 0 |  |  | 0 |  |  | 0 | 4.6 | 805 | 1265 |  |  |  |  | 0 | 2.75 | 3 |  | 0.25 | 6 | Rig move at night? |  |  |  | 12 |  | 3630 |  | 117.93 | 5402.93 | 5402.93 | 0.072183 | Cummulative Cost 38: 165897.72; EOM Cummulative Cost 39: 165897.72; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3,slow drilling, E.O.H 80m, Move rod bench, pull rods onto ST, Mast down rig, start to pack up site ready to move holes. Stand by on Client as no moving rig on N/S, continue with housekeeping and Maintenace; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250628N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-29 05:02 | DS 5am | SF25_DMET003 |  | Benjamin Payton | 4 | 520 | 0 | 15.4 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 | 15.4 | 2695 | 2695 | 1 | 1 | 1 | 13122 | 750 | 4.75 | 5.5 |  | 0.25 | 1 |  | 0.5 |  |  | 12 |  | 2980 |  | 396.12 | 7341.12 | 7166.12 | 0.070834 | Cummulative Cost 38: 173238.84; EOM Cummulative Cost 39: 173238.84; Combined Cost Per Metre 40: 476.6961; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, Stanby until daylight to move rig, Move rig & equipment to next pad, Set up drill site-tight pad positioning gear, Line rig up to client hole requirements, Set up site, Strat drilling from surface, Pull out barrel, Run in rock roller and ream open hole, Pull out and install PVC collar, Run in 3m barrel and continue to drill PQ3, Weekly toolbox meeting Assets: DR41 / LT 92 / LP73 / RV 04 / ST56 / GP62 / GP04 / KV08 / BV17 / DDH1DL173 / DDH1DL160; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250629D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-29 17:02 | NS 5pm | SF25_DMET003 |  | Zeke Shackelton | 3 | 390 | 15.4 | 45.4 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10.25 | 1 |  | 0.25 |  |  | 0.5 |  |  | 12 |  | 550 |  |  | 6190 | 6190 | 0.063005 | Cummulative Cost 38: 179428.84; EOM Cummulative Cost 39: 179428.84; Combined Cost Per Metre 40: 206.3333; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250629N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-30 05:02 | DS 5am | SF25_DMET004 |  | Benjamin Payton | 4 | 520 | 45.4 | 62.5 | 17.1 | 62.5 | 63.4 | 0.9 |  |  | 0 |  |  | 0 | 18 | 3114 | 3450 | 1 | 1 | 1 | 13122 | 750 | 7.5 | 4.25 |  | 0.25 | [5 empty] | 12 |  | 2045 |  | 776.68 | 7541.68 | 7366.68 | 0.06895 | Cummulative Cost 38: 186970.52; EOM Cummulative Cost 39: 186970.52; Combined Cost Per Metre 40: 418.9822; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250630D; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-06-30 17:02 | NS 5pm | SF25_DMET004 |  | Zeke Shackelton | 3 | 390 |  |  | 0 | 63.4 | 66.4 | 3 |  |  | 0 |  |  | 0 | 3 | 405 | 575 |  |  |  |  | 0 | 1.25 | 3 |  | 2.25 | 5.5 | Water springing from pad |  |  |  | 12 |  | 4170 |  |  | 5135 | 5135 | 0.075949 | Cummulative Cost 38: 192105.52; EOM Cummulative Cost 39: 192105.52; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 06; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250630N; Shift Shorthand 49: 2025-06
M 80/268 | Met | MET | 2025-07-01 05:02 | DS 5am | SF25_DMET008 |  | Benjamin Payton | 4 | 520 | 0 | 1.8 | 1.8 |  |  | 0 |  |  | 0 |  |  | 0 | 1.8 | 315 | 460 | 1 | 1 | 1 | 13122 | 750 | 1 | 4 | Rig went to wrong pad and set up - costs associated to this were removed - AST | 0.75 | 1 |  | 5.25 |  |  | 12 |  | 2470 |  | 761 | 4961 | 4786 | 0.10482 | Cummulative Cost 38: 197066.52; EOM Cummulative Cost 39: 4961; PLOD LINK 41: LINK; Comments 42: Drillers went to the wrong pad and setup. They initially charged for this, but the Plod was refused as we showed them the pad and put a collar peg in for the correct site. The plod has since been adjusted to not include costs associated with the incorrect move.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507001D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-01 17:02 | NS 5pm | SF25_DMET008 |  | Zeke Shackelton | 3 | 390 | 1.8 | 20.2 | 18.4 |  |  | 0 |  |  | 0 |  |  | 0 | 18.4 | 3220 | 4140 |  |  |  |  | 0 | 9 | 2.75 |  | 0.25 | [5 empty] | 12 |  | 1355 |  | 395 | 6280 | 6280.85 | 0.062102 | Cummulative Cost 38: 203346.52; EOM Cummulative Cost 39: 11241; Combined Cost Per Metre 40: 341.3043; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-Start all equipment, Continue drilling PQ3 then drill MR to 6m case off with pvc. change over to 3m barrel and and continue to drill PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507001N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-02 05:02 | DS 5am | SF25_DMET008 |  | Benjamin Payton | 3 | 390 | 20.2 | 41.8 | 21.6 |  |  | 0 |  |  | 0 |  |  | 0 | 21.6 | 3780 | 4485 | 1 | 1 | 1 | 13122 | 750 | 9.75 | 1.5 |  | 0.25 | 0.5 |  |  |  |  | 12 |  | 960 |  | 0 | 6585 | 6410 | 0.059226 | Cummulative Cost 38: 209931.52; EOM Cummulative Cost 39: 17826; Combined Cost Per Metre 40: 304.8611; PLOD LINK 41: LINK; Comments 42: Note: Charged for 3 accom instead of listed 4 people. (-$120) Pre-shift meeting, Pre-start all equipment, Drill PQ3, Pull rods for bit change/Worn bit,= (29.8m drilled with new bit) Ream 18m back to bottom due to cave in, Drill on PQ3, Survey hole @ 36m, Stop drilling for Client drill pad inspections, sign offs; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507002D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-02 17:02 | NS 5pm | SF25_DMET008 |  | Zeke Shackelton | 3 | 390 | 41.8 | 50 | 8.2 | 50 | 54.6 | 4.6 | 0 | 1.8 | 1.8 |  |  | 0 | 14.6 | 2371 | 2875 |  |  |  |  | 0 | 6.25 | 5.5 | Difficult ground conditions listed - short bit life and 4 hours reaming | 0.25 | [5 empty] | 12 |  | 2620 |  | 0 | 5885 | 5885 | 0.06627 | Cummulative Cost 38: 215816.52; EOM Cummulative Cost 39: 23711; Combined Cost Per Metre 40: 403.0822; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507002N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-03 05:02 | DS 5am | SF25_DMET008 | SF25_DMET009 | Benjamin Payton | 3 | 390 | 54.6 | 60.2 | 5.6 |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 5.6 | 980 | 1955 | 1 | 1 | 1 | 13122 | 750 | 4.25 | 6.5 |  | 0.25 | 0.5 | Rig/site inspection 30mins |  | 0.5 |  | 12 |  | 3260 |  | 761 | 7116 | 6941 | 0.054806 | Cummulative Cost 38: 222932.52; EOM Cummulative Cost 39: 30827; Combined Cost Per Metre 40: 1270.7143; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507003D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-03 17:02 | NS 5pm | SF25_DMET009 |  | Zeke Shackelton | 3 | 390 | 1.8 | 10.2 | 8.4 |  |  | 0 |  |  | 0 |  |  | 0 | 8.4 | 1470 | 3680 |  |  |  |  | 0 | 8 | 3 | Difficult ground conditions - broken oxides - geo checked core | 0.25 |  |  |  | 0.75 |  | 12 |  | 1470 |  | 395 | 5935 | 5935.85 | 0.065712 | Cummulative Cost 38: 228867.52; EOM Cummulative Cost 39: 36762; Combined Cost Per Metre 40: 706.5476; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to dill PQ3. pull out case off with pvc swelling clays sand and cave in having to ream to bottom of hole every run, Slow going due to poor formation being drilled, pulled barrel x two times first time to clean barrel second to change bit, snapped wireline housekeeping and Maintenace; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507003N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-04 05:02 | DS 5am | SF25_DMET009 |  | Benjamin Payton | 3 | 390 | 10.2 | 21.4 | 11.2 |  |  | 0 |  |  | 0 |  |  | 0 | 11.2 | 1960 | 4255 | 1 | 1 | 1 | 13122 | 750 | 9.25 | 2.5 | Difficult ground conditions - broken oxides - had to ream PWT to 12m | 0.25 | [5 empty] | 12 |  | 1240 |  | 290.49 | 6925.49 | 6750.49 | 0.056314 | Cummulative Cost 38: 235793.01; EOM Cummulative Cost 39: 43687.49; Combined Cost Per Metre 40: 618.3473; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, Drill PQ3, Drill first 1.5m through pressurized ground and hole collaring off, Slow going to get down fto depth for reaming PWT, Ream 12m PWT casing into hole, Drill on PQ3 = Extremely fractured formation, short runs Survey hole @ 18m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507004D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-04 17:02 | NS 5pm | SF25_DMET009 |  | Zeke Shackelton | 3 | 390 | 21.4 | 40.6 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 | 19.2 | 3360 | 3910 |  |  |  |  | 0 | 8.5 | 2.25 |  | 1.25 |  | Core farm delivery listed as 1 hour inactive time - does the drill rig have to stop for core delivery? - Due to the limited size of drill pad - they couldn't move the core until they moved site - so was done all at once in bulk |  |  |  | 12 |  | 1485 |  | 117.93 | 5902.93 | 5902.93 | 0.066069 | Cummulative Cost 38: 241695.94; EOM Cummulative Cost 39: 49590.42; Combined Cost Per Metre 40: 307.4443; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507004N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-05 05:02 | DS 5am | SF25_DMET009 |  | Benjamin Payton | 3 | 390 | 40.6 | 63.9 | 23.3 |  |  | 0 |  |  | 0 |  |  | 0 | 23.3 | 4077.5 | 4485 | 1 | 1 | 1 | 13122 | 750 | 9.75 | 2 | Minor reaming of PWT | 0.25 | [5 empty] | 12 |  | 1010 |  | 117.93 | 6752.93 | 6577.93 | 0.057753 | Cummulative Cost 38: 248448.87; EOM Cummulative Cost 39: 56343.35; Combined Cost Per Metre 40: 289.8253; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, Pull rods for core in barrel, Ream back to bottom from 18m, Drill on PQ3, Survey hole @ 54m, Advancve PWT casing 3m as rattled down low; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507005D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-05 17:02 | NS 5pm | SF25_DMET009 |  | Zeke Shackelton | 3 | 390 | 63.9 | 79.1 | 15.2 |  |  | 0 |  |  | 0 |  |  | 0 | 15.2 | 2660 | 4025 |  |  |  |  | 0 | 8.75 | 2.5 | Slow reaming listed | 0.25 |  |  |  | 0.5 |  | 12 |  | 1240 |  | 117.93 | 5772.93 | 5772.93 | 0.067557 | Cummulative Cost 38: 254221.8; EOM Cummulative Cost 39: 62116.28; Combined Cost Per Metre 40: 379.798; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue to dill PQ3. reamed 1m of pwt very slow reaming. pulled rods ground is to hard put a softer bit on. Drilling PQ3 still slow due to hard ground. survey at 72m.housekeeping and Maintenace; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507005N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-06 05:02 | DS 5am | SF25_DMET009 |  | Benjamin Payton | 3 | 390 | 79.1 | 97 | 17.9 |  |  | 0 |  |  | 0 |  |  | 0 | 17.9 | 3132.5 | 4600 | 1 | 1 | 1 | 13122 | 750 | 10 | 1.25 |  | 0.25 |  |  | 0.5 |  |  | 12 |  | 665 |  | 878.93 | 7283.93 | 7108.93 | 0.053543 | Cummulative Cost 38: 261505.73; EOM Cummulative Cost 39: 69400.21; Combined Cost Per Metre 40: 406.9235; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, Drill on PQ3, Bit change /worn bit = hard abrasive formation (15m drilled with new 12-14 bit), Run in with rod grease, Drill on PQ3, Survey hole @ 90m, weekly toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507006D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-06 17:02 | NS 5pm | SF25_DMET009 |  | Zeke Shackelton | 3 | 390 | 97 | 105.3 | 8.3 |  |  | 0 |  |  | 0 |  |  | 0 | 8.3 | 1452.5 | 2070 |  |  |  |  | 0 | 4.5 | 3.75 |  | 0.25 | 3 |  | 0.5 |  |  | 12 |  | 2895 |  | 117.93 | 5472.93 | 5472.93 | 0.07126 | Cummulative Cost 38: 266978.66; EOM Cummulative Cost 39: 74873.14; Combined Cost Per Metre 40: 659.3892; PLOD LINK 41: LINK; Comments 42: Toolbox meeting. Pre-shift meeting, Pre-start all equipment, continue to dill PQ3 to E.O.H 105.3. pulled rods out and casing. established water for next hole packed site up. housekeeping and Maintenace; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507006N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-07 05:02 | DS 5am | SF25_DMET009 | SF25_DMET012 | Benjamin Payton | 3 | 390 | 105.3 | 105.3 | 0 |  |  | 0 | 0 | 10.4 | 10.4 |  |  | 0 | 10.4 | 1820 | 2185 | 1 | 1 | 1 | 13122 | 750 | 4.75 | 5.5 | Standby and packup due to no moving on NS | 0.75 | 1 |  |  |  |  | 12 |  | 3160 |  | 422.05 | 6907.05 | 6732.05 | 0.056464 | Cummulative Cost 38: 273885.71; EOM Cummulative Cost 39: 81780.19; Combined Cost Per Metre 40: 664.1394; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507007D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-07 17:02 | NS 5pm | SF25_DMET012 |  | Zeke Shackelton | 3 | 390 | 10.4 | 36.8 | 26.4 |  |  | 0 |  |  | 0 |  |  | 0 | 26.4 | 4620 | 4945 |  |  |  |  | 0 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 |  | 117.93 | 5952.93 | 5952.93 | 0.065514 | Cummulative Cost 38: 279838.64; EOM Cummulative Cost 39: 87733.12; Combined Cost Per Metre 40: 225.4898; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507007N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-08 05:02 | DS 5am | SF25_DMET012 |  | Carl Jonas | 3 | 390 | 36.8 | 42.4 | 5.6 |  |  | 0 |  |  | 0 |  |  | 0 | 5.6 | 980 | 3220 | 1 | 1 | 1 | 13122 | 750 | 7 | 4.75 |  | 0.25 | [5 empty] | 12 |  | 2275 |  | 235.86 | 6870.86 | 6695.86 | 0.056761 | Cummulative Cost 38: 286709.5; EOM Cummulative Cost 39: 94603.98; Combined Cost Per Metre 40: 1226.9393; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Finish setting up drill site, make up barrel & tubes, check all running gear / Wait on water for sumps to fill / Client pre-drill inspection / Drill PQ3 from surface / Open out hole with rock roller, Grout 6.0m 150mm PVC in place, Flush back to bottom, Drill on PQ3 / Pull rods out and change bit for ground conditions to try improve core recovery in soft sands & broken formation; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507008D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-08 17:02 | NS 5pm | SF25_DMET012 |  | Dean Melville | 2 | 260 | 42.4 | 69.4 | 27 |  |  | 0 |  |  | 0 |  |  | 0 | 27 | 4725 | 4725 |  |  |  |  | 0 | 9 | 1.5 |  | 0.5 |  |  |  | 1 |  | 12 |  | 870 |  | 117.93 | 5972.93 | 5972.93 | 0.04353 | Cummulative Cost 38: 292682.43; EOM Cummulative Cost 39: 100576.91; Combined Cost Per Metre 40: 221.2196; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507008N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-09 05:02 | DS 5am | SF25_DMET012 |  | Carl Jonas | 5 | 650 | 69.4 | 79 | 9.6 |  |  | 0 |  |  | 0 |  |  | 0 | 9.6 | 1680 | 2070 | 1 | 1 | 1 | 13122 | 750 | 4.5 |  | Breakdown repairs | 0.5 |  |  |  | 7 |  | 12 |  | 180 |  | 235.86 | 3885.86 | 3710.86 | 0.16727 | Cummulative Cost 38: 296568.29; EOM Cummulative Cost 39: 104462.77; Combined Cost Per Metre 40: 404.7771; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507009D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-09 17:02 | NS 5pm | SF25_DMET012 | SF25_DMET013 | Dean Melville | 2 | 260 | 79 | 90.4 | 11.4 |  |  | 0 |  |  | 0 |  |  | 0 | 11.4 | 1995 | 1995 |  |  |  |  | 0 | 4 | 5 | Rig Move | 0.5 | 2.5 | Rig move at night - we are now permitting moves at night |  |  |  | 12 |  | 3380 |  | 236.49 | 5871.49 | 5871.49 | 0.044282 | Cummulative Cost 38: 302439.78; EOM Cummulative Cost 39: 110334.26; Combined Cost Per Metre 40: 515.043; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2507009N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-10 05:02 | DS 5am | SF25_DMET013 |  | Carl Jonas | 4 | 520 | 0 | 7.9 | 7.9 |  |  | 0 |  |  | 0 |  |  | 0 | 7.9 | 1382.5 | 2300 | 1 | 1 | 1 | 13122 | 750 | 5 | 2.5 | Rig move and repairs | 0.5 | 2 | Rig move at night - we are now permitting moves at night |  | 2 |  | 12 |  | 2050 |  | 570.72 | 6190.72 | 6015.72 | 0.083997 | Cummulative Cost 38: 308630.5; EOM Cummulative Cost 39: 116524.98; Combined Cost Per Metre 40: 783.6354; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250710D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-10 17:02 | NS 5pm | SF25_DMET013 |  | Dean Melville | 3 | 390 | 7.9 | 27.5 | 19.6 |  |  | 0 |  |  | 0 |  |  | 0 | 19.6 | 3430 | 4025 |  |  |  |  | 0 | 8.75 | 2.25 |  | 1 | [5 empty] | 12 |  | 1395 |  | 490.8 | 6300.8 | 6300.8 | 0.061897 | Cummulative Cost 38: 314931.3; EOM Cummulative Cost 39: 122825.78; Combined Cost Per Metre 40: 321.4694; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250710N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-11 05:02 | DS 5am | SF25_DMET013 |  | Carl Jonas | 4 | 520 | 27.5 | 45.5 | 18 |  |  | 0 |  |  | 0 |  |  | 0 | 18 | 3150 | 4140 | 1 | 1 | 1 | 13122 | 750 | 9 | 2.5 |  | 0.5 | [5 empty] | 12 |  | 1330 |  | 269.72 | 7009.72 | 6834.72 | 0.074183 | Cummulative Cost 38: 321941.02; EOM Cummulative Cost 39: 129835.5; Combined Cost Per Metre 40: 389.4289; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250711D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-11 17:02 | NS 5pm | SF25_DMET013 |  | Dean Melville | 3 | 390 | 45.5 | 55.7 | 10.2 |  |  | 0 |  |  | 0 |  |  | 0 | 10.2 | 1785 | 4370 |  |  |  |  | 0 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 |  | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 327918.95; EOM Cummulative Cost 39: 135813.43; Combined Cost Per Metre 40: 586.0716; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250711N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-12 05:02 | DS 5am | SF25_DMET013 |  | Carl Jonas | 4 | 520 | 55.7 | 66.5 | 10.8 |  |  | 0 |  |  | 0 |  |  | 0 | 10.8 | 1890 | 4485 | 1 | 1 | 1 | 13122 | 750 | 9.75 | 1.5 |  | 0.5 |  |  | 0.25 |  |  | 12 |  | 870 |  | 269.72 | 6894.72 | 6719.72 | 0.07542 | Cummulative Cost 38: 334813.67; EOM Cummulative Cost 39: 142708.15; Combined Cost Per Metre 40: 638.4; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250712D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-12 17:02 | NS 5pm | SF25_DMET013 |  | Dean Melville | 3 | 390 | 66.5 | 87.5 | 21 |  |  | 0 |  |  | 0 |  |  | 0 | 21 | 3675 | 4945 |  |  |  |  | 0 | 10.75 | 0.25 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 295 |  | 117.93 | 5747.93 | 5747.93 | 0.067851 | Cummulative Cost 38: 340561.6; EOM Cummulative Cost 39: 148456.08; Combined Cost Per Metre 40: 273.711; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250712N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-13 05:02 | DS 5am | SF25_DMET013 |  | Carl Jonas | 4 | 520 | 87.5 | 90.5 | 3 |  |  | 0 |  |  | 0 |  |  | 0 | 3 | 525 | 525 | 1 | 1 | 1 | 13122 | 750 | 1 | 10.5 | Rig move | 0.5 | [5 empty] | 12 |  | 5010 |  | 0 | 6805 | 6630 | 0.076414 | Cummulative Cost 38: 347366.6; EOM Cummulative Cost 39: 155261.08; Combined Cost Per Metre 40: 2268.3333; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250713D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-13 17:02 | NS 5pm | SF25_DMET004 |  | Dean Melville | 3 | 390 | 66.4 | 80.9 | 14.5 |  |  | 0 |  |  | 0 |  |  | 0 | 14.5 | 2537.5 | 3450 |  |  |  |  | 0 | 7.5 | 3.75 |  | 0.75 | [5 empty] | 12 |  | 1995 |  | 117.93 | 5952.93 | 5952.93 | 0.065514 | Cummulative Cost 38: 353319.53; EOM Cummulative Cost 39: 161214.01; Combined Cost Per Metre 40: 410.5469; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: finish setting up site, run poly to pad, run rods into hole to 60m ream barrel to 66.4m, start coring PQ3 gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250713N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-14 05:02 | DS 5am | SF25_DMET004 |  | Carl Jonas | 3 | 390 | 80.9 | 93.6 | 12.7 |  |  | 0 |  |  | 0 |  |  | 0 | 12.7 | 2222.5 | 4140 | 1 | 1 | 1 | 13122 | 750 | 9 | 2.5 |  | 0.5 | [5 empty] | 12 |  | 1330 |  | 220 | 6830 | 6655 | 0.057101 | Cummulative Cost 38: 360149.53; EOM Cummulative Cost 39: 168044.01; Combined Cost Per Metre 40: 537.7953; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment, continue drilling PQ3, pull out rods for bit change due to warn bit, run rods back in with rod grease, continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250714D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-14 17:02 | NS 5pm | SF25_DMET004 |  | Dean Melville | 3 | 390 | 93.6 | 117.6 | 24 |  |  | 0 |  |  | 0 |  |  | 0 | 24 | 4200 | 4945 |  |  |  |  | 0 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 |  | 236.49 | 6071.49 | 6071.49 | 0.064235 | Cummulative Cost 38: 366221.02; EOM Cummulative Cost 39: 174115.5; Combined Cost Per Metre 40: 252.9787; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250714N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-15 05:02 | DS 5am | SF25_DMET004 | SF25_DMET005 | Carl Jonas | 3 | 390 | 117.6 | 120.2 | 2.6 |  |  | 0 | 0 | 7.7 | 7.7 |  |  | 0 | 10.3 | 1802.5 | 1840 | 1 | 1 | 1 | 13122 | 750 | 4 | 7.5 |  | 0.5 | [5 empty] | 12 |  | 3630 |  | 277.4 | 6887.4 | 6712.4 | 0.056625 | Cummulative Cost 38: 373108.42; EOM Cummulative Cost 39: 181002.9; Combined Cost Per Metre 40: 668.6796; PLOD LINK 41: LINK; Comments 42: Continue drilling PQ3, pull out rods EOH in 3m lengths, mast down and move rig forward and line up for next hole DMET005, start the hole PQ3, rock roll hole for PVC colar; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250715D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-15 17:02 | NS 5pm | SF25_DMET005 |  | Dean Melville | 3 | 390 | 7.7 | 21.5 | 13.8 |  |  | 0 |  |  | 0 |  |  | 0 | 13.8 | 2415 | 2415 |  |  |  |  | 0 | 5.25 | 1 | crew change | 2.75 |  | cement PVC collar | 3 |  |  | 12 |  | 1450 |  | 3105.93 | 7360.93 | 7360.93 | 0.052982 | Cummulative Cost 38: 380469.35; EOM Cummulative Cost 39: 188363.83; Combined Cost Per Metre 40: 533.4007; PLOD LINK 41: LINK; Comments 42: Install PVC collar, cement in place, continue drilling HQ3 core, flush hole end of shift for crew change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250715N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-16 05:02 | DS 5am | SF25_DMET005 |  | Nicholas Nakovics | 3 | 390 | 21.5 | 21.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 13122 | 575 | 0 | 0.5 | crew change | 0.75 |  |  | 9 | 1.75 |  | 12 |  | 500 |  |  | 1465 | 1465 | 0.26621 | Cummulative Cost 38: 381934.35; EOM Cummulative Cost 39: 189828.83; PLOD LINK 41: LINK; Comments 42: Crew Change pick up stores, dump rubbish, pick up food order, changeover gas bottles, Run in 6m rods, Seat tube. Maintenance leaking fuel filter adjust wireline arcemedies; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250716D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-16 17:02 | NS 5pm | SF25_DMET005 |  | Carl Jonas | 3 | 390 | 21.5 | 54.5 | 33 |  |  | 0 |  |  | 0 |  |  | 0 | 33 | 5775 | 5775 |  |  |  |  | 0 | 9.75 | 1.75 |  | 0.5 | [5 empty] | 12 |  | 985 |  | 117.93 | 7267.93 | 7267.93 | 0.05366 | Cummulative Cost 38: 389202.28; EOM Cummulative Cost 39: 197096.76; Combined Cost Per Metre 40: 220.2403; PLOD LINK 41: LINK; Comments 42: Condition hole sumps are small so there's a lot of cuttings, continue drilling PQ3, survey @36M, continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250716N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-17 05:02 | DS 5am | SF25_DMET005 |  | Nicholas Nakovics | 3 | 390 | 54.5 | 75.2 | 20.7 |  |  | 0 |  |  | 0 |  |  | 0 | 20.7 | 3622.5 | 4600 |  | 1 | 1 | 13122 | 575 | 10 | 1.25 |  | 0.75 | [5 empty] | 12 |  | 845 |  |  | 6410 | 6410 | 0.060842 | Cummulative Cost 38: 395612.28; EOM Cummulative Cost 39: 203506.76; Combined Cost Per Metre 40: 309.6618; PLOD LINK 41: LINK; Comments 42: Drill PQ3, Survey @ 54m. Bit change due to ground conditions, drill PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250717D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-17 17:02 | NS 5pm | SF25_DMET005 |  | Carl Jonas | 3 | 390 | 75.2 | 86.7 | 11.5 |  |  | 0 |  |  | 0 |  |  | 0 | 11.5 | 2012.5 | 4140 |  |  |  |  | 0 | 9 | 2.5 |  | 0.5 | [5 empty] | 12 |  | 1330 |  | 337.93 | 6197.93 | 6197.93 | 0.062924 | Cummulative Cost 38: 401810.21; EOM Cummulative Cost 39: 209704.69; Combined Cost Per Metre 40: 538.9504; PLOD LINK 41: LINK; Comments 42: condition hole sumps are small so there's a lot of cuttings, continue drilling PQ3, pull out for bit inspection and to grease rods, survey @ 72m, continue drilling PQ3 hard broken ground, condition hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250717N; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-18 05:02 | DS 5am | SF25_DMET005 |  | Nicholas Nakovics | 3 | 390 | 86.7 | 108.5 | 21.8 |  |  | 0 |  |  | 0 |  |  | 0 | 21.8 | 3815 | 4600 |  | 1 | 1 | 13122 | 575 | 10 | 1.25 |  | 0.75 | [5 empty] | 12 |  | 845 |  | 117.93 | 6527.93 | 6527.93 | 0.059743 | Cummulative Cost 38: 408338.14; EOM Cummulative Cost 39: 216232.62; Combined Cost Per Metre 40: 299.4463; PLOD LINK 41: LINK; Comments 42: Drill PQ3 /Survey @90 / Bit Change worn bit / Drill PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250718D; Shift Shorthand 49: 2025-07
M 80/268 | Met | MET | 2025-07-18 17:02 | NS 5pm | SF25_DMET005 |  | Carl Jonas | 3 | 390 | 108.5 | 120.5 | 12 |  |  | 0 |  |  | 0 |  |  | 0 | 12 | 2100 | 2100 |  |  |  |  | 0 | 3.5 | 8 |  | 0.5 | [5 empty] | 12 |  | 3860 |  | 117.93 | 6467.93 | 6467.93 | 0.060297 | Cummulative Cost 38: 414806.07; EOM Cummulative Cost 39: 222700.55; Combined Cost Per Metre 40: 538.9942; PLOD LINK 41: LINK; Comments 42: Condition hole sumps are small so there's a lot of cuttings, continue drilling PQ3,survey @108m, survey @120m EOH, pull out all rods EOH, mast down and move rig, mast up and align for new hole, set up drill pad; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250718N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-19 05:02 | DS 5am | SF25_DDGT003 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 0 | 30.6 | 30.6 |  |  | 0 |  |  | 0 | 30.6 | 4131 | 4370 |  | 1 | 1 | 13122 | 575 | 9.5 | 1.25 |  | 1.25 | [5 empty] | 12 |  | 1025 |  |  | 6360 | 6360 | 0.061321 | Cummulative Cost 38: 421166.07; EOM Cummulative Cost 39: 229060.55; Combined Cost Per Metre 40: 207.8431; PLOD LINK 41: LINK; Comments 42: Site set up / Start of hole Drill Hq3 / Reaming PQ ream over to 3.1m case off / Continue drilling HQ3 / Survey @18m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250719D; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-19 17:02 | NS 5pm | SF25_DDGT003 |  | Carl Jonas | 3 | 390 |  |  | 0 | 30.6 | 60.6 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4140 |  |  |  |  | 0 | 9 | 2.5 |  | 0.5 | [5 empty] | 12 |  | 1330 |  | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 427144; EOM Cummulative Cost 39: 235038.48; Combined Cost Per Metre 40: 199.2643; PLOD LINK 41: LINK; Comments 42: condition hole sumps are small so there's a lot of cuttings, continue drilling HQ3,survey@36m, continue drilling, survey @54m, continue drilling HQ3, condition hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250719N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-20 05:02 | DS 5am | SF25_DDGT003 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 60.6 | 90.6 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4830 |  | 1 | 1 | 13122 | 575 | 10.5 | 0.25 |  | 0.75 |  |  | 0.5 |  |  | 12 |  | 385 |  |  | 6180 | 6180 | 0.063107 | Cummulative Cost 38: 433324; EOM Cummulative Cost 39: 241218.48; Combined Cost Per Metre 40: 206; PLOD LINK 41: LINK; Comments 42: Continue drilling HQ3 / Survey @72m / toolbox; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250720D; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-20 17:02 | NS 5pm | SF25_DDGT003 |  | Carl Jonas | 3 | 390 |  |  | 0 | 90.6 | 110 | 19.4 |  |  | 0 |  |  | 0 | 19.4 | 2619 | 2645 |  |  |  |  | 0 | 5.75 | 5.25 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 2595 |  | 117.93 | 5747.93 | 5747.93 | 0.067851 | Cummulative Cost 38: 439071.93; EOM Cummulative Cost 39: 246966.41; Combined Cost Per Metre 40: 296.2851; PLOD LINK 41: LINK; Comments 42: Continue Drilling HQ3 / Survey @108m, pull out all rods EOH, rig down, pack up site, rig move to next pad, rig up, survey @0m, set up site; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250720N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-21 05:02 | DS 5am | SF25_DDGT004 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 0 | 30.6 | 30.6 |  |  | 0 |  |  | 0 | 30.6 | 4131 | 4830 |  | 1 | 1 | 13122 | 575 | 10.5 | 0.75 |  | 0.75 | [5 empty] | 12 |  | 615 |  |  | 6410 | 6410 | 0.060842 | Cummulative Cost 38: 445481.93; EOM Cummulative Cost 39: 253376.41; Combined Cost Per Metre 40: 209.4771; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Ream in PQ casing / Seat casing / Drill HQ3 / Survey @18m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250721D; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-21 17:02 | NS 5pm | SF25_DDGT004 |  | Carl Jonas | 3 | 390 |  |  | 0 | 30.6 | 60.6 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4600 |  |  |  |  | 0 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 |  | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 451459.86; EOM Cummulative Cost 39: 259354.34; Combined Cost Per Metre 40: 199.2643; PLOD LINK 41: LINK; Comments 42: Condition hole/ continue Drilling HQ3 / survey @36m/ continue drilling HQ3/ survey @54m/ continue drilling HQ3/ condition hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250721N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-22 05:02 | DS 5am | SF25_DDGT004 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 60.6 | 90.6 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 5060 |  | 1 | 1 | 13122 | 575 | 11 | 0.25 |  | 0.75 | [5 empty] | 12 |  | 385 |  |  | 6410 | 6410 | 0.060842 | Cummulative Cost 38: 457869.86; EOM Cummulative Cost 39: 265764.34; Combined Cost Per Metre 40: 213.6667; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey @72m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250722D; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-22 17:02 | NS 5pm | SF25_DDGT004 |  | Carl Jonas | 3 | 390 |  |  | 0 | 90.6 | 110 | 19.4 |  |  | 0 |  |  | 0 | 19.4 | 2619 | 3220 |  |  |  |  | 0 | 7 | 4.5 |  | 0.5 | [5 empty] | 12 |  | 2250 |  | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 463847.79; EOM Cummulative Cost 39: 271742.27; Combined Cost Per Metre 40: 308.1407; PLOD LINK 41: LINK; Comments 42: continue Drilling HQ3 / survey @90m / continue drilling HQ3/ survey @108m EOH, pull out rods and casing/ rig down/ pack up drill site/ move to next pad and start setting up.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250722N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-23 05:02 | DS 5am | SF25_DDGT007 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 0 | 11.9 | 11.9 |  |  | 0 |  |  | 0 | 11.9 | 1606.5 | 2990 |  | 1 | 1 | 13122 | 575 | 6.5 | 4.75 |  | 0.75 | [5 empty] | 12 |  | 2455 |  |  | 6410 | 6410 | 0.060842 | Cummulative Cost 38: 470257.79; EOM Cummulative Cost 39: 278152.27; Combined Cost Per Metre 40: 538.6555; PLOD LINK 41: LINK; Comments 42: Line up rig / Surface Shot / Site set-up / Site inspection / Drill Hq3 / PQ reaming to 6.1m / pullout for core in barrel/; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250723D; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-23 17:02 | NS 5pm | SF25_DDGT007 |  | Carl Jonas | 3 | 390 |  |  | 0 | 11.9 | 42.4 | 30.5 |  |  | 0 |  |  | 0 | 30.5 | 4117.5 | 4370 |  |  |  |  | 0 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 |  | 138.7 | 5998.7 | 5998.7 | 0.065014 | Cummulative Cost 38: 476256.49; EOM Cummulative Cost 39: 284150.97; Combined Cost Per Metre 40: 196.6787; PLOD LINK 41: LINK; Comments 42: run in barrel ream to bottom/ continue Drilling HQ3 / pull out rods for bit change/ run rods in Ream to bottom/ survey @18m/ continue drilling HQ3/ survey @36m/ continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250723N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-24 05:02 | DS 5am | SF25_DDGT007 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 42.4 | 72.4 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 5060 |  | 1 | 1 | 13122 | 575 | 11 | 0.25 |  | 0.75 | [5 empty] | 12 |  | 385 |  |  | 6410 | 6410 | 0.060842 | Cummulative Cost 38: 482666.49; EOM Cummulative Cost 39: 290560.97; Combined Cost Per Metre 40: 213.6667; PLOD LINK 41: LINK; Comments 42: Drill Hq3 / Survey; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250724D; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-24 17:02 | NS 5pm | SF25_DDGT007 |  | Carl Jonas | 3 | 390 |  |  | 0 | 72.4 | 102.4 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4600 |  |  |  |  | 0 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 |  | 138.7 | 5998.7 | 5998.7 | 0.065014 | Cummulative Cost 38: 488665.19; EOM Cummulative Cost 39: 296559.67; Combined Cost Per Metre 40: 199.9567; PLOD LINK 41: LINK; Comments 42: condition hole due to sumps being full of cuttings /continue Drilling HQ3 / survey@72m/ continue drilling HQ3/ survey@90m/ continue drilling HQ3/ condition hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250724N; Shift Shorthand 49: 2025-07
M 80/268 | Geotech | GT | 2025-07-25 05:02 | DS 5am | SF25_DDGT007 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 102.4 | 120 | 17.6 |  |  | 0 |  |  | 0 | 17.6 | 2376 | 2376 |  | 1 | 1 | 13122 | 575 | 4 | 7.25 |  | 0.75 | [5 empty] | 12 |  | 3605 |  |  | 6946 | 6946 | 0.056147 | Cummulative Cost 38: 495611.19; EOM Cummulative Cost 39: 303505.67; Combined Cost Per Metre 40: 394.6591; PLOD LINK 41: LINK; Comments 42: Drill Hq3 / Survey@114 / E.O.H / pull out rods and casing/ rig down/ pack up drill site/ Move between holes / rig aligned / Site set-up / surface shot 0m /; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250725D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-25 17:02 | NS 5pm | SF25_DDGT008 |  | Carl Jonas | 3 | 390 |  |  | 0 | 0 | 18.5 | 18.5 |  |  | 0 |  |  | 0 | 18.5 | 2497.5 | 4370 |  |  |  |  | 0 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 |  | 138.7 | 5998.7 | 5998.7 | 0.065014 | Cummulative Cost 38: 501609.89; EOM Cummulative Cost 39: 309504.37; Combined Cost Per Metre 40: 324.2541; PLOD LINK 41: LINK; Comments 42: Drill HQ3, ream 3m PQ casing, continue drilling HQ3, pull out for bit change, run rods in, continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250725N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-26 05:02 | DS 5am | SF25_DDGT008 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 18.5 | 48.5 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4945 |  | 1 | 1 | 13122 | 575 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 |  |  | 6410 | 6410 | 0.060842 | Cummulative Cost 38: 508019.89; EOM Cummulative Cost 39: 315914.37; Combined Cost Per Metre 40: 213.6667; PLOD LINK 41: LINK; Comments 42: Drill Hq3 / Survey @18, 36; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250726D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-26 17:02 | NS 5pm | SF25_DDGT008 |  | Carl Jonas | 3 | 390 |  |  | 0 | 48.5 | 78.5 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4830 |  |  |  |  | 0 | 10.5 | 1 |  | 0.5 | [5 empty] | 12 |  | 640 |  |  | 5860 | 5860 | 0.066553 | Cummulative Cost 38: 513879.89; EOM Cummulative Cost 39: 321774.37; Combined Cost Per Metre 40: 195.3333; PLOD LINK 41: LINK; Comments 42: condition hole/ continue drilling HQ3/ survey @54m/ continue drilling HQ3/ survey @72m/ continue drilling HQ3/ condition hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250726N; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-27 05:02 | DS 5am | SF25_DDGT008 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 78.5 | 108.5 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4830 |  | 1 | 1 | 13122 | 575 | 10.5 | 0.25 |  | 0.75 |  |  | 0.5 |  |  | 12 |  | 385 |  |  | 6180 | 6180 | 0.063107 | Cummulative Cost 38: 520059.89; EOM Cummulative Cost 39: 327954.37; Combined Cost Per Metre 40: 206; PLOD LINK 41: LINK; Comments 42: Drill Hq3 / Survey @90m / Toolbox at EOS; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250727D; Shift Shorthand 49: 2025-07
M 80/269 | Geotech | GT | 2025-07-27 17:02 | NS 5pm | SF25_DDGT008 |  | Carl Jonas | 3 | 390 |  |  | 0 | 108.5 | 130 | 21.5 |  |  | 0 |  |  | 0 | 21.5 | 2902.5 | 2902.5 |  |  |  |  | 0 | 6 | 5 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 2480 |  |  | 5772.5 | 5772.5 | 0.067562 | Cummulative Cost 38: 525832.39; EOM Cummulative Cost 39: 333726.87; Combined Cost Per Metre 40: 268.4884; PLOD LINK 41: LINK; Comments 42: Toolbox at SOS, continue drilling HQ3 / survey @108m continue drilling HQ3/ survey @126m/ pull rods out EOH/ pull casing/ rig down pack up site/ move all equipment and rig to next pad.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250727N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-28 05:02 | DS 5am | SF25_DMET014 |  | Nicholas Nakovics | 3 | 390 | 0 | 18.2 | 18.2 |  |  | 0 |  |  | 0 |  |  | 0 | 18.2 | 3185 | 3185 |  | 1 | 1 | 13122 | 575 | 6.25 | 4.75 |  | 1 | [5 empty] | 12 |  | 2545 | 786.12 | 396.12 | 7091.12 | 7091.12 | 0.054998 | Cummulative Cost 38: 532923.51; EOM Cummulative Cost 39: 340817.99; Combined Cost Per Metre 40: 389.622; PLOD LINK 41: LINK; Comments 42: Pré-shift meeting, Pre-start equipment / Rigging up / Surface shot / Site set-up / Drill PQ3 / Pullout / Open hole with rock roller / PVC collar hole / Run in 3m PQ barrel / Drill PQ; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250728D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-28 17:02 | NS 5pm | SF25_DMET014 |  | Carl Jonas | 3 | 390 | 18.2 | 39.2 | 21 |  |  | 0 |  |  | 0 |  |  | 0 | 21 | 3675 | 4370 |  |  |  |  | 0 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 747.5 | 357.5 | 6217.5 | 6217.5 | 0.062726 | Cummulative Cost 38: 539141.01; EOM Cummulative Cost 39: 347035.49; Combined Cost Per Metre 40: 296.0714; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / continue drilling PQ3 / survey @18m continue drilling PQ3/pulled rods for bit change ran rods in with rod grease/lost water @31m Bomed hole, successful water return lost water again shortly after/ continue drilling PQ3/ survey @36m/ bombed hole again successful water return/ water delay; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250728N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-29 05:02 | DS 5am | SF25_DMET014 |  | Nicholas Nakovics | 3 | 390 | 39.2 | 50.3 | 11.1 |  |  | 0 |  |  | 0 |  |  | 0 | 11.1 | 1942.5 | 4255 |  | 1 | 1 | 13122 | 575 | 9.25 | 2 |  | 0.75 | [5 empty] | 12 |  | 1190 | 1161.2 | 771.2 | 7181.2 | 7181.2 | 0.054308 | Cummulative Cost 38: 546322.21; EOM Cummulative Cost 39: 354216.69; Combined Cost Per Metre 40: 646.955; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250729D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-29 17:02 | NS 5pm | SF25_DMET014 |  | Carl Jonas | 3 | 390 | 50.3 | 55.8 | 5.5 |  |  | 0 |  |  | 0 |  |  | 0 | 5.5 | 962.5 | 2300 |  |  |  |  | 0 | 5 | 2.5 | crew change | 0.5 |  |  | 4 |  |  | 12 |  | 1330 | 507.93 | 117.93 | 4137.93 | 4137.93 | 0.09425 | Cummulative Cost 38: 550460.14; EOM Cummulative Cost 39: 358354.62; Combined Cost Per Metre 40: 752.3509; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250729N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-30 05:02 | DS 5am | SF25_DMET014 |  | Dean Melville | 3 | 390 | 55.8 | 55.8 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 13122 | 575 |  | 0.25 |  | 0.75 |  |  | 11 |  |  | 12 |  | 385 | 390 |  | 1350 | 1350 | 0.28889 | Cummulative Cost 38: 551810.14; EOM Cummulative Cost 39: 359704.62; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250730D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-30 17:02 | NS 5pm | SF25_DMET014 |  | Nicholas Nakovics | 3 | 390 | 55.8 | 78.2 | 22.4 |  |  | 0 |  |  | 0 |  |  | 0 | 22.4 | 3920 | 4945 |  |  |  |  | 0 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 | 390 |  | 5835 | 5835 | 0.066838 | Cummulative Cost 38: 557645.14; EOM Cummulative Cost 39: 365539.62; Combined Cost Per Metre 40: 260.4911; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250730N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-31 05:02 | DS 5am | SF25_DMET014 | SF25_DMET015 | Dean Melville | 3 | 390 | 78.2 | 85.5 | 7.3 |  |  | 0 | 0 | 6.3 | 6.3 |  |  | 0 | 13.6 | 2380 | 2530 |  | 1 | 1 | 13122 | 575 | 5.5 | 4.75 |  | 1.75 | [5 empty] | 12 |  | 2815 | 754.57 | 364.57 | 6674.57 | 6674.57 | 0.058431 | Cummulative Cost 38: 564319.71; EOM Cummulative Cost 39: 372214.19; Combined Cost Per Metre 40: 490.7772; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 31; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250731D; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-07-31 17:02 | NS 5pm | SF25_DMET015 |  | Nicholas Nakovics | 3 | 390 | 6.3 | 36.6 | 30.3 |  |  | 0 |  |  | 0 |  |  | 0 | 30.3 | 5302.5 | 5302.5 |  |  |  |  | 0 | 10.25 | 1 |  | 0.75 | [5 empty] | 12 |  | 730 | 21975 | 21585 | 28007.5 | 28007.5 | 0.013925 | Cummulative Cost 38: 592327.21; EOM Cummulative Cost 39: 400221.69; Combined Cost Per Metre 40: 924.3399; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 07; Day 46: 31; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250731N; Shift Shorthand 49: 2025-07
M 80/269 | Met | MET | 2025-08-01 05:02 | DS 5am | SF25_DMET015 |  | Dean Melville | 3 | 390 | 36.6 | 66.6 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 | 1 | 1 | 1 | 13122 | 750 | 9.25 | 2 |  | 0.75 | [5 empty] | 12 |  | 1190 | 665 | 275 | 7855 | 7855 | 0.04965 | Cummulative Cost 38: 600182.21; EOM Cummulative Cost 39: 7855; Combined Cost Per Metre 40: 261.8333; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: try to regain water return, continue drilling PQ3 core, gyro surveys, pull out for bit change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508001D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-01 17:02 | NS 5pm | SF25_DMET015 |  | Nicholas Nakovics | 3 | 390 | 66.6 | 85 | 18.4 |  |  | 0 |  |  | 0 |  |  | 0 | 18.4 | 3220 | 4140 |  |  |  |  | 0 | 9 | 2.25 |  | 0.75 | [5 empty] | 12 |  | 1305 | 610 | 220 | 6055 | 6055 | 0.06441 | Cummulative Cost 38: 606237.21; EOM Cummulative Cost 39: 13910; Combined Cost Per Metre 40: 329.0761; PLOD LINK 41: LINK; Comments 42: Pré-shift meeting, Pre-start equipment / Drill PQ3 / Bit change / Survey @72,81 / E.O.H / pullout / Rigging down; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508001N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-02 05:02 | DS 5am | SF25_DMET016 |  | Dean Melville | 3 | 390 | 0 | 9.6 | 9.6 |  |  | 0 |  |  | 0 |  |  | 0 | 9.6 | 1680 | 3220 | 1 | 1 | 1 | 13122 | 750 | 7 | 4.25 |  | 0.75 | [5 empty] | 12 |  | 2225 | 390 | 0 | 6585 | 6585 | 0.059226 | Cummulative Cost 38: 612822.21; EOM Cummulative Cost 39: 20495; Combined Cost Per Metre 40: 685.9375; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508002D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-02 17:02 | NS 5pm | SF25_DMET016 |  | Nicholas Nakovics | 3 | 390 | 9.6 | 24.6 | 15 |  |  | 0 |  |  | 0 |  |  | 0 | 15 | 2625 | 3795 |  |  |  |  | 0 | 8.25 | 3 |  | 0.75 | [5 empty] | 12 |  | 1650 | 610 | 220 | 6055 | 6055 | 0.06441 | Cummulative Cost 38: 618877.21; EOM Cummulative Cost 39: 26550; Combined Cost Per Metre 40: 403.6667; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508002N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-03 05:02 | DS 5am | SF25_DMET016 |  | Dean Melville | 3 | 390 | 24.6 | 48.6 | 24 |  |  | 0 |  |  | 0 |  |  | 0 | 24 | 4200 | 4200 | 1 | 1 | 1 | 13122 | 750 | 9 | 1.75 |  | 0.75 |  |  | 0.5 |  |  | 12 |  | 1075 | 727.93 | 337.93 | 6752.93 | 6752.93 | 0.057753 | Cummulative Cost 38: 625630.14; EOM Cummulative Cost 39: 33302.93; Combined Cost Per Metre 40: 281.3721; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508003D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-03 17:02 | NS 5pm | SF25_DMET016 |  | Nicholas Nakovics | 3 | 390 | 48.6 | 74.3 | 25.7 |  |  | 0 |  |  | 0 |  |  | 0 | 25.7 | 4497.5 | 4600 |  |  |  |  | 0 | 10 | 0.75 |  | 0.75 |  |  | 0.5 |  |  | 12 |  | 615 | 390 | 0 | 5605 | 5605 | 0.069581 | Cummulative Cost 38: 631235.14; EOM Cummulative Cost 39: 38907.93; Combined Cost Per Metre 40: 218.0934; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508003N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-04 05:02 | DS 5am | SF25_DMET016 |  | Dean Melville | 3 | 390 | 74.3 | 86.8 | 12.5 |  |  | 0 |  |  | 0 |  |  | 0 | 12.5 | 2187.5 | 3450 | 1 | 1 | 1 | 13122 | 750 | 7.5 | 2.75 | Poor ground conditions- a lot of hole conditioning work | 1.75 | [5 empty] | 12 |  | 1895 | 507.93 | 117.93 | 6602.93 | 6602.93 | 0.059065 | Cummulative Cost 38: 637838.07; EOM Cummulative Cost 39: 45510.86; Combined Cost Per Metre 40: 528.2344; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508004D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-04 17:02 | NS 5pm | SF25_DMET016 |  | Nicholas Nakovics | 3 | 390 | 86.8 | 104.1 | 17.3 |  |  | 0 |  |  | 0 |  |  | 0 | 17.3 | 3027.5 | 4485 |  |  |  |  | 0 | 9.75 | 1.5 |  | 0.75 | [5 empty] | 12 |  | 960 | 610 | 220 | 6055 | 6055 | 0.06441 | Cummulative Cost 38: 643893.07; EOM Cummulative Cost 39: 51565.86; Combined Cost Per Metre 40: 350; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508004N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-05 05:02 | DS 5am | SF25_DMET016 | SF25_DDGT009 | Dean Melville | 3 | 390 | 104.1 | 110.2 | 6.1 | 0 | 3.9 | 3.9 |  |  | 0 |  |  | 0 | 10 | 1594 | 2415 | 1 | 1 | 1 | 13122 | 750 | 5.25 | 6 |  | 0.75 | [5 empty] | 12 |  | 3030 | 528.7 | 138.7 | 6723.7 | 6723.7 | 0.058004 | Cummulative Cost 38: 650616.77; EOM Cummulative Cost 39: 58289.56; Combined Cost Per Metre 40: 672.37; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508005D; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-05 17:02 | NS 5pm | SF25_DDGT009 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 3.9 | 18.2 | 14.3 |  |  | 0 |  |  | 0 | 14.3 | 1930.5 | 4140 |  |  |  |  | 0 | 9 | 2.25 |  | 0.75 | [5 empty] | 12 |  | 1305 | 390 | 0 | 5835 | 5835 | 0.066838 | Cummulative Cost 38: 656451.77; EOM Cummulative Cost 39: 64124.56; Combined Cost Per Metre 40: 408.042; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508005N; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-06 05:02 | DS 5am | SF25_DDGT009 |  | Dean Melville | 3 | 390 |  |  | 0 | 18.2 | 48.9 | 30.7 |  |  | 0 |  |  | 0 | 30.7 | 4144.5 | 4715 | 1 | 1 | 1 | 13122 | 750 | 10.25 | 1 |  | 0.75 | [5 empty] | 12 |  | 730 | 528.7 | 138.7 | 6723.7 | 6723.7 | 0.058004 | Cummulative Cost 38: 663175.47; EOM Cummulative Cost 39: 70848.26; Combined Cost Per Metre 40: 219.013; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: continue drilling HQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508006D; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-06 17:02 | NS 5pm | SF25_DDGT009 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 48.9 | 81.9 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 4945 |  |  |  |  | 0 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 | 390 | 0 | 5835 | 5835 | 0.066838 | Cummulative Cost 38: 669010.47; EOM Cummulative Cost 39: 76683.26; Combined Cost Per Metre 40: 176.8182; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508006N; Shift Shorthand 49: 2025-08
M 80/269 | Geotech | GT | 2025-08-07 05:02 | DS 5am | SF25_DDGT009 |  | Dean Melville | 3 | 390 |  |  | 0 | 81.9 | 99.9 | 18 |  |  | 0 |  |  | 0 | 18 | 2430 | 2430 | 1 | 1 | 1 | 13122 | 750 | 5 | 6.25 |  | 0.75 | [5 empty] | 12 |  | 3145 | 528.7 | 138.7 | 6853.7 | 6853.7 | 0.056904 | Cummulative Cost 38: 675864.17; EOM Cummulative Cost 39: 83536.96; Combined Cost Per Metre 40: 380.7611; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508007D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-07 17:02 | NS 5pm | SF25_DDRD004 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 0 | 10.7 | 10.7 |  |  | 0 |  |  | 0 | 10.7 | 1444.5 | 1444.5 |  |  |  |  | 0 | 3 | 8.25 |  | 0.75 | [5 empty] | 12 |  | 4065 | 390 | 0 | 5899.5 | 5899.5 | 0.066107 | Cummulative Cost 38: 681763.67; EOM Cummulative Cost 39: 89436.46; Combined Cost Per Metre 40: 551.3551; PLOD LINK 41: LINK; Comments 42: Pré-shift meeting, Pre-start equipment / Tramming / Site set-up / mast shot / establish water supply / Drill HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508007N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-08 05:02 | DS 5am | SF25_DDRD004 |  | Dean Melville | 3 | 390 |  |  | 0 | 10.7 | 45.5 | 34.8 |  |  | 0 |  |  | 0 | 34.8 | 4698 | 4698 | 1 | 1 | 1 | 13122 | 750 | 8.25 | 3 |  | 0.75 | [5 empty] | 12 |  | 1650 | 664.75 | 274.75 | 7762.75 | 7762.75 | 0.05024 | Cummulative Cost 38: 689526.42; EOM Cummulative Cost 39: 97199.21; Combined Cost Per Metre 40: 223.0675; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508008D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-08 17:02 | NS 5pm | SF25_DDRD004 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 45.5 | 75.5 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4945 |  |  |  |  | 0 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 | 390 | 0 | 5835 | 5835 | 0.066838 | Cummulative Cost 38: 695361.42; EOM Cummulative Cost 39: 103034.21; Combined Cost Per Metre 40: 194.5; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508008N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-09 05:02 | DS 5am | SF25_DDRD004 | SF25_DDRD005 | Dean Melville | 3 | 390 |  |  | 0 | 75.5 | 90.5 | 15 |  |  | 0 | 0 | 0 | 0 | 15 | 2025 | 2025 | 1 | 1 | 1 | 13122 | 750 | 4.25 | 7 |  | 0.75 | [5 empty] | 12 |  | 3490 | 528.7 | 138.7 | 6793.7 | 6793.7 | 0.057406 | Cummulative Cost 38: 702155.12; EOM Cummulative Cost 39: 109827.91; Combined Cost Per Metre 40: 452.9133; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: continue drilling HQ3 core to EOH, pull out, pack up, move to next pad, set up on next pad.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508009D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-09 17:02 | NS 5pm | SF25_DDRD005 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 0 | 30.7 | 30.7 |  |  | 0 |  |  | 0 | 30.7 | 4144.5 | 4144.5 |  |  |  |  | 0 | 9 | 2.25 |  | 0.75 | [5 empty] | 12 |  | 1305 | 390 | 0 | 5839.5 | 5839.5 | 0.066787 | Cummulative Cost 38: 707994.62; EOM Cummulative Cost 39: 115667.41; Combined Cost Per Metre 40: 190.2117; PLOD LINK 41: LINK; Comments 42: Pré-shift meeting, Pre-start equipment / Drill HQ3 / Ream PQ casing / Barrel change to 3m gear / Drill HQ3 / Survey @18; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-2508009N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-10 05:02 | DS 5am | SF25_DDRD005 |  | Dean Melville | 3 | 390 |  |  | 0 | 30.7 | 60.7 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4485 | 1 | 1 | 1 | 13122 | 750 | 9.75 | 1 |  | 0.75 |  |  | 0.5 |  | Toolbox | 12 |  | 730 | 528.7 | 138.7 | 6493.7 | 6493.7 | 0.060058 | Cummulative Cost 38: 714488.32; EOM Cummulative Cost 39: 122161.11; Combined Cost Per Metre 40: 216.4567; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: continue drilling HQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250810D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-10 17:02 | NS 5pm | SF25_DDRD005 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 60.7 | 90 | 29.3 |  |  | 0 |  |  | 0 | 29.3 | 3955.5 | 4255 |  |  |  |  | 0 | 9.25 | 1.5 |  | 0.75 |  |  | 0.5 |  | Toolbox | 12 |  | 960 | 390 | 0 | 5605 | 5605 | 0.069581 | Cummulative Cost 38: 720093.32; EOM Cummulative Cost 39: 127766.11; Combined Cost Per Metre 40: 191.2969; PLOD LINK 41: LINK; Comments 42: Toolbox / Pré-shift meeting / Pre-start equipment / Drill HQ3 to EOH / Survey @72,87 / Pull rods and casing; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250810N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-11 05:02 | DS 5am | SF25_DDRD006 |  | Dean Melville | 3 | 390 |  |  | 0 | 0 | 15.9 | 15.9 |  |  | 0 |  |  | 0 | 15.9 | 2146.5 | 2146.5 | 1 | 1 | 1 | 13122 | 750 | 4.5 | 6.75 |  | 0.75 | [5 empty] | 12 |  | 3375 | 390 | 0 | 6661.5 | 6661.5 | 0.058545 | Cummulative Cost 38: 726754.82; EOM Cummulative Cost 39: 134427.61; Combined Cost Per Metre 40: 418.9623; PLOD LINK 41: LINK; Comments 42: move rig onto next pad, set up, mast shot, start coring HQ3 from surface, ream HWT casing.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250811D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-11 17:02 | NS 5pm | SF25_DDRD006 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 15.9 | 45.9 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4945 |  |  |  |  | 0 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 | 390 | 0 | 5835 | 5835 | 0.066838 | Cummulative Cost 38: 732589.82; EOM Cummulative Cost 39: 140262.61; Combined Cost Per Metre 40: 194.5; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey @18,36; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250811N; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-12 05:02 | DS 5am | SF25_DDRD006 |  | Dean Melville | 3 | 390 |  |  | 0 | 45.9 | 75.9 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4050 | 1 | 1 | 1 | 13122 | 750 | 7.5 | 0.75 | running poly pipe to next pad | 3.75 |  | running poly pipe to next pad |  |  |  | 12 |  | 1695 | 390 | 0 | 6885 | 6885 | 0.056645 | Cummulative Cost 38: 739474.82; EOM Cummulative Cost 39: 147147.61; Combined Cost Per Metre 40: 229.5; PLOD LINK 41: LINK; Comments 42: ontinue drilling HQ3 core, gyro surveys. set up pipeline to next pad; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250812D; Shift Shorthand 49: 2025-08
M 80/268 | A Vein DD | DDRD | 2025-08-12 17:02 | NS 5pm | SF25_DDRD006 |  | Nicholas Nakovics | 3 | 390 |  |  | 0 | 75.9 | 90 | 14.1 |  |  | 0 |  |  | 0 | 14.1 | 1903.5 | 3220 |  |  |  |  | 0 | 7 | 4.25 |  | 0.75 | [5 empty] | 12 |  | 2225 | 390 | 0 | 5835 | 5835 | 0.066838 | Cummulative Cost 38: 745309.82; EOM Cummulative Cost 39: 152982.61; Combined Cost Per Metre 40: 413.8298; PLOD LINK 41: LINK; Comments 42: Drill HQ3 / Survey 72,87 / Pullout E.O.H / Rigging down / Tramming; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250812N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-13 05:02 | DS 5am | SF25_DMET011 |  | Carl Jonas | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 3.5 | crew change | 0.5 |  |  | 8 |  | crew change | 12 |  | 1790 | 390 | 0 | 2180 | 2180 | 0.1789 | Cummulative Cost 38: 747489.82; EOM Cummulative Cost 39: 155162.61; PLOD LINK 41: LINK; Comments 42: Crew change pick up food, rubbish run/ drive to site/ Pre-shift meeting, Pre-start all equipment / go with client to see new pad/ pack up drill site/ start tracking rig to next pad; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250813D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-13 17:02 | NS 5pm | SF25_DMET011 |  | Dean Melville | 3 | 390 | 0 | 7.3 | 7.3 |  |  | 0 |  |  | 0 |  |  | 0 | 7.3 | 1277.5 | 3220 | 1 | 1 | 1 | 13122 | 750 | 7 | 4.25 |  | 0.75 | [5 empty] | 12 |  | 2225 | 528.7 | 138.7 | 6723.7 | 6723.7 | 0.058004 | Cummulative Cost 38: 754213.52; EOM Cummulative Cost 39: 161886.31; Combined Cost Per Metre 40: 921.0548; PLOD LINK 41: LINK; Comments 42: move rig and gear to next pad, set up, line sumps start filling, start coring PQ3 from surface.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250813N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-14 05:02 | DS 5am | SF25_DMET011 |  | Carl Jonas | 3 | 390 | 7.3 | 24.6 | 17.3 |  |  | 0 |  |  | 0 |  |  | 0 | 17.3 | 3027.5 | 4025 |  | 1 | 1 | 13122 | 575 | 8.75 | 2.75 |  | 0.5 | [5 empty] | 12 |  | 1445 | 507.93 | 117.93 | 6552.93 | 6552.93 | 0.059515 | Cummulative Cost 38: 760766.45; EOM Cummulative Cost 39: 168439.24; Combined Cost Per Metre 40: 378.7821; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3/ Ream 9m PWT casing/ continue drilling PQ3/ survey @18m/ continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250814D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-14 17:02 | NS 5pm | SF25_DMET011 |  | Dean Melville | 3 | 390 | 24.6 | 51.6 | 27 |  |  | 0 |  |  | 0 |  |  | 0 | 27 | 4725 | 4725 | 1 |  |  |  | 175 | 10 | 1.25 |  | 0.75 | [5 empty] | 12 |  | 845 | 610 | 220 | 6355 | 6355 | 0.061369 | Cummulative Cost 38: 767121.45; EOM Cummulative Cost 39: 174794.24; Combined Cost Per Metre 40: 235.3704; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3, gyro surveys; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250814N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-15 05:02 | DS 5am | SF25_DMET011 |  | Carl Jonas | 3 | 390 | 51.6 | 57.4 | 5.8 |  |  | 0 |  |  | 0 |  |  | 0 | 5.8 | 1015 | 1840 |  | 1 | 1 | 13122 | 575 | 4 | 4 | fixing lister pump, re-establishing water supply | 0.5 |  |  |  | 3.5 | fixing lister pump | 12 |  | 2020 | 390 | 0 | 4825 | 4825 | 0.080829 | Cummulative Cost 38: 771946.45; EOM Cummulative Cost 39: 179619.24; Combined Cost Per Metre 40: 831.8966; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3/ very hard ground/ lister pump broke down/ standby water delay/continue drilling PQ3/ pull out for bit change warn bit/ continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250815D; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-15 17:02 | NS 5pm | SF25_DMET011 |  | Dean Melville | 3 | 390 | 57.4 | 81.6 | 24.2 |  |  | 0 |  |  | 0 |  |  | 0 | 24.2 | 4235 | 4485 | 1 |  |  |  | 175 | 9.75 | 1.5 |  | 0.75 | [5 empty] | 12 |  | 960 | 1949.56 | 1559.56 | 7569.56 | 7569.56 | 0.051522 | Cummulative Cost 38: 779516.01; EOM Cummulative Cost 39: 187188.8; Combined Cost Per Metre 40: 312.7917; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core, gyro surveys, pull out for bit change. Freight arrived on site.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250815N; Shift Shorthand 49: 2025-08
M 80/269 | Met | MET | 2025-08-16 05:02 | DS 5am | SF25_DMET011 |  | Carl Jonas | 3 | 390 | 81.6 | 100 | 18.4 |  |  | 0 |  |  | 0 |  |  | 0 | 18.4 | 3220 | 3220 |  | 1 | 1 | 13122 | 575 | 7 | 4.5 |  | 0.5 | [5 empty] | 12 |  | 2250 | 390 | 0 | 6435 | 6435 | 0.060606 | Cummulative Cost 38: 785951.01; EOM Cummulative Cost 39: 193623.8; Combined Cost Per Metre 40: 349.7283; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3/ water delay/ continue drilling PQ3/ survey @90m/ continue drilling PQ3/ survey @97m EOH/ pack up site/ pull out PQ rods and PWT casing; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250816D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-16 17:02 | NS 5pm | SF25_DDRD015 |  | Dean Melville | 3 | 390 |  |  | 0 | 0 | 12.4 | 12.4 |  |  | 0 |  |  | 0 | 12.4 | 1674 | 2530 | 1 |  |  |  | 175 | 5.5 | 5.75 |  | 0.75 | [5 empty] | 12 |  | 2915 | 610 | 220 | 6230 | 6230 | 0.0626 | Cummulative Cost 38: 792181.01; EOM Cummulative Cost 39: 199853.8; Combined Cost Per Metre 40: 502.4194; PLOD LINK 41: LINK; Comments 42: line sumps, run poly to pad, move rig onto next pad, mast shot survey, start coring HQ3 from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250816N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-17 05:02 | DS 5am | SF25_DDRD015 |  | Carl Jonas | 3 | 390 |  |  | 0 | 12.4 | 42.8 | 30.4 |  |  | 0 |  |  | 0 | 30.4 | 4104 | 4370 |  | 1 | 1 | 13122 | 575 | 9.5 | 1.5 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 870 | 390 | 0 | 6205 | 6205 | 0.062853 | Cummulative Cost 38: 798386.01; EOM Cummulative Cost 39: 206058.8; Combined Cost Per Metre 40: 204.1118; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3/ barrel change to 3M barrel and ori gear/ survey @18m/ continue drilling HQ3/ survey @36m/ continue drilling HQ3/ Toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250817D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-17 17:02 | NS 5pm | SF25_DDRD015 |  | Dean Melville | 3 | 390 |  |  | 0 | 42.8 | 78.8 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4860 | 1 |  |  |  | 175 | 9.75 | 1 |  | 0.75 |  |  | 0.5 |  | Toolbox | 12 |  | 730 | 508.56 | 118.56 | 6273.56 | 6273.56 | 0.062166 | Cummulative Cost 38: 804659.57; EOM Cummulative Cost 39: 212332.36; Combined Cost Per Metre 40: 174.2656; PLOD LINK 41: LINK; Comments 42: Continue drilling HQ3 core, gyro surveys; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250817N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-18 05:02 | DS 5am | SF25_DDRD015 |  | Carl Jonas | 3 | 390 |  |  | 0 | 78.8 | 108.8 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4050 |  | 1 | 1 | 13122 | 575 | 8.5 | 3 |  | 0.5 | [5 empty] | 12 |  | 1560 | 390 | 0 | 6575 | 6575 | 0.059316 | Cummulative Cost 38: 811234.57; EOM Cummulative Cost 39: 218907.36; Combined Cost Per Metre 40: 219.1667; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3/ survey @ 90m/ continue drilling HQ3/ rod pull for Bit change / run rods back in/ continue drilling HQ3/ condition hole due to large amount of cutting in hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250818D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-18 17:02 | NS 5pm | SF25_DDRD015 |  | Dean Melville | 3 | 390 |  |  | 0 | 108.8 | 144.8 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4860 | 1 |  |  |  | 175 | 10.25 | 1 |  | 0.75 | [5 empty] | 12 |  | 730 | 508.56 | 118.56 | 6273.56 | 6273.56 | 0.062166 | Cummulative Cost 38: 817508.13; EOM Cummulative Cost 39: 225180.92; Combined Cost Per Metre 40: 174.2656; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3 core, gyro surveys; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250818N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-19 05:02 | DS 5am | SF25_DDRD015 |  | Carl Jonas | 3 | 390 |  |  | 0 | 144.8 | 177.8 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 4600 |  | 1 | 1 | 13122 | 575 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 | 507.93 | 117.93 | 6552.93 | 6552.93 | 0.059515 | Cummulative Cost 38: 824061.06; EOM Cummulative Cost 39: 231733.85; Combined Cost Per Metre 40: 198.5736; PLOD LINK 41: LINK; Comments 42: condition hole/ continue drilling HQ3/ survey @144m/ continue drilling HQ3/ survey @162m/ continue drilling HQ3/ condition hole due to cuttings down hole; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250819D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-19 17:02 | NS 5pm | SF25_DDRD015 |  | Dean Melville | 3 | 390 |  |  | 0 | 177.8 | 213.8 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 5067 | 1 |  |  |  | 175 | 10.25 | 1 |  | 0.75 | [5 empty] | 12 |  | 730 | 626.49 | 236.49 | 6598.49 | 6598.49 | 0.059104 | Cummulative Cost 38: 830659.55; EOM Cummulative Cost 39: 238332.34; Combined Cost Per Metre 40: 183.2914; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3 core, gyro surveys; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250819N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-20 05:02 | DS 5am | SF25_DDRD015 |  | Carl Jonas | 3 | 390 |  |  | 0 | 213.8 | 246.8 | 33 |  |  | 0 |  |  | 0 | 33 | 4455 | 4950 |  | 1 | 1 | 13122 | 575 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 | 507.93 | 117.93 | 6902.93 | 6902.93 | 0.056498 | Cummulative Cost 38: 837562.48; EOM Cummulative Cost 39: 245235.27; Combined Cost Per Metre 40: 209.1797; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3/ survey @216m/ continue drilling HQ3/ survey @234m/ continue drilling HQ3 as Geo asked to extend hole/ survey @246m EOH/ pack up site/ start pulling out HQ rods EOH; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250820D; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-20 17:02 | NS 5pm | SF25_DDRD008 |  | Dean Melville | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 |  |  |  | 175 |  | 11.25 |  | 0.75 | [5 empty] | 12 |  | 5445 | 1151 | 761 | 6771 | 6771 | 0.057599 | Cummulative Cost 38: 844333.48; EOM Cummulative Cost 39: 252006.27; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: pull out, pack up, move to next hole, run poly to pad, start setting up, mast shot; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250820N; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-21 05:02 | DS 5am | SF25_DDRD008 |  | Carl Jonas | 3 | 390 |  |  | 0 | 0 | 21.5 | 21.5 |  |  | 0 |  |  | 0 | 21.5 | 2902.5 | 4140 |  | 1 | 1 | 13122 | 575 | 9 | 2.5 |  | 0.5 | [5 empty] | 12 |  | 1330 | 798.42 | 408.42 | 6843.42 | 6843.42 | 0.056989 | Cummulative Cost 38: 851176.9; EOM Cummulative Cost 39: 258849.69; Combined Cost Per Metre 40: 318.2986; PLOD LINK 41: LINK; Comments 42: set up drill site/ survey @0m/ start drilling HQ3 SOH/ ream PWT casing 6M/ change barrel to #m and add ori gear/ continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250821D; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-21 17:02 | NS 5pm | SF25_DDRD008 |  | Dean Melville | 3 | 390 |  |  | 0 | 21.5 | 57.5 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4860 | 1 |  |  |  | 175 | 10 | 1.25 |  | 0.75 | [5 empty] | 12 |  | 845 | 541.79 | 151.79 | 6421.79 | 6421.79 | 0.060731 | Cummulative Cost 38: 857598.69; EOM Cummulative Cost 39: 265271.48; Combined Cost Per Metre 40: 178.3831; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250821N; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-22 05:02 | DS 5am | SF25_DDRD008 |  | Carl Jonas | 3 | 390 |  |  | 0 | 57.5 | 93.5 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4860 |  | 1 | 1 | 13122 | 575 | 10 | 1.5 |  | 0.5 | [5 empty] | 12 |  | 870 | 507.93 | 117.93 | 6812.93 | 6812.93 | 0.057244 | Cummulative Cost 38: 864411.62; EOM Cummulative Cost 39: 272084.41; Combined Cost Per Metre 40: 189.2481; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / set up drill site/ survey @0m/ start drilling HQ3 SOH/ ream PWT casing 6M/ change barrel to #m and add ori gear/ continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250822D; Shift Shorthand 49: 2025-08
M 80/268 | G Vein DD | DDRD | 2025-08-22 17:02 | NS 5pm | SF25_DDRD008 |  | Dean Melville | 3 | 390 |  |  | 0 | 93.5 | 110 | 16.5 |  |  | 0 |  |  | 0 | 16.5 | 2227.5 | 2300 | 1 |  |  |  | 175 | 5 | 6.25 | Rig Move | 0.75 | [5 empty] | 12 |  | 3145 | 691 | 301 | 6311 | 6311 | 0.061797 | Cummulative Cost 38: 870722.62; EOM Cummulative Cost 39: 278395.41; Combined Cost Per Metre 40: 382.4848; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: continue drilling HQ3 core to EOH depth, eoh survey, pull out, move to next pad set up on next pad; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250822N; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-23 05:02 | DS 5am | SF25_DDRD009 |  | Carl Jonas | 3 | 390 |  |  | 0 | 0 | 36.7 | 36.7 |  |  | 0 |  |  | 0 | 36.7 | 4954.5 | 4954.5 |  | 1 | 1 | 13122 | 575 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 507.93 | 117.93 | 7137.43 | 7137.43 | 0.054642 | Cummulative Cost 38: 877860.05; EOM Cummulative Cost 39: 285532.84; Combined Cost Per Metre 40: 194.4804; PLOD LINK 41: LINK; Comments 42: Start drilling Hq3 SOH/ ream 6m PQ casing in hole/ pull out and change barrel to 3m barrel with ori gear/ continue drilling HQ3/ survey @18m/ continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250823D; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-23 17:02 | NS 5pm | SF25_DDRD009 |  | Dean Melville | 3 | 390 |  |  | 0 | 36.7 | 72.7 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4860 | 1 |  |  |  | 175 | 10.25 | 1 |  | 0.75 | [5 empty] | 12 |  | 730 | 528.7 | 138.7 | 6293.7 | 6293.7 | 0.061967 | Cummulative Cost 38: 884153.75; EOM Cummulative Cost 39: 291826.54; Combined Cost Per Metre 40: 174.825; PLOD LINK 41: LINK; Comments 42: continue drilling HQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250823N; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-24 05:02 | DS 5am | SF25_DDRD009 |  | Carl Jonas | 3 | 390 |  |  | 0 | 72.7 | 96.7 | 24 |  |  | 0 |  |  | 0 | 24 | 3240 | 3240 |  | 1 | 1 | 13122 | 575 | 6 | 5 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 2480 | 507.93 | 117.93 | 6802.93 | 6802.93 | 0.057328 | Cummulative Cost 38: 890956.68; EOM Cummulative Cost 39: 298629.47; Combined Cost Per Metre 40: 283.4554; PLOD LINK 41: LINK; Comments 42: continue drilling Hq3/ survey @72m/ continue drilling/ survey @93m EOH/ pack up site/ pull out all rods and casing/ rig down/ tram to next pad/ rig up/ 0m survey on new Hole DDRD011/ toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250824D; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-24 17:02 | NS 5pm | SF25_DDRD011 |  | Dean Melville | 3 | 390 |  |  | 0 | 0 | 22.8 | 22.8 |  |  | 0 |  |  | 0 | 22.8 | 3078 | 3335 | 1 |  |  |  | 175 | 7.25 | 3.5 |  | 0.75 |  |  | 0.5 |  | Toolbox | 12 |  | 1880 | 680.49 | 290.49 | 6070.49 | 6070.49 | 0.064245 | Cummulative Cost 38: 897027.17; EOM Cummulative Cost 39: 304699.96; Combined Cost Per Metre 40: 266.2496; PLOD LINK 41: LINK; Comments 42: finish site setup, start coring HQ from surface, ream HWT casing.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250824N; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-25 05:02 | DS 5am | SF25_DDRD011 |  | Carl Jonas | 3 | 390 |  |  | 0 | 22.8 | 54.8 | 32 |  |  | 0 |  |  | 0 | 32 | 4320 | 4370 |  | 1 | 1 | 13122 | 575 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 507.93 | 117.93 | 6552.93 | 6552.93 | 0.059515 | Cummulative Cost 38: 903580.1; EOM Cummulative Cost 39: 311252.89; Combined Cost Per Metre 40: 204.7791; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / continue drilling Hq3/ survey @18m/ continue drilling HQ3/ pull out rods for bit change/ run rods back in/ continue drilling hQ3/ survey @36m/continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250825D; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-25 17:02 | NS 5pm | SF25_DDRD011 |  | Dean Melville | 3 | 390 |  |  | 0 | 54.8 | 90.8 | 36 |  |  | 0 |  |  | 0 | 36 | 4860 | 4945 | 1 |  |  |  | 175 | 10.75 | 0.5 |  | 0.75 | [5 empty] | 12 |  | 500 | 507.93 | 117.93 | 6127.93 | 6127.93 | 0.063643 | Cummulative Cost 38: 909708.03; EOM Cummulative Cost 39: 317380.82; Combined Cost Per Metre 40: 170.2203; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start equipment: continue drilling HQ3 core, gyro surveys,; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250825N; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-26 05:02 | DS 5am | SF25_DDRD011 |  | Carl Jonas | 3 | 390 |  |  | 0 | 90.8 | 126.6 | 35.8 |  |  | 0 |  |  | 0 | 35.8 | 4833 | 4833 |  | 1 | 1 | 13122 | 575 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 507.93 | 117.93 | 7015.93 | 7015.93 | 0.055588 | Cummulative Cost 38: 916723.96; EOM Cummulative Cost 39: 324396.75; Combined Cost Per Metre 40: 195.9757; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment /survey@90m/ continue drilling Hq3/ survey @108m/ continue drilling HQ3/ pull out rods for bit change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250826D; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-26 17:02 | NS 5pm | SF25_DDRD011 |  | Dean Melville | 3 | 390 |  |  | 0 | 126.6 | 141.8 | 15.2 |  |  | 0 |  |  | 0 | 15.2 | 2052 | 2645 | 1 |  |  |  | 175 | 5.75 | 1.5 | Drilling costs reduced due to hole being canned on N/S without Geology agreement | 0.75 |  |  | 4 |  | costs for rigging should be DDH1 expense. Crew change | 12 |  | 960 | 390 | 0 | 4170 | 4170 | 0.093525 | Cummulative Cost 38: 920893.96; EOM Cummulative Cost 39: 328566.75; Combined Cost Per Metre 40: 274.3421; PLOD LINK 41: LINK; Comments 42: re-shift meeting / Pre-start all equipment / Drill HQ3 / Survey @ 72m & 90m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250826N; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-27 05:02 | DS 5am | SF25_DDRD011 |  | Tyla Smith | 3 | 390 |  |  | 0 | 141.8 | 141.8 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 13122 | 575 | 0 | 0 |  | 0.5 |  |  | 11.5 |  | Shift change - hole was canned without geo consultation - costs for rigging DDH1 Expense | 12 |  | 180 | 390 | 0 | 1145 | 1145 | 0.34061 | Cummulative Cost 38: 922038.96; EOM Cummulative Cost 39: 329711.75; PLOD LINK 41: LINK; Comments 42: re-shift meeting, Pre-start all equipment, continue to drill HQ3, survey @ 108m & 126m, condition hole throughout shift DR38,; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250827D; Shift Shorthand 49: 2025-08
M 80/269 | G Vein DD | DDRD | 2025-08-27 17:02 | NS 5pm | SF25_DDRD011 |  | Carl Jonas | 3 | 390 |  |  | 0 | 141.8 | 171.8 | 30 |  |  | 0 |  |  | 0 | 30 | 4050 | 4050 |  |  |  |  | 0 | 8.5 | 3 |  | 0.5 | [5 empty] | 12 |  | 1560 | 507.93 | 117.93 | 6117.93 | 6117.93 | 0.063747 | Cummulative Cost 38: 928156.89; EOM Cummulative Cost 39: 335829.68; Combined Cost Per Metre 40: 203.931; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting / Pre-start all equipment / Drill HQ3 / Survey @ 144m / Drilling harder broken formation 0.3m cavity 148.9-149.2m DR38,; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250827N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-28 05:02 | DS 5am | SF25_DDRD018 |  | Tyla Smith | 3 | 390 |  |  | 0 | 0 | 4.7 | 4.7 |  |  | 0 |  |  | 0 | 4.7 | 634.5 | 634.5 |  | 1 | 1 | 13122 | 575 | 1 | 9 |  | 0.5 | 1.5 | Water supply issue - both rigs starting new holes - filling sumps at the same time |  |  |  | 12 |  | 4860 | 390 | 0 | 6459.5 | 6459.5 | 0.060376 | Cummulative Cost 38: 934616.39; EOM Cummulative Cost 39: 342289.18; Combined Cost Per Metre 40: 1374.3617; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting - Pre-start all equipment - Pull rods for EOH - Pulling casing - Packup site - Tram rig to next pad - Multiple attempts to line up rig - Setup rig / site - Water Delay - Collar Hole with 1.5m gear; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250828D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-28 17:02 | NS 5pm | SF25_DDRD018 |  | Carl Jonas | 3 | 390 |  |  | 0 | 4.7 | 35.9 | 31.2 |  |  | 0 |  |  | 0 | 31.2 | 4212 | 4370 |  |  |  |  | 0 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 680.49 | 290.49 | 6150.49 | 6150.49 | 0.06341 | Cummulative Cost 38: 940766.88; EOM Cummulative Cost 39: 348439.67; Combined Cost Per Metre 40: 197.1311; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / continue drilling HQ3/ survey@18m/ ream 6m PQ casing/ barrel change to 3m barrel with ori gear/ continue drilling HQ3/ no water return down hole lost @32.3m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250828N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-29 05:02 | DS 5am | SF25_DDRD018 |  | Tyla Smith | 3 | 390 |  |  | 0 | 35.9 | 72.4 | 36.5 |  |  | 0 |  |  | 0 | 36.5 | 4927.5 | 4927.5 |  | 1 | 1 | 13122 | 575 | 9.25 | 1.25 |  | 0.5 | 1 | Water supply issue - both rigs starting new holes - loss of water return - bore pump not keeping up |  |  |  | 12 |  | 1115 | 527.5 | 137.5 | 7145 | 7145 | 0.054584 | Cummulative Cost 38: 947911.88; EOM Cummulative Cost 39: 355584.67; Combined Cost Per Metre 40: 195.7534; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting - Pre-start all equipment - Mix Muds/ Condition hole/ Bomb hole with LC Stop to try and get water return back - Continue drilling HQ3 - Hard ground, slow drilling - Gyro Survey @36m - Water delay - Continue drilling HQ3 - Short runs due to ground conditions; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250829D; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-29 17:02 | NS 5pm | SF25_DDRD018 |  | Carl Jonas | 3 | 390 |  |  | 0 | 72.4 | 108.6 | 36.2 |  |  | 0 |  |  | 0 | 36.2 | 4887 | 4887 |  |  |  |  | 0 | 10.5 | 1 |  | 0.5 | [5 empty] | 12 |  | 640 | 507.93 | 117.93 | 6034.93 | 6034.93 | 0.064624 | Cummulative Cost 38: 953946.81; EOM Cummulative Cost 39: 361619.6; Combined Cost Per Metre 40: 166.7108; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment /condition hole/ survey @72m/ continue drilling HQ3/ survey@90m/ continue drilling HQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250829N; Shift Shorthand 49: 2025-08
M 80/269 | Infill | DDRD | 2025-08-30 05:02 | DS 5am | SF25_DDRD018 |  | Tyla Smith | 3 | 390 |  |  | 0 | 108.6 | 130 | 21.4 |  |  | 0 |  |  | 0 | 21.4 | 2889 | 2889 |  | 1 | 1 | 13122 | 575 | 5 | 4.5 |  | 0.5 | 2 | Checking works required on pads for New met holes with driller |  |  |  | 12 |  | 2970 | 390 | 0 | 6824 | 6824 | 0.057151 | Cummulative Cost 38: 960770.81; EOM Cummulative Cost 39: 368443.6; Combined Cost Per Metre 40: 318.8785; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting - Pre-start all equipment - Mix Muds/ Condition hole - Continue drilling HQ3 - Gyro Survey @108 - Continue Drilling HQ3 to EOH Dephth - Gyro Survey @126m - Pulling Rods - Client consultation Checking future drill pads - Continue pulling rods - Pulling casing - Rigging Down - Site pack up; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250830D; Shift Shorthand 49: 2025-08
M 80/268 | Additional Met | DDMet | 2025-08-30 17:02 | NS 5pm | SF25_DMET029 |  | Carl Jonas | 3 | 390 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 11.5 | Long distance to tram rig and setup on pad for new MET holes. | 0.5 | [5 empty] | 12 |  | 5470 | 1151 | 761 | 6621 | 6621 | 0.058903 | Cummulative Cost 38: 967391.81; EOM Cummulative Cost 39: 375064.6; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / finish packing up site and move gear and tram rig to next pad/ set up next pad/ line sumps, set up poly line/ align rig/ survey @0m/ set up ready to drill; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250830N; Shift Shorthand 49: 2025-08
M 80/268 | Additional Met | DDMet | 2025-08-31 05:02 | DS 5am | SF25_DMET029 |  | Tyla Smith | 3 | 390 | 0 | 12 | 12 |  |  | 0 |  |  | 0 |  |  | 0 | 12 | 2100 | 2530 |  | 1 | 1 | 13122 | 575 | 5.5 | 5.5 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 2710 | 484.85 | 94.85 | 6299.85 | 6299.85 | 0.061906 | Cummulative Cost 38: 973691.66; EOM Cummulative Cost 39: 381364.45; Combined Cost Per Metre 40: 524.9875; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 31; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250831D; Shift Shorthand 49: 2025-08
M 80/268 | Additional Met | DDMet | 2025-08-31 17:02 | NS 5pm | SF25_DMET029 |  | Carl Jonas | 3 | 390 | 12.6 | 42.6 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10 | 1 |  | 0.5 |  |  | 0.5 |  |  | 12 |  | 640 | 8935.43 | 8545.43 | 14825.43 | 14825.43 | 0.026306 | Cummulative Cost 38: 988517.09; EOM Cummulative Cost 39: 396189.88; Combined Cost Per Metre 40: 494.181; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 08; Day 46: 31; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250831N; Shift Shorthand 49: 2025-08
M 80/268 | Additional Met | DDMet | 2025-09-01 05:02 | DS 5am | SF25_DMET029 |  | Tyla Smith | 3 | 390 | 42.6 | 50 | 7.4 |  |  | 0 |  |  | 0 |  |  | 0 | 7.4 | 1295 | 1840 |  | 1 | 1 | 13122 | 575 | 4 | 6.5 |  | 1.5 | [5 empty] | 12 |  | 3530 | 390 | 0 | 6335 | 6335 | 0.061563 | Cummulative Cost 38: 994852.09; EOM Cummulative Cost 39: 6335; Combined Cost Per Metre 40: 856.0811; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250901D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-01 17:02 | NS 5pm | SF25_DMET052 |  | Carl Jonas | 3 | 390 | 0 | 7.7 | 7.7 |  |  | 0 |  |  | 0 |  |  | 0 | 7.7 | 1347.5 | 1347.5 |  |  |  |  | 0 | 2.5 | 9 |  | 0.5 | [5 empty] | 12 |  | 4320 | 1123.63 | 733.63 | 6791.13 | 6791.13 | 0.057428 | Cummulative Cost 38: 1001643.22; EOM Cummulative Cost 39: 13126.13; Combined Cost Per Metre 40: 881.9649; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250901N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-02 05:02 | DS 5am | SF25_DMET052 |  | Tyla Smith | 3 | 390 | 7.7 | 28.8 | 21.1 |  |  | 0 |  |  | 0 |  |  | 0 | 21.1 | 3692.5 | 3692.5 |  | 1 | 1 | 13122 | 575 | 7.75 | 3.75 |  | 0.5 | [5 empty] | 12 |  | 1905 | 817.99 | 427.99 | 6990.49 | 6990.49 | 0.05579 | Cummulative Cost 38: 1008633.71; EOM Cummulative Cost 39: 20116.62; Combined Cost Per Metre 40: 331.3028; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting - Pre-start all equipment - Mixing muds/ Condition hole - Continue drilling PQ3 - Pull and run rods for stuck tube - Flush hole to lift cuttings - Continue drilling - Survey @18m - Continue drilling - Water delays, repair poly - Bomb hole with LC stop to try and get back water return - Continue drilling.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250902D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-02 17:02 | NS 5pm | SF25_DMET052 |  | Carl Jonas | 3 | 390 | 28.8 | 35.9 | 7.1 |  |  | 0 |  |  | 0 |  |  | 0 | 7.1 | 1242.5 | 2990 |  |  |  |  | 0 | 6.5 | 5 | Bit change - hard ground | 0.5 | [5 empty] | 12 |  | 2480 | 507.93 | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 1014611.64; EOM Cummulative Cost 39: 26094.55; Combined Cost Per Metre 40: 841.962; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250902N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-03 05:02 | DS 5am | SF25_DMET052 |  | Tyla Smith | 3 | 390 | 35.9 | 41.8 | 5.9 |  |  | 0 |  |  | 0 |  |  | 0 | 5.9 | 1032.5 | 1380 |  | 1 | 1 | 13122 | 575 | 3 | 7.5 | Fixing poly around site | 1.5 | [5 empty] | 12 |  | 3990 | 390 | 0 | 6335 | 6335 | 0.061563 | Cummulative Cost 38: 1020946.64; EOM Cummulative Cost 39: 32429.55; Combined Cost Per Metre 40: 1073.7288; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250903D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-03 17:02 | NS 5pm | SF25_DMET052 | SF25_DMET033 | Carl Jonas | 3 | 390 | 41.8 | 45.5 | 3.7 |  |  | 0 | 0 | 6.1 | 6.1 |  |  | 0 | 9.8 | 1715 | 2530 |  |  |  |  | 0 | 5.5 | 6 | Rig Move | 0.5 | [5 empty] | 12 |  | 2940 | 1241.83 | 851.83 | 6711.83 | 6711.83 | 0.058106 | Cummulative Cost 38: 1027658.47; EOM Cummulative Cost 39: 39141.38; Combined Cost Per Metre 40: 684.8806; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / survey @36m/ continue drilling PQ3 (short runs broken hard ground) /survey @ 43m EOH/ pull out PQ rods/ rig down move rig and align for next hole/ survey @0m/ set up drill site/ start drilling PQ3 from 0m/ pull out barrel and open hole with rock roller to 6m/ insert PVC casing/ collar set PVC wait to dry Assets: DR41 / LT 92 / LP73 / RV 04 / ST56 / GP62 / GP04 / KV08 / BV17 / DDH1DL173 / DDH1DL160; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250903N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-04 05:02 | DS 5am | SF25_DMET033 |  | Tyla Smith | 3 | 390 | 6.1 | 18.5 | 12.4 |  |  | 0 |  |  | 0 |  |  | 0 | 12.4 | 2170 | 4370 |  | 1 | 1 | 13122 | 575 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 390 | 0 | 6435 | 6435 | 0.060606 | Cummulative Cost 38: 1034093.47; EOM Cummulative Cost 39: 45576.38; Combined Cost Per Metre 40: 518.9516; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting - Pre-start all equipment - Running barrel - Mixing muds/ Condition hole - Continue Drilling PQ3, Hard ground, Slow drilling - Pull and run rods for stuck tube - Mix muds/ Condition hole - Continue drilling - Gyro Survey; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250904D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-04 17:02 | NS 5pm | SF25_DMET033 |  | Carl Jonas | 3 | 390 | 18.5 | 26.5 | 8 |  |  | 0 |  |  | 0 |  |  | 0 | 8 | 1400 | 3220 |  |  |  |  | 0 | 7 | 4.5 | Bit inspection + Change | 0.5 | [5 empty] | 12 |  | 2250 | 507.93 | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 1040071.4; EOM Cummulative Cost 39: 51554.31; Combined Cost Per Metre 40: 747.2413; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250904N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-05 05:02 | DS 5am | SF25_DMET033 |  | Tyla Smith | 3 | 390 | 26.5 | 35 | 8.5 |  |  | 0 |  |  | 0 |  |  | 0 | 8.5 | 1487.5 | 2875 |  | 1 | 1 | 13122 | 575 | 6.25 | 5.25 | Pack up and tram to new site - current one is tricky to maneuver out. | 0.5 | [5 empty] | 12 |  | 2595 | 610 | 220 | 6655 | 6655 | 0.058603 | Cummulative Cost 38: 1046726.4; EOM Cummulative Cost 39: 58209.31; Combined Cost Per Metre 40: 782.9412; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250905D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-05 17:02 | NS 5pm | SF25_DMET030 |  | Carl Jonas | 3 | 390 | 0 | 5.7 | 5.7 |  |  | 0 |  |  | 0 |  |  | 0 | 5.7 | 997.5 | 997.5 |  |  |  |  | 0 | 2 | 9.5 | Set up new pad, set up water line | 0.5 | [5 empty] | 12 |  | 4550 | 507.93 | 117.93 | 6055.43 | 6055.43 | 0.064405 | Cummulative Cost 38: 1052781.83; EOM Cummulative Cost 39: 64264.74; Combined Cost Per Metre 40: 1062.3561; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250905N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-06 05:02 | DS 5am | SF25_DMET030 |  | Tyla Smith | 3 | 390 | 5.7 | 9.5 | 3.8 |  |  | 0 |  |  | 0 |  |  | 0 | 3.8 | 665 | 1495 |  | 1 | 1 | 13122 | 575 | 3.25 | 8.25 | Set up new water line | 0.5 | [5 empty] | 12 |  | 3975 | 785.85 | 395.85 | 6830.85 | 6830.85 | 0.057094 | Cummulative Cost 38: 1059612.68; EOM Cummulative Cost 39: 71095.59; Combined Cost Per Metre 40: 1797.5921; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting - Pre-start all equipment - Mixing muds/ Condition hole - Continue drilling PQ3, Rock rolling - Set PVC Casing - Ream back to bottom - Switch to 3m Gear - Continue drilling PQ3, Slow Drilling - Mixing muds throughout shift when necessary - Standby, go and pull submersible pump from existing bore, roll up poly, - Run poly from new pump and connect to existing poly line; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250906D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-06 17:02 | NS 5pm | SF25_DMET030 |  | Carl Jonas | 3 | 390 | 9.5 | 31.9 | 22.4 |  |  | 0 |  |  | 0 |  |  | 0 | 22.4 | 3920 | 4025 |  |  |  |  | 0 | 8.75 | 2.75 |  | 0.5 | [5 empty] | 12 |  | 1445 | 507.93 | 117.93 | 5977.93 | 5977.93 | 0.06524 | Cummulative Cost 38: 1065590.61; EOM Cummulative Cost 39: 77073.52; Combined Cost Per Metre 40: 266.8719; PLOD LINK 41: LINK; Comments 42: Pre-shift meeting, Pre-start all equipment / set up lister at second bore and get water pumping/ condition hole/ continue drilling PQ3 short runs very broken ground/ survey @18m/ continue drilling PQ3 broken ground short runs it got much worse/ condition hole Assets: DR41 / LT 92 / LP73 / RV 04 / ST56 / GP62 / GP04 / KV08 / BV17 / DDH1DL173 / DDH1DL160; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250906N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-07 05:02 | DS 5am | SF25_DMET030 |  | Tyla Smith | 3 | 390 | 31.9 | 42.5 | 10.6 |  |  | 0 |  |  | 0 |  |  | 0 | 10.6 | 1855 | 4255 |  | 1 | 1 | 13122 | 575 | 9.25 | 1.75 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 985 | 610 | 220 | 6425 | 6425 | 0.0607 | Cummulative Cost 38: 1072015.61; EOM Cummulative Cost 39: 83498.52; Combined Cost Per Metre 40: 606.1321; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250907D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-07 17:02 | NS 5pm | SF25_DMET030 |  | Carl Jonas | 3 | 390 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 11 |  | 0.5 |  |  | 0.5 |  | Toolbox | 12 |  | 5240 | 390 | 0 | 5630 | 5630 | 0.069272 | Cummulative Cost 38: 1077645.61; EOM Cummulative Cost 39: 89128.52; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250907N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-08 05:02 | DS 5am | SF25_DMET055 |  | Tyla Smith | 3 | 390 | 0 | 15.4 | 15.4 |  |  | 0 |  |  | 0 |  |  | 0 | 15.4 | 2695 | 2990 |  | 1 | 1 | 13122 | 575 | 6.5 | 5 |  | 0.5 | [5 empty] | 12 |  | 2480 | 1289.12 | 899.12 | 7334.12 | 7334.12 | 0.053176 | Cummulative Cost 38: 1084979.73; EOM Cummulative Cost 39: 96462.64; Combined Cost Per Metre 40: 476.2416; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250908D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-08 17:02 | NS 5pm | SF25_DMET055 |  | Carl Jonas | 3 | 390 | 15.4 | 30.4 | 15 |  |  | 0 |  |  | 0 |  |  | 0 | 15 | 2625 | 2990 |  |  |  |  | 0 | 6.5 | 2 |  | 2 |  |  |  | 1.5 |  | 12 |  | 1640 | 1132.85 | 742.85 | 5762.85 | 5762.85 | 0.067675 | Cummulative Cost 38: 1090742.58; EOM Cummulative Cost 39: 102225.49; Combined Cost Per Metre 40: 384.19; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250908N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-09 05:02 | DS 5am | SF25_DMET055 |  | Tyla Smith | 3 | 390 | 30.4 | 54.4 | 24 |  |  | 0 |  |  | 0 |  |  | 0 | 24 | 4200 | 4370 |  | 1 | 1 | 13122 | 575 | 9.5 | 2 |  | 0.5 | [5 empty] | 12 |  | 1100 | 481.06 | 91.06 | 6526.06 | 6526.06 | 0.05976 | Cummulative Cost 38: 1097268.64; EOM Cummulative Cost 39: 108751.55; Combined Cost Per Metre 40: 271.9192; PLOD LINK 41: LINK; Comments 42: Mixing muds/ Condition hole - Start Drilling PQ3 - Gyro Survey @36m - Continue drilling PQ3 - Shutdown for client rig inductions - Continue drilling PQ3 - Mix muds/ Condition Hole throughout shift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250909D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-09 17:02 | NS 5pm | SF25_DMET055 |  | Carl Jonas | 3 | 390 | 54.4 | 62.9 | 8.5 |  |  | 0 |  |  | 0 |  |  | 0 | 8.5 | 1487.5 | 2415 |  |  |  |  | 0 | 5.25 | 1.25 | crew change | 0.5 |  |  | 4 | 1 | rig service and fly out | 12 |  | 755 | 390 | 0 | 3560 | 3560 | 0.10955 | Cummulative Cost 38: 1100828.64; EOM Cummulative Cost 39: 112311.55; Combined Cost Per Metre 40: 418.8235; PLOD LINK 41: LINK; Comments 42: condition hole due to ground conditions/ continue drilling PQ3/ hard ground slow drilling/ survey @54m/ continue drilling/ crew change; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250909N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-10 05:02 | DS 5am | SF25_DMET055 |  | Dean Melville | 4 | 520 | 62.9 | 63.4 | 0.5 |  |  | 0 |  |  | 0 |  |  | 0 | 0.5 | 87.5 | 115 | 1 | 1 | 1 | 13122 | 750 | 0.25 | 0.75 | crew change | 1 |  |  | 8.75 | 1.25 | fly in maintenance on bore pump | 12 |  | 705 | 520 | 0 | 2090 | 2090 | 0.2488 | Cummulative Cost 38: 1102918.64; EOM Cummulative Cost 39: 114401.55; Combined Cost Per Metre 40: 4180; PLOD LINK 41: LINK; Comments 42: crew change, travel to site, repairs on bore pump, continue drilling PQ3 core; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250910D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-10 17:02 | NS 5pm | SF25_DMET055 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1102918.64; EOM Cummulative Cost 39: 114401.55; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250910N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-11 05:02 | DS 5am | SF25_DMET055 |  | Dean Melville | 4 | 520 | 63.4 | 96.4 | 33 |  |  | 0 |  |  | 0 |  |  | 0 | 33 | 5775 | 5775 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 520 | 0 | 7865 | 7865 | 0.066116 | Cummulative Cost 38: 1110783.64; EOM Cummulative Cost 39: 122266.55; Combined Cost Per Metre 40: 238.3333; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core, gyro surveys; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250911D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-11 17:02 | NS 5pm | SF25_DMET055 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1110783.64; EOM Cummulative Cost 39: 122266.55; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250911N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-12 05:02 | DS 5am | SF25_DMET055 |  | Dean Melville | 4 | 520 | 96.4 | 110 | 13.6 |  |  | 0 |  |  | 0 |  |  | 0 | 13.6 | 2380 | 2415 | 1 | 1 | 1 | 13122 | 750 | 5.25 | 5.75 |  | 1 | [5 empty] | 12 |  | 3005 | 637.93 | 117.93 | 6807.93 | 6807.93 | 0.076382 | Cummulative Cost 38: 1117591.57; EOM Cummulative Cost 39: 129074.48; Combined Cost Per Metre 40: 500.5831; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core to EOH depth, gyro survey, pack up, move to next pad set up drill site.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250912D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-12 17:02 | NS 5pm | SF25_DMET055 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1117591.57; EOM Cummulative Cost 39: 129074.48; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250912N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-13 05:02 | DS 5am | SF25_DMET053 |  | Dean Melville | 4 | 520 | 0 | 30.6 | 30.6 |  |  | 0 |  |  | 0 |  |  | 0 | 30.6 | 5355 | 5355 | 1 | 1 | 1 | 13122 | 750 | 9.25 | 1.75 |  | 1 | [5 empty] | 12 |  | 1165 | 928.42 | 408.42 | 8198.42 | 8198.42 | 0.063427 | Cummulative Cost 38: 1125789.99; EOM Cummulative Cost 39: 137272.9; Combined Cost Per Metre 40: 267.9222; PLOD LINK 41: LINK; Comments 42: start coring PQ3 from surface, ream PWT casing, gyro survey; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250913D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-13 17:02 | NS 5pm | SF25_DMET053 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1125789.99; EOM Cummulative Cost 39: 137272.9; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250913N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-14 05:02 | DS 5am | SF25_DMET053 | SF25_DMET036 | Dean Melville | 4 | 520 | 30.6 | 50 | 19.4 |  |  | 0 | 0 | 8.3 | 8.3 |  |  | 0 | 27.7 | 4847.5 | 4847.5 | 1 | 1 | 1 | 13122 | 750 | 7.5 | 2.5 |  | 1 |  |  | 1 |  | Toolbox | 12 |  | 1510 | 928.42 | 408.42 | 8035.92 | 8035.92 | 0.064709 | Cummulative Cost 38: 1133825.91; EOM Cummulative Cost 39: 145308.82; Combined Cost Per Metre 40: 290.1054; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 to EOH, gyro surveys, set up on next hole (same pad) toolbox meeting end of shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250914D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-14 17:02 | NS 5pm | SF25_DMET036 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1133825.91; EOM Cummulative Cost 39: 145308.82; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250914N; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-15 05:02 | DS 5am | SF25_DMET036 |  | Dean Melville | 4 | 520 | 8.3 | 35 | 26.7 |  |  | 0 |  |  | 0 |  |  | 0 | 26.7 | 4672.5 | 4672.5 | 1 | 1 | 1 | 13122 | 750 | 6.5 | 4.5 |  | 1 | [5 empty] | 12 |  | 2430 | 1649.81 | 1129.81 | 9502.31 | 9502.31 | 0.054724 | Cummulative Cost 38: 1143328.22; EOM Cummulative Cost 39: 154811.13; Combined Cost Per Metre 40: 355.8918; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 to EOH, gyro surveys, pack up, run bore pump into bore, run poly to next pad. Added frieght costs; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250915D; Shift Shorthand 49: 2025-09
M 80/268 | Additional Met | DDMet | 2025-09-15 17:02 | NS 5pm | SF25_DMET036 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1143328.22; EOM Cummulative Cost 39: 154811.13; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250915N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-16 05:02 | DS 5am | SF25_DMET050 |  | Dean Melville | 4 | 520 | 0 | 15.5 | 15.5 |  |  | 0 |  |  | 0 |  |  | 0 | 15.5 | 2712.5 | 2712.5 | 1 | 1 | 1 | 13122 | 750 | 5.25 | 5.75 |  | 1 | [5 empty] | 12 |  | 3005 | 928.42 | 408.42 | 7395.92 | 7395.92 | 0.070309 | Cummulative Cost 38: 1150724.14; EOM Cummulative Cost 39: 162207.05; Combined Cost Per Metre 40: 477.1561; PLOD LINK 41: LINK; Comments 42: finish running poly, move gear to next pad, start coring PQ3 from surface, ream PWT casing; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250916D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-16 17:02 | NS 5pm | SF25_DMET050 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1150724.14; EOM Cummulative Cost 39: 162207.05; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250916N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-17 05:02 | DS 5am | SF25_DMET050 |  | Dean Melville | 4 | 520 | 15.5 | 45.5 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 637.93 | 117.93 | 7457.93 | 7457.93 | 0.069724 | Cummulative Cost 38: 1158182.07; EOM Cummulative Cost 39: 169664.98; Combined Cost Per Metre 40: 248.5977; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250917D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-17 17:02 | NS 5pm | SF25_DMET050 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1158182.07; EOM Cummulative Cost 39: 169664.98; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250917N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-18 05:02 | DS 5am | SF25_DMET050 |  | Dean Melville | 4 | 520 | 45.5 | 67.7 | 22.2 |  |  | 0 |  |  | 0 |  |  | 0 | 22.2 | 3885 | 4370 | 1 | 1 | 1 | 13122 | 750 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 637.93 | 117.93 | 6807.93 | 6807.93 | 0.076382 | Cummulative Cost 38: 1164990; EOM Cummulative Cost 39: 176472.91; Combined Cost Per Metre 40: 306.6635; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core, gyro surveys, pull out for bit change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250918D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-18 17:02 | NS 5pm | SF25_DMET050 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1164990; EOM Cummulative Cost 39: 176472.91; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250918N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-19 05:02 | DS 5am | SF25_DMET050 |  | Dean Melville | 4 | 520 | 67.7 | 96.5 | 28.8 |  |  | 0 |  |  | 0 |  |  | 0 | 28.8 | 5040 | 5040 | 1 | 1 | 1 | 13122 | 750 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 637.93 | 117.93 | 7477.93 | 7477.93 | 0.069538 | Cummulative Cost 38: 1172467.93; EOM Cummulative Cost 39: 183950.84; Combined Cost Per Metre 40: 259.6503; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core, gyro surveys, advance PWT to 9m; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250919D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-19 17:02 | NS 5pm | SF25_DMET050 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1172467.93; EOM Cummulative Cost 39: 183950.84; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250919N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-20 05:02 | DS 5am | SF25_DMET050 |  | Dean Melville | 4 | 520 | 96.5 | 120 | 23.5 |  |  | 0 |  |  | 0 |  |  | 0 | 23.5 | 4112.5 | 4140 | 1 | 1 | 1 | 13122 | 750 | 9 | 2 |  | 1 | [5 empty] | 12 |  | 1280 | 637.93 | 117.93 | 6807.93 | 6807.93 | 0.076382 | Cummulative Cost 38: 1179275.86; EOM Cummulative Cost 39: 190758.77; Combined Cost Per Metre 40: 289.6991; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core to EOH, gyro surveys, pull out rods; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250920D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-20 17:02 | NS 5pm | SF25_DMET050 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1179275.86; EOM Cummulative Cost 39: 190758.77; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250920N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-21 05:02 | DS 5am | SF25_DMET042 |  | Dean Melville | 4 | 520 | 0 | 12.6 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 | 12.6 | 2205 | 2990 | 1 | 1 | 1 | 13122 | 750 | 6.5 | 4 |  | 1 |  |  | 0.5 |  | Toolbox | 12 |  | 2200 | 637.93 | 117.93 | 6577.93 | 6577.93 | 0.079052 | Cummulative Cost 38: 1185853.79; EOM Cummulative Cost 39: 197336.7; Combined Cost Per Metre 40: 522.0579; PLOD LINK 41: LINK; Comments 42: move rig onto next hole, start coring PQ3 from surface, ream PWT casing.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250921D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-21 17:02 | NS 5pm | SF25_DMET042 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1185853.79; EOM Cummulative Cost 39: 197336.7; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250921N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-22 05:02 | DS 5am | SF25_DMET042 |  | Dean Melville | 4 | 520 | 12.6 | 42.3 | 29.7 |  |  | 0 |  |  | 0 |  |  | 0 | 29.7 | 5197.5 | 5197.5 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 756.49 | 236.49 | 7523.99 | 7523.99 | 0.069112 | Cummulative Cost 38: 1193377.78; EOM Cummulative Cost 39: 204860.69; Combined Cost Per Metre 40: 253.333; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core, gyro surveys, pull out for bit change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250922D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-22 17:02 | NS 5pm | SF25_DMET042 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1193377.78; EOM Cummulative Cost 39: 204860.69; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250922N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-23 05:02 | DS 5am | SF25_DMET042 |  | Dean Melville | 4 | 520 | 42.3 | 66.6 | 24.3 |  |  | 0 |  |  | 0 |  |  | 0 | 24.3 | 4252.5 | 4600 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 637.93 | 117.93 | 6807.93 | 6807.93 | 0.076382 | Cummulative Cost 38: 1200185.71; EOM Cummulative Cost 39: 211668.62; Combined Cost Per Metre 40: 280.1617; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core, gyro surveys, pull out for bit change.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250923D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-23 17:02 | NS 5pm | SF25_DMET042 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  | Cummulative Cost 38: 1200185.71; EOM Cummulative Cost 39: 211668.62; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250923N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-24 05:02 | DS 5am | SF25_DMET042 |  | Dean Melville | 4 | 520 | 66.6 | 90.6 | 24 |  |  | 0 |  |  | 0 |  |  | 0 | 24 | 4200 | 4945 | 1 | 1 | 1 | 13122 | 750 | 10.75 | 0.25 |  | 1 | [5 empty] | 12 |  | 475 | 637.93 | 117.93 | 6807.93 | 6807.93 | 0.076382 | Cummulative Cost 38: 1206993.64; EOM Cummulative Cost 39: 218476.55; Combined Cost Per Metre 40: 283.6637; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250924D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-24 17:02 | NS 5pm | SF25_DMET042 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  | Cummulative Cost 38: 1206993.64; EOM Cummulative Cost 39: 218476.55; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250924N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-25 05:02 | DS 5am | SF25_DMET042 |  | Carl Jonas | 4 | 520 | 90.6 | 120 | 29.4 |  |  | 0 |  |  | 0 |  |  | 0 | 29.4 | 5145 | 5145 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 983.98 | 463.98 | 7698.98 | 7698.98 | 0.067541 | Cummulative Cost 38: 1214692.62; EOM Cummulative Cost 39: 226175.53; Combined Cost Per Metre 40: 261.8701; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: condition hole/ continue drilling PQ3 core, gyro surveys @90m/ continue drilling PQ3/ survey @108m/ continue drilling; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250925D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-25 17:02 | NS 5pm | SF25_DMET042 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  | Cummulative Cost 38: 1214692.62; EOM Cummulative Cost 39: 226175.53; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 25; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250925N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-26 05:02 | DS 5am | SF25_DMET043 |  | Carl Jonas | 4 | 520 | 0 | 5.9 | 5.9 |  |  | 0 |  |  | 0 |  |  | 0 | 5.9 | 1032.5 | 1495 | 1 | 1 | 1 | 13122 | 750 | 3.25 | 7.75 |  | 1 | [5 empty] | 12 |  | 3925 | 1229.42 | 709.42 | 7399.42 | 7399.42 | 0.070276 | Cummulative Cost 38: 1222092.04; EOM Cummulative Cost 39: 233574.95; Combined Cost Per Metre 40: 1254.139; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, gyro surveys @EOH120m/ pull out PQ rods EOH/ caseing was stuck worked it and got it free/ pull out all PWT casing/ pack up rig and drill site move to next pad/ rig up and align, 0m survey/ set up new site/ start drilling PQ3/ rock role hole/ run in PVC casing and set the colar/ wait for colar to set; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 26; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250926D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-26 17:02 | NS 5pm | SF25_DMET043 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 | 0 |  | Cummulative Cost 38: 1222092.04; EOM Cummulative Cost 39: 233574.95; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 26; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250926N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-27 05:02 | DS 5am | SF25_DMET043 |  | Carl Jonas | 4 | 520 | 5.9 | 18.5 | 12.6 |  |  | 0 |  |  | 0 |  |  | 0 | 12.6 | 2205 | 4485 | 1 | 1 | 1 | 13122 | 750 | 9.75 | 1.25 |  | 1 | [5 empty] | 12 |  | 935 | 928.42 | 408.42 | 7098.42 | 7098.42 | 0.073256 | Cummulative Cost 38: 1229190.46; EOM Cummulative Cost 39: 240673.37; Combined Cost Per Metre 40: 563.3667; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 27; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250927D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-27 17:02 | NS 5pm | SF25_DMET043 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1229190.46; EOM Cummulative Cost 39: 240673.37; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 27; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250927N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-28 05:02 | DS 5am | SF25_DMET043 |  | Carl Jonas | 4 | 520 | 18.5 | 45.5 | 27 |  |  | 0 |  |  | 0 |  |  | 0 | 27 | 4725 | 4725 | 1 | 1 | 1 | 13122 | 750 | 9.5 | 1 |  | 1 |  |  | 0.5 |  | Toolbox | 12 |  | 820 | 928.42 | 408.42 | 7223.42 | 7223.42 | 0.071988 | Cummulative Cost 38: 1236413.88; EOM Cummulative Cost 39: 247896.79; Combined Cost Per Metre 40: 267.5341; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, continue drilling PQ3/ survey @18m/ continue drilling PQ3/ survey @36m/ continue drilling PQ3/ Toolbox meeting; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 28; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250928D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-28 17:02 | NS 5pm | SF25_DMET043 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1236413.88; EOM Cummulative Cost 39: 247896.79; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 28; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250928N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-29 05:02 | DS 5am | SF25_DMET043 |  | Carl Jonas | 4 | 520 | 45.5 | 63.5 | 18 |  |  | 0 |  |  | 0 |  |  | 0 | 18 | 3150 | 4370 | 1 | 1 | 1 | 13122 | 750 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 628.93 | 108.93 | 6798.93 | 6798.93 | 0.076483 | Cummulative Cost 38: 1243212.81; EOM Cummulative Cost 39: 254695.72; Combined Cost Per Metre 40: 377.7183; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, continue drilling PQ3/ survey @18m/ continue drilling PQ3/ survey @54m/ pull out for bit inspection change front reamer and run rods back down hole/ continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 29; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250929D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-29 17:02 | NS 5pm | SF25_DMET043 |  | Dean Melville | 3 | 390 | 63.5 | 93.5 | 30 |  |  | 0 |  |  | 0 |  |  | 0 | 30 | 5250 | 5250 |  |  |  |  | 0 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 507.93 | 117.93 | 6577.93 | 6577.93 | 0.059289 | Cummulative Cost 38: 1249790.74; EOM Cummulative Cost 39: 261273.65; Combined Cost Per Metre 40: 219.2643; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 29; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250929N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-30 05:02 | DS 5am | SF25_DMET043 | SF25_DMET044 | Carl Jonas | 4 | 520 | 93.5 | 100 | 6.5 |  |  | 0 | 0 | 5.9 | 5.9 |  |  | 0 | 12.4 | 2170 | 2170 | 1 | 1 | 1 | 13122 | 750 | 3.25 | 7.75 |  | 1 | [5 empty] | 12 |  | 3925 | 1111.49 | 591.49 | 7956.49 | 7956.49 | 0.065355 | Cummulative Cost 38: 1257747.23; EOM Cummulative Cost 39: 269230.14; Combined Cost Per Metre 40: 641.6524; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, continue drilling PQ3/ survey @97m/ pull out all rods EOH/ rig down/ pack up site/ tram rig and move gear to next pad/ align rig/ survey @0m/ set up site/ start hole/ drill to 6m/ rock roll/ PVC colar hole and let set; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 30; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250930D; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-09-30 17:02 | NS 5pm | SF25_DMET044 |  | Dean Melville | 3 | 390 | 5.9 | 41.9 | 36 |  |  | 0 |  |  | 0 |  |  | 0 | 36 | 6300 | 6300 |  |  |  |  | 0 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 12130.84 | 11740.84 | 19480.84 | 19480.84 | 0.02002 | Cummulative Cost 38: 1277228.07; EOM Cummulative Cost 39: 288710.98; Combined Cost Per Metre 40: 541.1344; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: run in 3m barrel, continue drilling PQ3 core, gyro surveys, pull out for bit change. - Flights and extra monthly costs added; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 09; Day 46: 30; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-250930N; Shift Shorthand 49: 2025-09
M 80/269 | Additional Met | DDMet | 2025-10-01 05:02 | DS 5am | SF25_DMET044 |  | Carl Jonas | 4 | 520 | 41.9 | 53.6 | 11.7 |  |  | 0 |  |  | 0 |  |  | 0 | 11.7 | 2047.5 | 4600 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 520 | 0 | 6690 | 6690 | 0.077728 | Cummulative Cost 38: 1283918.07; EOM Cummulative Cost 39: 6690; Combined Cost Per Metre 40: 571.7949; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, condition hole/ continue drilling PQ3/ pull out for bit inspection/ continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 01; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251001D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-01 17:02 | NS 5pm | SF25_DMET044 |  | Dean Melville | 3 | 390 | 53.6 | 73.1 | 19.5 |  |  | 0 |  |  | 0 |  |  | 0 | 19.5 | 3412.5 | 3910 |  |  |  |  | 0 | 8.5 | 2.5 |  | 1 | [5 empty] | 12 |  | 1510 | 727.93 | 337.93 | 6147.93 | 6147.93 | 0.063436 | Cummulative Cost 38: 1290066; EOM Cummulative Cost 39: 12837.93; Combined Cost Per Metre 40: 315.2785; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core, gyro surveys, pull out for bit change; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 01; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251001N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-02 05:02 | DS 5am | SF25_DMET044 |  | Carl Jonas | 4 | 520 | 73.1 | 88.7 | 15.6 |  |  | 0 |  |  | 0 |  |  | 0 | 15.6 | 2730 | 4370 | 1 | 1 | 1 | 13122 | 750 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 520 | 0 | 6690 | 6690 | 0.077728 | Cummulative Cost 38: 1296756; EOM Cummulative Cost 39: 19527.93; Combined Cost Per Metre 40: 428.8462; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, condition hole/ continue drilling PQ3/ survey @72m/ pull out for bit inspection/ continue drilling PQ3; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 02; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251002D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-02 17:02 | NS 5pm | SF25_DMET044 |  | Dean Melville | 3 | 390 | 88.7 | 110.1 | 21.4 |  |  | 0 |  |  | 0 |  |  | 0 | 21.4 | 3745 | 4600 |  |  |  |  | 0 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 507.93 | 117.93 | 5927.93 | 5927.93 | 0.06579 | Cummulative Cost 38: 1302683.93; EOM Cummulative Cost 39: 25455.86; Combined Cost Per Metre 40: 277.0061; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 02; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251002N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-03 05:02 | DS 5am | SF25_DMET044 |  | Carl Jonas | 4 | 520 | 110.1 | 135.6 | 25.5 |  |  | 0 |  |  | 0 |  |  | 0 | 25.5 | 4462.5 | 4462.5 | 1 | 1 | 1 | 13122 | 750 | 8.5 | 0.5 |  | 1 | 2 | Lightning Delay/standby 2 hours |  |  |  | 12 |  | 1310 | 520 | 0 | 7042.5 | 7042.5 | 0.073837 | Cummulative Cost 38: 1309726.43; EOM Cummulative Cost 39: 32498.36; Combined Cost Per Metre 40: 276.1765; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, condition hole/ continue drilling PQ3/ survey @126m/continue drilling PQ3/ lightning delay from 2:55pm; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 03; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251003D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-03 17:02 | NS 5pm | SF25_DMET044 | SF25_DMET031 | Dean Melville | 3 | 390 | 135.6 | 140 | 4.4 |  |  | 0 | 0 | 2.8 | 2.8 |  |  | 0 | 7.2 | 1260 | 1610 |  |  |  |  | 0 | 3.5 | 7.5 |  | 1 | [5 empty] | 12 |  | 3810 | 646.63 | 256.63 | 6066.63 | 6066.63 | 0.064286 | Cummulative Cost 38: 1315793.06; EOM Cummulative Cost 39: 38564.99; Combined Cost Per Metre 40: 842.5875; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core to EOH depth, EOH survey, pull out, move onto next pad. set up, start coring PQ3 from surface.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 03; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251003N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-04 05:02 | DS 5am | SF25_DMET031 |  | Carl Jonas | 4 | 520 | 2.8 | 12.5 | 9.7 |  |  | 0 |  |  | 0 |  |  | 0 | 9.7 | 1697.5 | 2990 | 1 | 1 | 1 | 13122 | 750 | 6.5 | 4.5 |  | 1 | [5 empty] | 12 |  | 2430 | 520 | 0 | 6690 | 6690 | 0.077728 | Cummulative Cost 38: 1322483.06; EOM Cummulative Cost 39: 45254.99; Combined Cost Per Metre 40: 689.6907; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment:, ran in barrel/ continue drilling PQ3 short runs broken ground/ pulled out to rock role hole for PVC the rock roller couldn't do it because of the ground so pulled it out went run in 3m barrel hole had caved in had to change back to 1.5m gear and ream out hole while reaming to bottom the hole diverted and cut a lip spoke to geo and they said continue drilling/ reamed 6m PWT casing/ condition hole/ pulled out 1.5 gear ready for 3m gear/; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 04; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251004D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-04 17:02 | NS 5pm | SF25_DMET031 |  | Dean Melville | 3 | 390 | 12.5 | 30 | 17.5 |  |  | 0 |  |  | 0 |  |  | 0 | 17.5 | 3062.5 | 4600 |  |  |  |  | 0 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 646.63 | 256.63 | 6066.63 | 6066.63 | 0.064286 | Cummulative Cost 38: 1328549.69; EOM Cummulative Cost 39: 51321.62; Combined Cost Per Metre 40: 346.6646; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: continue drilling PQ3 core to EOH, gyro surveys.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 04; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251004N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-05 05:02 | DS 5am | SF25_DMET031 |  | Carl Jonas | 2 | 260 | 30 | 30 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 | 0 | 0 |  | 1 |  |  | 11 |  | No driller onsite due to injury | 12 |  | 360 | 260 | 0 | 1370 | 1370 | 0.18978 | Cummulative Cost 38: 1329919.69; EOM Cummulative Cost 39: 52691.62; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: no driller on dayshift. toolbox end of shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 05; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251005D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-05 17:02 | NS 5pm | SF25_DMET031 | SF25_DMET046 | Dean Melville | 3 | 390 | 30 | 33.9 | 3.9 |  |  | 0 | 0 | 2.9 | 2.9 |  |  | 0 | 6.8 | 1190 | 1265 |  |  |  |  | 0 | 2.75 | 7.75 |  | 1 |  |  | 0.5 |  | Toolbox | 12 |  | 3925 | 390 | 0 | 5580 | 5580 | 0.069892 | Cummulative Cost 38: 1335499.69; EOM Cummulative Cost 39: 58271.62; Combined Cost Per Metre 40: 820.5882; PLOD LINK 41: LINK; Comments 42: preshift meeting, prestart equipment: hole extended to 33.9m, pull out, move rig to next pad, set up, mast shot, start coring PQ3 from surface.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 05; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251005N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-06 05:02 | DS 5am | SF25_DMET046 |  | Carl Jonas | 2 | 260 | 2.9 | 2.9 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 | 0 | 0 |  | 1 |  |  | 11 |  | No driller onsite due to injury | 12 |  | 360 | 260 | 0 | 1370 | 1370 | 0.18978 | Cummulative Cost 38: 1336869.69; EOM Cummulative Cost 39: 59641.62; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: no driller on dayshift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 06; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251006D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-06 17:02 | NS 5pm | SF25_DMET046 |  | Dean Melville | 3 | 390 | 2.9 | 13.8 | 10.9 |  |  | 0 |  |  | 0 |  |  | 0 | 10.9 | 1907.5 | 3910 |  |  |  |  | 0 | 8.5 | 2.5 |  | 1 | [5 empty] | 12 |  | 1510 | 830.7 | 440.7 | 6250.7 | 6250.7 | 0.062393 | Cummulative Cost 38: 1343120.39; EOM Cummulative Cost 39: 65892.32; Combined Cost Per Metre 40: 573.4587; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 core (broken/ pressurized), ream PWT casing, pull out for stuck tubes.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 06; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251006N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-07 05:02 | DS 5am | SF25_DMET046 |  | Carl Jonas | 2 | 260 | 13.8 | 13.8 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 |  |  |  | 1 |  |  | 11 |  | No driller onsite due to injury | 12 |  | 360 | 260 | 0 | 1370 | 1370 | 0.18978 | Cummulative Cost 38: 1344490.39; EOM Cummulative Cost 39: 67262.32; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no driller on dayshift; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 07; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251007D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-07 17:02 | NS 5pm | SF25_DMET046 |  | Dean Melville | 3 | 390 | 13.8 | 25.8 | 12 |  |  | 0 |  |  | 0 |  |  | 0 | 12 | 2100 | 2100 |  |  |  |  | 0 | 4.5 | 3.5 | packed up early for crew change | 1 |  |  | 3 |  |  | 12 |  | 1970 | 1050.7 | 660.7 | 5120.7 | 5120.7 | 0.076161 | Cummulative Cost 38: 1349611.09; EOM Cummulative Cost 39: 72383.02; Combined Cost Per Metre 40: 426.725; PLOD LINK 41: LINK; Comments 42: ream barrel back to BOH, advance PWT casing to 12m, continue drilling PQ3 core, gyro surveys; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 07; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251007N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-08 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 4 | 520 | 25.8 | 30.5 | 4.7 |  |  | 0 |  |  | 0 |  |  | 0 | 4.7 | 822.5 | 1610 | 1 | 1 | 1 | 13122 | 750 | 3.5 | 1.25 | crew change | 1 |  |  | 6.25 |  | crew change | 12 |  | 935 | 520 | 0 | 3815 | 3815 | 0.1363 | Cummulative Cost 38: 1353426.09; EOM Cummulative Cost 39: 76198.02; Combined Cost Per Metre 40: 811.7021; PLOD LINK 41: LINK; Comments 42: Flush Hole and core ahead in broken ground, Pull Barrel and change to 3m Standard, Had to ream from 12m due to new Reamer as Existing reamer shell was U/S, Core ahead 3m Standard.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 08; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251008D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-08 17:02 | NS 5pm | SF25_DMET046 |  |  |  |  | 30.5 | 30.5 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  | no NS driller | 12 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1353426.09; EOM Cummulative Cost 39: 76198.02; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 08; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251008N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-09 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 5 | 650 | 30.5 | 69.5 | 39 |  |  | 0 |  |  | 0 |  |  | 0 | 39 | 6825 | 6825 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 1092.28 | 442.28 | 9487.28 | 9487.28 | 0.068513 | Cummulative Cost 38: 1362913.37; EOM Cummulative Cost 39: 85685.3; Combined Cost Per Metre 40: 243.2636; PLOD LINK 41: LINK; Comments 42: Flush Hole and core ahead and Survey every 18m, Lost water return and rods bogged @71.6m, Work rods (Stuck) Consult Client / DDH1 Operations, Work Rods.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 09; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251009D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-09 17:02 | NS 5pm | SF25_DMET046 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  | no NS driller | 12 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1362913.37; EOM Cummulative Cost 39: 85685.3; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 09; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251009N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-10 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 5 | 650 | 69.5 | 71.6 | 2.1 | 71.6 | 78.4 | 6.8 |  |  | 0 |  |  | 0 | 8.9 | 1285.5 | 1380 | 1 | 1 | 1 | 13122 | 750 | 3 | 5 | shut down for lightning | 1 | 3 | shut down for lightning |  |  |  | 12 |  | 3740 | 767.93 | 117.93 | 6637.93 | 6637.93 | 0.097922 | Cummulative Cost 38: 1369551.3; EOM Cummulative Cost 39: 92323.23; Combined Cost Per Metre 40: 745.8348; PLOD LINK 41: LINK; Comments 42: Re-Align Rig, Make up overshot on HRQ Rods, Run Overshot on rods and retrieve PQ3 Tube, Run HQ3 Standard Barrel, Drill through stuck PQ Barrel, Core ahead to 76.5m, Work PQ Barrel (still stuck), Pull HQ barrel to add Ori's and change to softer matrix bit, Run Barrel and drill on HQ3, Shut down Lightning.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 10; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251010D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-10 17:02 | NS 5pm | SF25_DMET046 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  | no NS driller | 12 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1369551.3; EOM Cummulative Cost 39: 92323.23; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 10; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251010N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-11 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 5 | 650 |  |  | 0 | 78.4 | 105.4 | 27 |  |  | 0 |  |  | 0 | 27 | 3645 | 3645 | 1 | 1 | 1 | 13122 | 750 | 7.5 | 0.5 | shut down for lightning | 1 | 3 | shut down for lightning |  |  |  | 12 |  | 1670 | 767.93 | 117.93 | 6832.93 | 6832.93 | 0.095128 | Cummulative Cost 38: 1376384.23; EOM Cummulative Cost 39: 99156.16; Combined Cost Per Metre 40: 253.0715; PLOD LINK 41: LINK; Comments 42: Core Ahead and survey in Harder competent formation, Shut down for Lightning; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 11; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251011D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-11 17:02 | NS 5pm | SF25_DMET046 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  | no NS driller | 12 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1376384.23; EOM Cummulative Cost 39: 99156.16; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 11; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251011N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-12 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 5 | 650 |  |  | 0 | 105.4 | 126.4 | 21 |  |  | 0 |  |  | 0 | 21 | 2835 | 3450 | 1 | 1 | 1 | 13122 | 750 | 7.5 | 0.25 | shut down for lightning | 1 | 3 | shut down for lightning | 0.25 |  | toolbox meeting | 12 |  | 1555 | 767.93 | 117.93 | 6522.93 | 6522.93 | 0.099648 | Cummulative Cost 38: 1382907.16; EOM Cummulative Cost 39: 105679.09; Combined Cost Per Metre 40: 310.6157; PLOD LINK 41: LINK; Comments 42: Core Ahead and survey in Harder competent formation, Shut down for Lightning; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 12; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251012D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-12 17:02 | NS 5pm | SF25_DMET046 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  | no NS driller | 12 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1382907.16; EOM Cummulative Cost 39: 105679.09; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 12; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251012N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-13 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 5 | 650 |  |  | 0 | 126.4 | 147.4 | 21 |  |  | 0 |  |  | 0 | 21 | 2835 | 4370 | 1 | 1 | 1 | 13122 | 750 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 1146.2 | 496.2 | 7316.2 | 7316.2 | 0.088844 | Cummulative Cost 38: 1390223.36; EOM Cummulative Cost 39: 112995.29; Combined Cost Per Metre 40: 348.3905; PLOD LINK 41: LINK; Comments 42: Core Ahead and survey, Pull and change bit due to poor penetration @133.5m, Ran Softer series bit, Daff rods on way in, Lost water return 135.4m, Pump LCM and regain; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 13; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251013D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-13 17:02 | NS 5pm | SF25_DMET046 | [6 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  |  | 12 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1390223.36; EOM Cummulative Cost 39: 112995.29; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no NS at the moment; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 13; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251013N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-14 05:02 | DS 5am | SF25_DMET046 |  | Wade Thompson | 6 | 780 |  |  | 0 | 147.4 | 159.4 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 2185 | 1 | 1 | 1 | 13122 | 750 | 4.75 | 6.25 |  | 1 | [5 empty] | 12 |  | 3235 | 6011.25 | 5231.25 | 12181.25 | 12181.25 | 0.064033 | Cummulative Cost 38: 1402404.61; EOM Cummulative Cost 39: 125176.54; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: Core Ahead and survey in broken ground, Client called EOH @ 159.4m, Pull HQ Barrel, Work PQ Barrel (Still Stuck) Run HW Cutters to 65.5m, Preform cut, Pull HW Cutters, Pull PHD, Pull PWT, Mast down and pack site. *****Drill Steel in Hole 65.5m -> 71.6m*****; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 14; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251014D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-14 17:02 | NS 5pm | SF25_DMET045 |  | Scott O'Hehir | 0 | 0 | 0 | 10.7 | 10.7 |  |  | 0 |  |  | 0 |  |  | 0 | 10.7 | 1872.5 | 3335 |  |  |  |  | 0 | 7.25 | 3.75 |  | 1 | [5 empty] | 12 |  | 2085 | 117.93 | 117.93 | 5537.93 | 5537.93 | 0 | Cummulative Cost 38: 1407942.54; EOM Cummulative Cost 39: 130714.47; Combined Cost Per Metre 40: 517.5636; PLOD LINK 41: LINK; Comments 42: rig up, azi line mast shot, site setup, mix muds, drill HWT from surface; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 14; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251014N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-15 05:02 | DS 5am | SF25_DMET045 |  | Wade Thompson | 6 | 780 | 10.7 | 21.6 | 10.9 |  |  | 0 |  |  | 0 |  |  | 0 | 10.9 | 1907.5 | 2530 | 1 | 1 | 1 | 13122 | 750 | 5.5 | 5 |  | 1 |  |  | 0.5 |  | hazard observation training | 12 |  | 2660 | 1359.46 | 579.46 | 7299.46 | 7299.46 | 0.10686 | Cummulative Cost 38: 1415242; EOM Cummulative Cost 39: 138013.93; Combined Cost Per Metre 40: 669.6752; PLOD LINK 41: LINK; Comments 42: Pull Barrel, Open hole with 6-1/2" Roller to 4.5m, Pull Roller, Run and Set PVC Casing, Run Barrel, Core Ahed in broken ground to 17.7m, Pull Barrel, Run PHD Blank, Ream 9m PWT casing, Flush and seat with casing Pac, Pull PHD Blank, Run 3m Standard Barrel, Drill on; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 15; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251015D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-15 17:02 | NS 5pm | SF25_DMET045 |  | Scott O'Hehir | 0 | 0 | 21.6 | 40.8 | 19.2 |  |  | 0 |  |  | 0 |  |  | 0 | 19.2 | 3360 | 3360 |  |  |  |  | 0 | 5.5 | 0.75 | shut down for lightning | 5.25 |  |  | 0.5 |  | hazard observation training | 12 |  | 2235 | 1280.49 | 1280.49 | 6875.49 | 6875.49 | 0 | Cummulative Cost 38: 1422117.49; EOM Cummulative Cost 39: 144889.42; Combined Cost Per Metre 40: 358.0984; PLOD LINK 41: LINK; Comments 42: continue drilling PQ3 from 21.6m, survey 18m, continue coring, very broken, bogged barrel, freed up, tried to continue drilling, barrel locking up in cave in getting back to bottom, pulled out to check bit and barrel, standby lightning. From 1.15 am>EOS; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 15; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251015N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-16 05:02 | DS 5am | SF25_DMET045 |  | Wade Thompson | 6 | 780 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 | 0 | 0 | standby due to overnight rain making access road unusable | 1 | 11 | standby due to overnight rain making access road unusable |  |  |  | 12 |  | 4320 | 780 | 0 | 5850 | 5850 | 0.13333 | Cummulative Cost 38: 1427967.49; EOM Cummulative Cost 39: 150739.42; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: Standby, No Access in to site from Doon Doon Roadhouse due to rain event.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 16; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251016D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-16 17:02 | NS 5pm | SF25_DMET045 |  | Scott O'Hehir | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | standby due to overnight rain making access road unusable | 1 | 11 | standby due to overnight rain making access road unusable |  |  |  | 12 |  | 4320 | 0 | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1432287.49; EOM Cummulative Cost 39: 155059.42; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: Standby, No Access in to site from Doon Doon Roadhouse due to rain event.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 16; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251016N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-17 05:02 | DS 5am | SF25_DMET045 |  | Wade Thompson | 6 | 780 | 40.8 | 75.6 | 34.8 |  |  | 0 |  |  | 0 |  |  | 0 | 34.8 | 6090 | 6090 | 1 | 1 | 1 | 13122 | 750 | 9.75 | 1.25 |  | 1 | [5 empty] | 12 |  | 935 | 1174.13 | 394.13 | 8949.13 | 8949.13 | 0.087159 | Cummulative Cost 38: 1441236.62; EOM Cummulative Cost 39: 164008.55; Combined Cost Per Metre 40: 257.1589; PLOD LINK 41: LINK; Comments 42: Run Barrel, Core ahead and survey, Poor water return, Pump multiple LCM throughout shift to regain better water return, Some faulted ground.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 17; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251017D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-17 17:02 | NS 5pm | SF25_DMET045 |  | Scott O'Hehir | 0 | 0 | 75.6 | 86.9 | 11.3 |  |  | 0 |  |  | 0 |  |  | 0 | 11.3 | 1977.5 | 1977.5 |  |  |  |  | 0 | 2.5 | 0.75 | offsider fell ill no sufficient crew to perform drilling tasks | 1 |  |  | 6 | 1.75 | service rig and lighting plant | 12 |  | 705 | 138.7 | 138.7 | 2821.2 | 2821.2 | 0 | Cummulative Cost 38: 1444057.82; EOM Cummulative Cost 39: 166829.75; Combined Cost Per Metre 40: 249.6637; PLOD LINK 41: LINK; Comments 42: Continue coring PQ3, Mix muds throughout shift viscosity checks, Offsider fell ill standby, planned maintenance.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 17; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251017N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-18 05:02 | DS 5am | SF25_DMET045 |  | Wade Thompson | 6 | 780 | 86.9 | 113.8 | 26.9 |  |  | 0 |  |  | 0 |  |  | 0 | 26.9 | 4707.5 | 4707.5 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 1036.63 | 256.63 | 7314.13 | 7314.13 | 0.10664 | Cummulative Cost 38: 1451371.95; EOM Cummulative Cost 39: 174143.88; Combined Cost Per Metre 40: 271.9007; PLOD LINK 41: LINK; Comments 42: Core ahead and survey, Poor water return, Pump LCM throughout shift, Ground becoming Hard; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 18; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251018D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-18 17:02 | NS 5pm | SF25_DMET045 |  | Scott O'Hehir | 0 | 0 | 113.8 | 123.9 | 10.1 |  |  | 0 |  |  | 0 |  |  | 0 | 10.1 | 1767.5 | 2415 |  |  |  |  | 0 | 5.25 | 5.75 |  | 1 | [5 empty] | 12 |  | 3005 | 496.2 | 496.2 | 5916.2 | 5916.2 | 0 | Cummulative Cost 38: 1457288.15; EOM Cummulative Cost 39: 180060.08; Combined Cost Per Metre 40: 585.7624; PLOD LINK 41: LINK; Comments 42: flush hole, bombed lc stop to try get water return, Continue coring PQ3, dead bit, bit change, continue coring, drill pulled itself off jack blocks, Mix muds throughout shift viscosity checks, Pull rods bit U/S.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 18; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251018N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-19 05:02 | DS 5am | SF25_DMET045 |  | Wade Thompson | 6 | 780 | 123.9 | 144.6 | 20.7 |  |  | 0 |  |  | 0 |  |  | 0 | 20.7 | 3622.5 | 4255 | 1 | 1 | 1 | 13122 | 750 | 9.25 | 1.5 |  | 1 |  |  | 0.25 |  | toolbox | 12 |  | 1050 | 1036.63 | 256.63 | 7091.63 | 7091.63 | 0.10999 | Cummulative Cost 38: 1464379.78; EOM Cummulative Cost 39: 187151.71; Combined Cost Per Metre 40: 342.5908; PLOD LINK 41: LINK; Comments 42: Run in Barrel, Flush to bottom, Core ahead and survey in Hard broken formation, No water return all shift, Toolbox meeting.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 19; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251019D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-19 17:02 | NS 5pm | SF25_DMET045 |  | Scott O'Hehir | 0 | 0 | 144.6 | 153.6 | 9 |  |  | 0 |  |  | 0 |  |  | 0 | 9 | 1575 | 2070 |  |  |  |  | 0 | 4.5 | 6.25 |  | 1 |  |  | 0.25 |  | toolbox | 12 |  | 3235 | 899.7 | 899.7 | 6204.7 | 6204.7 | 0 | Cummulative Cost 38: 1470584.48; EOM Cummulative Cost 39: 193356.41; Combined Cost Per Metre 40: 689.4111; PLOD LINK 41: LINK; Comments 42: flush hole, drill onto EOH, surveys @144.3 @EOH, EOH HWT rod pull, flush pwt casing, pull pwt casing, rig down, pack up site, rig move between holes.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 19; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251019N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-20 05:02 | DS 5am | SF25_DMET049 |  | Wade Thompson | 6 | 780 | 0 | 13.7 | 13.7 |  |  | 0 |  |  | 0 |  |  | 0 | 13.7 | 2397.5 | 2530 | 1 | 1 | 1 | 13122 | 750 | 5.5 | 5.5 |  | 1 | [5 empty] | 12 |  | 2890 | 1179.04 | 399.04 | 7349.04 | 7349.04 | 0.10614 | Cummulative Cost 38: 1477933.52; EOM Cummulative Cost 39: 200705.45; Combined Cost Per Metre 40: 536.4263; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 20; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251020D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-20 17:02 | NS 5pm | SF25_DMET049 |  | Scott O'Hehir | 0 | 0 | 13.7 | 33.6 | 19.9 |  |  | 0 |  |  | 0 |  |  | 0 | 19.9 | 3482.5 | 3482.5 |  |  |  |  | 0 | 7.25 | 3.75 |  | 1 | [5 empty] | 12 |  | 2085 | 138.7 | 138.7 | 5706.2 | 5706.2 | 0 | Cummulative Cost 38: 1483639.72; EOM Cummulative Cost 39: 206411.65; Combined Cost Per Metre 40: 286.7437; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 20; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251020N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-21 05:02 | DS 5am | SF25_DMET049 |  | Wade Thompson | 6 | 780 | 33.6 | 57.7 | 24.1 |  |  | 0 |  |  | 0 |  |  | 0 | 24.1 | 4217.5 | 4600 | 1 | 1 | 1 | 13122 | 750 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 1392.68 | 612.68 | 7562.68 | 7562.68 | 0.10314 | Cummulative Cost 38: 1491202.4; EOM Cummulative Cost 39: 213974.33; Combined Cost Per Metre 40: 313.8041; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 21; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251021D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-21 17:02 | NS 5pm | SF25_DMET049 |  | Scott O'Hehir | 0 | 0 | 57.7 | 90.6 | 32.9 |  |  | 0 |  |  | 0 |  |  | 0 | 32.9 | 5757.5 | 5757.5 |  |  |  |  | 0 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 504.79 | 504.79 | 7312.29 | 7312.29 | 0 | Cummulative Cost 38: 1498514.69; EOM Cummulative Cost 39: 221286.62; Combined Cost Per Metre 40: 222.2581; PLOD LINK 41: LINK; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 21; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251021N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-22 05:02 | DS 5am | SF25_DMET049 |  | Wade Thompson | 6 | 780 | 90.6 | 95.7 | 5.1 |  |  | 0 |  |  | 0 |  |  | 0 | 5.1 | 892.5 | 1150 | 1 | 1 | 1 | 13122 | 750 | 2.5 | 2 |  | 1 |  |  | 6.5 |  | crew change | 12 |  | 1280 | 1138.7 | 358.7 | 4318.7 | 4318.7 | 0.18061 | Cummulative Cost 38: 1502833.39; EOM Cummulative Cost 39: 225605.32; Combined Cost Per Metre 40: 846.8039; PLOD LINK 41: LINK; Comments 42: Crew Change day, Pre-Shift Meeting, Pre-Start Equipment checks, Flush hole, Core ahead PQ3, Bit change, Run barrel with rod grease, drill on.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 22; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251022D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-22 17:02 | NS 5pm | SF25_DMET049 |  | Scott O'Hehir | 0 | 0 | 95.7 | 125.3 | 29.6 |  |  | 0 |  |  | 0 |  |  | 0 | 29.6 | 5180 | 5180 |  |  |  |  | 0 | 9.75 | 1.25 |  | 1 | [5 empty] | 12 |  | 935 | 256.63 | 256.63 | 6371.63 | 6371.63 | 0 | Cummulative Cost 38: 1509205.02; EOM Cummulative Cost 39: 231976.95; Combined Cost Per Metre 40: 215.2578; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, flush hole, continue coring to survey, drill onto survey, drill on to survey. mix muds and condition hole throughout shift perform periodic viscosity checks.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 22; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251022N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-23 05:02 | DS 5am | SF25_DMET049 |  | Wade Thompson | 6 | 780 | 125.3 | 140.1 | 14.8 |  |  | 0 |  |  | 0 |  |  | 0 | 14.8 | 2590 | 2590 | 1 | 1 | 1 | 13122 | 750 | 5.5 | 5.5 |  | 1 | [5 empty] | 12 |  | 2890 | 1036.63 | 256.63 | 7266.63 | 7266.63 | 0.10734 | Cummulative Cost 38: 1516471.65; EOM Cummulative Cost 39: 239243.58; Combined Cost Per Metre 40: 490.9885; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Flush hole, Core ahead PQ3, to EOH @140.1m, Pull Barrel, Hook up to PWT, PWT stuck Flush and work, Rig move off alignment, Re Set Rig, Work Casing, Free Casing and pull on to Truck, Mast down, Start packing site, line next sump and get filling.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 23; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251023D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-23 17:02 | NS 5pm | SF25_DMET048 |  | Scott O'Hehir | 0 | 0 | 0 | 10.9 | 10.9 |  |  | 0 |  |  | 0 |  |  | 0 | 10.9 | 1907.5 | 1907.5 |  |  |  |  | 0 | 3.75 | 7.25 |  | 1 | [5 empty] | 12 |  | 3695 | 652.21 | 652.21 | 6254.71 | 6254.71 | 0 | Cummulative Cost 38: 1522726.36; EOM Cummulative Cost 39: 245498.29; Combined Cost Per Metre 40: 573.8266; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, finish pack up, rig move , rig up, Azi shot, set up site to drill, drill from surface to 7.9, Pull Barrel, Open hole with 6-1/2" rock Roller to 6m, Pull Roller, Run and Set PVC Casing, Run Barrel, flush to bottom, drill on to end of shift, mix mud condition hole throughout shift.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 23; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251023N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-24 05:02 | DS 5am | SF25_DMET048 |  | Wade Thompson | 6 | 780 | 10.9 | 19.9 | 9 |  |  | 0 |  |  | 0 |  |  | 0 | 9 | 1575 | 3680 | 1 | 1 | 1 | 13122 | 750 | 8 | 3 |  | 1 | [5 empty] | 12 |  | 1740 | 1013.55 | 233.55 | 7183.55 | 7183.55 | 0.10858 | Cummulative Cost 38: 1529909.91; EOM Cummulative Cost 39: 252681.84; Combined Cost Per Metre 40: 798.1722; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Flush hole, Core ahead PQ3 very broken ground, Pull barrel @19.9m, Run PHD casing blank, Ream PWT casing to 18m, Pull Blank, Re cement PVC Casing; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 24; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251024D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-24 17:02 | NS 5pm | SF25_DMET048 |  | Scott O'Hehir | 0 | 0 | 19.9 | 51.7 | 31.8 |  |  | 0 |  |  | 0 |  |  | 0 | 31.8 | 5565 | 5565 |  |  |  |  | 0 | 9 | 2 |  | 1 | [5 empty] | 12 |  | 1280 | 290.49 | 290.49 | 7135.49 | 7135.49 | 0 | Cummulative Cost 38: 1537045.4; EOM Cummulative Cost 39: 259817.33; Combined Cost Per Metre 40: 224.3865; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, run in 3m gear, drill on, survey, drill on, survey, drill on. mix mud condition hole throughout shift. barrel configuration-3m standard O/S fer O/S ber-bit new 7SA-HA91304/7; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 24; Shift Shorthand 47: N; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251024N; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-25 05:02 | DS 5am | SF25_DMET048 |  | Wade Thompson | 6 | 780 | 51.7 | 78.7 | 27 |  |  | 0 |  |  | 0 |  |  | 0 | 27 | 4725 | 4725 | 1 | 1 | 1 | 13122 | 750 | 10.25 | 0.75 |  | 1 | [5 empty] | 12 |  | 705 | 918.7 | 138.7 | 7098.7 | 7098.7 | 0.10988 | Cummulative Cost 38: 1544144.1; EOM Cummulative Cost 39: 266916.03; Combined Cost Per Metre 40: 262.9148; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Flush hole, Core ahead PQ3 Hard Ground Formation.; Stem 43: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-; Year 44: 25; Month 45: 10; Day 46: 25; Shift Shorthand 47: D; Shift Shorthand 48: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-wa/plods/1665-251025D; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-25 17:02 | NS 5pm | SF25_DMET048 |  | Scott O'Hehir | 0 | 0 | 78.7 | 99.7 | 21 |  |  | 0 |  |  | 0 |  |  | 0 | 21 | 3675 | 3675 |  |  |  |  | 0 | 7.5 | 3.5 |  | 1 | [5 empty] | 12 |  | 1970 | 496.2 | 496.2 | 6141.2 | 6141.2 | 0 | Cummulative Cost 38: 1550285.3; EOM Cummulative Cost 39: 273057.23; Combined Cost Per Metre 40: 292.4381; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-26 05:02 | DS 5am | SF25_DMET048 |  | Wade Thompson | 6 | 780 | 99.7 | 112.7 | 13 |  |  | 0 |  |  | 0 |  |  | 0 | 13 | 2275 | 3680 | 1 | 1 | 1 | 13122 | 750 | 8 | 2.75 |  | 1 |  |  | 0.25 |  | Toolbox | 12 |  | 1625 | 1138.7 | 358.7 | 7193.7 | 7193.7 | 0.10843 | Cummulative Cost 38: 1557479; EOM Cummulative Cost 39: 280250.93; Combined Cost Per Metre 40: 553.3615; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Core ahead PQ3 Hard Ground Formation, Pull barrel for bit change, Change Front reamer as was U/S, Run Rods with rod grease, Ream to bottom, Toolbox Meeting at EOS; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-26 17:02 | NS 5pm | SF25_DMET048 |  | Scott O'Hehir | 0 | 0 | 112.7 | 143 | 30.3 |  |  | 0 |  |  | 0 |  |  | 0 | 30.3 | 5302.5 | 5302.5 |  |  |  |  | 0 | 8.5 | 2.25 |  | 1 |  |  | 0.25 |  | Toolbox | 12 |  | 1395 | 220 | 220 | 6917.5 | 6917.5 | 0 | Cummulative Cost 38: 1564396.5; EOM Cummulative Cost 39: 287168.43; Combined Cost Per Metre 40: 228.3003; PLOD LINK 41: LINK; Comments 42: toolbox, Pre-Shift Meeting, Pre-Start Equipment checks, drill on to survey, drill on, survey, drill on, pull out excessive rod chatter, pulled out, back reamer was damaged pads missing, replaced, ran in greased, flushed, drilled on. mix mud condition hole throughout shift. ground conditions-hard-broken barrel configuration-3m blk ber std fer bit- 7-9 PQ3 #356185; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-27 05:02 | DS 5am | SF25_DMET048 |  | Wade Thompson | 6 | 780 | 143 | 156.5 | 13.5 |  |  | 0 |  |  | 0 |  |  | 0 | 13.5 | 2362.5 | 2875 | 1 | 1 | 1 | 13122 | 750 | 6.25 | 2.25 |  | 1 | 2.5 |  |  |  | Lightning standby | 12 |  | 2295 | 918.7 | 138.7 | 6838.7 | 6838.7 | 0.11406 | Cummulative Cost 38: 1571235.2; EOM Cummulative Cost 39: 294007.13; Combined Cost Per Metre 40: 506.5704; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-27 17:02 | NS 5pm | SF25_DMET048 | SF25_DMET047 | Scott O'Hehir | 0 | 0 | 156.5 | 159.6 | 3.1 |  |  | 0 | 0 | 7.8 | 7.8 |  |  | 0 | 10.9 | 1907.5 | 1907.5 |  |  |  |  | 0 | 3.25 | 7.75 |  | 1 | [5 empty] | 12 |  | 3925 | 262.13 | 262.13 | 6094.63 | 6094.63 | 0 | Cummulative Cost 38: 1577329.83; EOM Cummulative Cost 39: 300101.76; Combined Cost Per Metre 40: 559.1404; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-28 05:02 | DS 5am | SF25_DMET047 |  | Wade Thompson | 6 | 780 | 7.8 | 24.7 | 16.9 |  |  | 0 |  |  | 0 |  |  | 0 | 16.9 | 2957.5 | 3680 | 1 | 1 | 1 | 13122 | 750 | 8 | 3 |  | 1 | [5 empty] | 12 |  | 1740 | 2152.6 | 1372.6 | 8322.6 | 8332.6 | 0.093721 | Cummulative Cost 38: 1585652.43; EOM Cummulative Cost 39: 308424.36; Combined Cost Per Metre 40: 492.4615; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Pull barrel, Open hole to 2m with 6-1/2" Roller, insert and set PVC casing, Run 3-7/8" roller to clear hole to 7.8m, Pull Roller, Run PHD casing blank, Ream 6m PWT Casing, Flush with casing pac, Pull PHD Blank, Flush PQ barrel to bottom of hole and core ahead.; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-28 17:02 | NS 5pm | SF25_DMET047 |  | Scott O'Hehir | 0 | 0 | 24.7 | 51.7 | 27 |  |  | 0 |  |  | 0 |  |  | 0 | 27 | 4725 | 4725 |  |  |  |  | 0 | 9.5 | 1.5 |  | 1 | [5 empty] | 12 |  | 1050 | 91.06 | 91.06 | 5866.06 | 5866.06 | 0 | Cummulative Cost 38: 1591518.49; EOM Cummulative Cost 39: 314290.42; Combined Cost Per Metre 40: 217.2615; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, flush hole, drill on, bit change, run it, drill onto survey, drill on to survey, drill on to EOS. mix muds condition hole throughout shift. barrel configuration-3m ovs ber std fer bit- 7-9 PQ3 #356185; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-29 05:02 | DS 5am | SF25_DMET047 |  | Wade Thompson | 6 | 780 | 51.7 | 69.7 | 18 |  |  | 0 | [6 empty] | 18 | 3150 | 3335 | 1 | 1 | 1 | 13122 | 750 | 7.25 | 0.25 |  | 1 | 3.5 | Lightning delay 3.5 hours |  |  |  | 12 |  | 1735 | 1599.93 | 819.93 | 7419.93 | 7419.93 | 0.10512 | Cummulative Cost 38: 1598938.42; EOM Cummulative Cost 39: 321710.35; Combined Cost Per Metre 40: 412.2183; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Core ahead and survey, Shut down for Lightning.; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-29 17:02 | NS 5pm | SF25_DMET047 |  | Scott O'Hehir | 0 | 0 | 69.7 | 99.7 | 30 |  |  | 0 | [6 empty] | 30 | 5250 | 5250 |  |  |  |  | 0 | 10 | 1 |  | 1 | [5 empty] | 12 |  | 820 | 138.7 | 138.7 | 6208.7 | 6208.7 | 0 | Cummulative Cost 38: 1605147.12; EOM Cummulative Cost 39: 327919.05; Combined Cost Per Metre 40: 206.9567; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, flush hole, drill on to survey drill onto survey,drill on to EOS. mix muds condition hole throughout shift.; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-30 05:02 | DS 5am | SF25_DMET047 |  | Wade Thompson | 6 | 780 | 99.7 | 114.3 | 14.6 |  |  | 0 | [6 empty] | 14.6 | 2555 | 3680 | 1 | 1 | 1 | 13122 | 750 | 8 | 1.5 |  | 1 | 1.5 | Lightning delay 1.5 |  |  |  | 12 |  | 1590 | 897.93 | 117.93 | 6917.93 | 6917.93 | 0.11275 | Cummulative Cost 38: 1612065.05; EOM Cummulative Cost 39: 334836.98; Combined Cost Per Metre 40: 473.8308; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Core ahead very hard formation, Bit change to softer matrix bit, Shut down for Lightning.; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-30 17:02 | NS 5pm | SF25_DMET047 |  | Scott O'Hehir | 0 | 0 | 114.3 | 135.7 | 21.4 |  |  | 0 | [6 empty] | 21.4 | 3745 | 3745 |  |  |  |  | 0 | 7.75 | 1.75 |  | 1 | 1.5 | Lightning delay 1.5 |  |  |  | 12 |  | 1705 | 578.7 | 578.7 | 6028.7 | 6028.7 | 0 | Cummulative Cost 38: 1618093.75; EOM Cummulative Cost 39: 340865.68; Combined Cost Per Metre 40: 281.715; PLOD LINK 41: LINK; Comments 42: delay-lightning, Pre-Shift Meeting, Pre-Start Equipment checks, flush hole (no water return), continue coring PQ3, excessive rod chatter, pulled rods, rod greased, ran in, drilled onto survey mix muds condition hole throughout shift. ground conditions-very hard throughout shift,; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-31 05:02 | DS 5am | SF25_DMET047 |  | Wade Thompson | 6 | 780 | 135.7 | 159.7 | 24 |  |  | 0 | [6 empty] | 24 | 4200 | 4830 | 1 | 1 | 1 | 13122 | 750 | 10.5 | 0.5 |  | 1 | [5 empty] | 12 |  | 590 | 897.93 | 117.93 | 7067.93 | 7067.93 | 0.11036 | Cummulative Cost 38: 1625161.68; EOM Cummulative Cost 39: 347933.61; Combined Cost Per Metre 40: 294.4971; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Core ahead very hard formation.; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-10-31 17:02 | NS 5pm | SF25_DMET034 |  | Scott O'Hehir | 0 | 0 | 0 | 0 | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 8.5 |  | 1 | 2.5 | Lightning delay 2.5 |  |  |  | 12 |  | 5170 | 88.08 | 88.08 | 5258.08 | 5258.08 | 0 | Cummulative Cost 38: 1630419.76; EOM Cummulative Cost 39: 353191.69; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, EOH site pack up, pull rods, flush casing free up, pull casing, site pack up, delay lightning, rig move, rig up, mast shot. site set up.; Shift Shorthand 49: 2025-10
M 80/269 | Additional Met | DDMet | 2025-11-01 05:02 | DS 5am | SF25_DMET034 |  | Wade Thompson | 6 | 780 | 0 | 3 | 3 |  |  | 0 | [6 empty] | 3 | 525 | 1380 | 1 | 1 | 1 | 13122 | 750 | 3 | 3.5 |  | 1 | 4.5 | Site evacuation due to fires |  |  |  | 12 |  | 3590 | 780 | 0 | 6500 | 6500 | 0.12 | Cummulative Cost 38: 1636919.76; EOM Cummulative Cost 39: 6500; Combined Cost Per Metre 40: 2166.6667; PLOD LINK 41: LINK; Comments 42: Pre-Shift Meeting, Pre-Start Equipment checks, Mast check shot, Reconnect Polly line to site and start filling sumps, Continue set up site, consult client about local bushfire, Consult DDH1 Operations, Make the call to move humpy and second lighting plant to laydown area, Start drilling from surface, 13.30 notice that fire had come to close for safe operations, Consult Client and DDH1 Operations, Wake up Nightshift and Evacuate site to Doon Doon Roadhouse.; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-01 17:02 | NS 5pm | SF25_DMET034 |  | Scott O'Hehir | 0 | 0 | 3 | 3 | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 |  | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1641239.76; EOM Cummulative Cost 39: 10820; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: No Shift Worked due to bushfire, Crew evacuated to Doon Doon Roadhouse; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-02 05:02 | DS 5am | SF25_DMET034 |  | Wade Thompson | 6 |  | 3 | 3 | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 | 0 | 0 |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 | 0 | 0 | 5070 | 5070 | 0 | Cummulative Cost 38: 1646309.76; EOM Cummulative Cost 39: 15890; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: No Shift Worked crew at Doon Doon Roadhouse. Wade travel to Site with client, Fire still active on site, Travel back to Doon Doon; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-02 17:02 | NS 5pm | SF25_DMET034 |  | Scott O'Hehir | 0 | 0 | 3 | 3 | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 |  | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1650629.76; EOM Cummulative Cost 39: 20210; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: No Shift Worked due to bushfire, Crew evacuated to Doon Doon Roadhouse; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-03 05:02 | DS 5am | SF25_DMET034 |  | Wade Thompson | 6 |  | 3 | 3 | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 | 0 | 0 |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 | 0 | 0 | 5070 | 5070 | 0 | Cummulative Cost 38: 1655699.76; EOM Cummulative Cost 39: 25280; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: No Shift Worked crew at Doon Doon Roadhouse. Wade travel to Site with client, Fire still active on site, Travel back to Doon Doon; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-03 17:02 | NS 5pm | SF25_DMET034 |  | Scott O'Hehir | 0 | 0 | 3 | 3 | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 |  | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1660019.76; EOM Cummulative Cost 39: 29600; Combined Cost Per Metre 40: #DIV/0!; PLOD LINK 41: LINK; Comments 42: No Shift Worked due to bushfire, Crew evacuated to Doon Doon Roadhouse; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-04 05:02 | DS 5am | SF25_DMET034 |  | Wade Thompson | 6 | 780 | 3 | 13.7 | 10.7 |  |  | 0 | [6 empty] | 10.7 | 1872.5 | 2300 | 1 | 1 | 1 | 13122 | 750 | 5 | 2.75 | Awaiting all clear to return to site | 1.75 | 2.5 | Awaiting all clear to return to site |  |  |  | 12 |  | 2795 | 916.05 | 136.05 | 6761.05 | 6761.05 | 0.11537 | Cummulative Cost 38: 1666780.81; EOM Cummulative Cost 39: 36361.05; Combined Cost Per Metre 40: 631.8738; PLOD LINK 41: LINK; Comments 42: Wade travel to Site with client, Fire no longer active threat, Crew travel in to site from Doon Doon, Pre-Shift Meeting, Pre-Start Equipment checks, Re establish water supply due to burnt poly line, Wait for sumps to full, Flush hole and re commence coring, Ream in 3m PWT Casing, Run Barrel and core ahead.; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-04 17:02 | NS 5pm | SF25_DMET034 | [6 empty] | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 12 | no night shift after crew returned from Doon Doon in the morning |  |  |  | 12 |  | 4320 |  |  | 4320 | 4320 |  | Cummulative Cost 38: 1671100.81; EOM Cummulative Cost 39: 40681.05; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no night shift; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-05 05:02 | DS 5am | SF25_DMET034 |  | Scott O'Hehir | 6 | 780 | 13.7 | 27.3 | 13.6 |  |  | 0 | [6 empty] | 13.6 | 2380 | 2760 | 1 | 1 | 1 | 13122 | 750 | 6 | 1.25 | Site evacuation due to fires | 1.75 | 3 | Site evacuation due to fires |  |  |  | 12 |  | 2285 | 1035.43 | 255.43 | 6830.43 | 6830.43 | 0.11419 | Cummulative Cost 38: 1677931.24; EOM Cummulative Cost 39: 47511.48; Combined Cost Per Metre 40: 502.2375; PLOD LINK 41: LINK; Comments 42: pull barrel change configuration, flush and ream in, bombed hole LC stop, continue coring PQ, delay water sumps empty no water return. continue coring, standby bush fires.; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-05 17:02 | NS 5pm | SF25_DMET034 |  | Carl Jonas |  |  |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 |  |  | 4320 | 4320 |  | Cummulative Cost 38: 1682251.24; EOM Cummulative Cost 39: 51831.48; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no night shift; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-06 05:02 | DS 5am | SF25_DMET034 |  | Scott O'Hehir | 6 | 780 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 |  |  |  |  | 12 | No drilling due to bushfires on site |  |  |  | 12 |  | 4320 |  | -780 | 5070 | 5070 | 0.15385 | Cummulative Cost 38: 1687321.24; EOM Cummulative Cost 39: 56901.48; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: No Shift Worked due to bushfire, Crew evacuated to Doon Doon Roadhouse; Shift Shorthand 49: 2025-11
M 80/269 | Additional Met | DDMet | 2025-11-06 17:02 | NS 5pm | SF25_DMET034 |  | Carl Jonas |  |  | 27.3 | 40 | 12.7 |  |  | 0 | [6 empty] | 12.7 | 2222.5 | 4370 |  |  |  |  | 0 | 9.5 | 1 |  |  |  |  | 1.5 |  | travel back to site | 12 |  | 460 |  |  | 4830 | 4830 |  | Cummulative Cost 38: 1692151.24; EOM Cummulative Cost 39: 61731.48; Combined Cost Per Metre 40: 380.315; PLOD LINK 41: LINK; Comments 42: continue drilling pq3/ survey eoh @36m/ end of hole was 40m; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-07 05:02 | DS 5am | SF25_DMET032 |  | Scott O'Hehir | 5 | 650 | 0 | 1.6 | 1.6 |  |  | 0 | [6 empty] | 1.6 | 280 | 280 | 1 | 1 | 1 | 13122 | 750 | 0.5 | 6 |  | 1 | 3.5 | Lightning delay | 1 |  | travel back to site | 12 |  | 4380 | 767.93 | 117.93 | 6177.93 | 6177.93 | 0.10521 | Cummulative Cost 38: 1698329.17; EOM Cummulative Cost 39: 67909.41; Combined Cost Per Metre 40: 3861.2063; PLOD LINK 41: LINK; Comments 42: site pack up, pull rods, pull casing, rig down, rig move, rig up, survey, mast shot, site setup, delay lightning from 11; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-07 17:02 | NS 5pm | SF25_DMET032 |  | Carl Jonas | 0 | 0 | 1.6 | 5.4 | 3.8 |  |  | 0 | [6 empty] | 3.8 | 665 | 920 |  |  |  |  | 0 | 2 | 4.5 |  | 1 | 4.5 | Lightning delay |  |  |  | 12 |  | 4050 | 395.85 | 395.85 | 5365.85 | 5365.85 | 0 | Cummulative Cost 38: 1703695.02; EOM Cummulative Cost 39: 73275.26; Combined Cost Per Metre 40: 1412.0658; PLOD LINK 41: LINK; Comments 42: continue drilling pq3/ standby lightning/ / rock roll hole/ PVC ream PWT unsuccessful due to ground conditions; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-08 05:02 | DS 5am | SF25_DMET032 |  | Scott O'Hehir | 5 | 650 | 5.4 | 30 | 24.6 |  |  | 0 | [6 empty] | 24.6 | 4305 | 4305 | 1 | 1 | 1 | 13122 | 750 | 7.25 | 3.75 |  | 1 | [5 empty] | 12 |  | 2085 | 650 | 0 | 7790 | 7790 | 0.08344 | Cummulative Cost 38: 1711485.02; EOM Cummulative Cost 39: 81065.26; Combined Cost Per Metre 40: 316.6667; PLOD LINK 41: LINK; Comments 42: continue coring PQ3, pulled out change front reamer, reamed in and flushed, continue coring, survey 18M, continue coring to EOH, survey, EOH pull rods, move rod bench, rig down, move back, rig up, mast shot, set up site,; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-08 17:02 | NS 5pm | SF25_DMET051 |  | Carl Jonas | 0 | 0 | 0 | 12.5 | 12.5 |  |  | 0 | [6 empty] | 12.5 | 2187.5 | 2760 |  |  |  |  | 0 | 6 | 2 |  | 1 | 3 | Lightning delay |  |  |  | 12 |  | 2360 | 117.93 | 117.93 | 5237.93 | 5237.93 | 0 | Cummulative Cost 38: 1716722.95; EOM Cummulative Cost 39: 86303.19; Combined Cost Per Metre 40: 419.0344; PLOD LINK 41: LINK; Comments 42: drilling pq3 SOH/ standby lightning/ / ream PWT casing/ barrel change/ continue drilling PQ3; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-09 05:02 | DS 5am | SF25_DMET051 |  | Scott O'Hehir | 5 | 650 | 12.5 | 30 | 17.5 |  |  | 0 | [6 empty] | 17.5 | 3062.5 | 3680 | 1 | 1 | 1 | 13122 | 750 | 8 | 2 |  | 1 | 1 |  |  |  |  | 12 |  | 1640 | 650 | 0 | 6720 | 6720 | 0.096726 | Cummulative Cost 38: 1723442.95; EOM Cummulative Cost 39: 93023.19; Combined Cost Per Metre 40: 384; PLOD LINK 41: LINK; Comments 42: continue coring PQ3, survey, drill on to EOH, EOH survey, pull rods, pull out PWT, pack up site; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-09 17:02 | NS 5pm | SF25_DMET051 |  | Carl Jonas | 0 | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [6 empty] | 12 |  |  | 12 |  | 0 |  | 0 | 0 |  |  | Cummulative Cost 38: 1723442.95; EOM Cummulative Cost 39: 93023.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: NO NIGHT SHIFT, crew swapping back to days for demob; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-10 05:02 | DS 5am | SF25_DMET051 |  | Scott O'Hehir | 5 | 650 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 |  |  |  | 12 |  | commence pack up and demob |  |  |  | 12 |  | 4320 | 650 | 0 | 5720 | 5720 | 0.11364 | Cummulative Cost 38: 1729162.95; EOM Cummulative Cost 39: 98743.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: pack up for demobilize; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-10 17:02 | NS 5pm | SF25_DMET051 | [6 empty] | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1729162.95; EOM Cummulative Cost 39: 98743.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: no night shift; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-11 05:02 | DS 5am | SF25_DMET051 |  | Scott O'Hehir | 5 | 650 |  |  | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 13122 | 750 |  |  |  | 12 |  | pack up drive caravans to Kununurra |  |  |  | 12 |  | 4320 | 650 | 0 | 5720 | 5720 | 0.11364 | Cummulative Cost 38: 1734882.95; EOM Cummulative Cost 39: 104463.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: pack up for demobilize, trips into kununnara; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-11 17:02 | NS 5pm | SF25_DMET051 | [6 empty] | 0 |  |  | 0 | [6 empty] | 0 | 0 | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1734882.95; EOM Cummulative Cost 39: 104463.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-12 05:02 | DS 5am | SF25_DMET051 |  | Scott O'Hehir | 5 | 650 |  |  | 0 | [11 empty] | 0 | 1 | 1 | 1 | 13122 | 750 |  |  |  | 12 |  | continue site pack up |  |  |  | 12 |  | 4320 | 650 | 0 | 5720 | 5720 | 0.11364 | Cummulative Cost 38: 1740602.95; EOM Cummulative Cost 39: 110183.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: continue pack up; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-12 17:02 | NS 5pm | SF25_DMET051 | [6 empty] | 0 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1740602.95; EOM Cummulative Cost 39: 110183.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-13 05:02 | DS 5am | SF25_DMET051 |  | Scott O'Hehir | 5 | 650 |  |  | 0 | [11 empty] | 0 | 1 | 1 | 1 | 13122 | 750 |  |  |  | 4 |  |  | 8 |  |  | 12 |  | 1440 | 650 | 0 | 2840 | 2840 | 0.22887 | Cummulative Cost 38: 1743442.95; EOM Cummulative Cost 39: 113023.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: tried to get back to site, couldn't make it through in truck got through in LV cleaned up site, did a dump run to town, unpacked some gear in kununnara and loaded onto hino; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-13 17:02 | NS 5pm | SF25_DMET051 | [6 empty] | 0 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  |  | 0 |  |  | Cummulative Cost 38: 1743442.95; EOM Cummulative Cost 39: 113023.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-14 05:02 | DS 5am | SF25_DMET051 |  | Scott O'Hehir | 5 | 650 |  |  | 0 | [11 empty] | 0 | 1 | 1 | 1 | 13122 | 750 |  | 5 | tramming rig off-site | 4 |  |  | 3 |  |  | 12 |  | 3740 | 650 | 0 | 5140 | 5140 | 0.12646 | Cummulative Cost 38: 1748582.95; EOM Cummulative Cost 39: 118163.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: commenced tramming rig, delay due to lightning; Shift Shorthand 49: 2025-11
M 80/268 | Additional Met | DDMet | 2025-11-14 17:02 | NS 5pm | SF25_DMET051 |  |  | 0 | 0 |  |  | 0 | [11 empty] | 0 |  |  |  |  | 0 | [9 empty] | 0 |  | 0 |  | 0 | 0 |  |  | Cummulative Cost 38: 1748582.95; EOM Cummulative Cost 39: 118163.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-15 05:02 | DS 5am | SF_Tramming |  | Scott O'Hehir | 0 | 0 |  |  | 0 | [11 empty] | 0 |  |  |  |  | 0 |  | 5 | tramming rig off-site | 6 |  | Site evacuation due to flooded road | 1 |  |  | 12 |  | 4460 | 0 | 0 | 4460 | 4460 | 0 | Cummulative Cost 38: 1753042.95; EOM Cummulative Cost 39: 122623.19; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: site travel, trammed 7km , standby client lots of rain no access on the tracks.; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-15 17:02 | NS 5pm | SF_Tramming |  | Carl Jonas | 0 | 0 |  |  | 0 | [11 empty] | 0 |  |  |  |  | 0 |  |  |  | 12 |  | standby due to rain making access road unusable |  |  |  | 12 |  | 4320 | 6757.31 | 6757.31 | 11077.31 | 11077.31 | 0 | Cummulative Cost 38: 1764120.26; EOM Cummulative Cost 39: 133700.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: standby client lots of rain no access on the tracks. Flights and Freight added to consumables; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-16 05:02 | DS 5am | SF_Tramming |  | Scott O'Hehir | 0 | 0 |  |  | 0 | [11 empty] | 0 | [8 empty] | 12 | [5 empty] | 12 |  | 4320 | 0 | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1768440.26; EOM Cummulative Cost 39: 138020.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: standby client lots of rain no access on the tracks.; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-16 17:02 | NS 5pm | SF_Tramming |  | Carl Jonas | 0 | 0 |  |  | 0 | [11 empty] | 0 | [8 empty] | 12 | [5 empty] | 12 |  | 4320 | 0 | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1772760.26; EOM Cummulative Cost 39: 142340.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: standby client lots of rain no access on the tracks.; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-17 05:02 | DS 5am | SF_Tramming |  | Scott O'Hehir | 0 | 0 |  |  | 0 | [11 empty] | 0 | [8 empty] | 12 | [5 empty] | 12 |  | 4320 | 0 | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1777080.26; EOM Cummulative Cost 39: 146660.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: pre-shift, prestart equipment, standby no access dove out morning, and river was too high to cross, went out in the afternoon and river was better.; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-17 17:02 | NS 5pm | SF_Tramming |  | Carl Jonas | 0 | 0 |  |  | 0 | [11 empty] | 0 | [8 empty] | 12 | [5 empty] | 12 |  | 4320 | 0 | 0 | 4320 | 4320 | 0 | Cummulative Cost 38: 1781400.26; EOM Cummulative Cost 39: 150980.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: pre-shift, prestart equipment, standby client lots of rain no access on the tracks.; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-18 05:02 | DS 5am | SF_Tramming |  | Scott O'Hehir | 0 | 0 |  |  | 0 | [11 empty] | 0 | [6 empty] | 11 |  | 1 | [5 empty] | 12 |  | 5420 | 0 | 0 | 5420 | 5420 | 0 | Cummulative Cost 38: 1786820.26; EOM Cummulative Cost 39: 156400.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-18 17:02 | NS 5pm | SF_Tramming |  | Carl Jonas | 0 | 0 |  |  | 0 | [11 empty] | 0 | [6 empty] | 10 |  | 1 |  |  | 1 |  | crew change | 12 |  | 4960 |  | 0 | 4960 | 4960 | 0 | Cummulative Cost 38: 1791780.26; EOM Cummulative Cost 39: 161360.5; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: pre-shift, prestart equipment, tramming; Shift Shorthand 49: 2025-11
#N/A | Tramming To DoonDoon | Null | 2025-11-19 05:02 | DS 5am | SF_Tramming |  | Wade Thompson | 0 | 0 | [14 empty] | 0 | [6 empty] | 6.5 |  | 1 |  |  | 4.5 |  | crew change | 12 |  | 3350 | 7130.71 | 7130.71 | 10480.71 | 10480.71 | 0 | Cummulative Cost 38: 1802260.97; EOM Cummulative Cost 39: 171841.21; Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Crew fly in and drive to site, Pre-shift, Prestart equipment, Continue tramming rig towards Doon Doon Roadhouse, Load Rig on to MDM float towards the end of the day, Float Rig remaining 15km. Consumables incl flights and freight; Shift Shorthand 49: 2025-11
#N/A | End of program | [37 empty] | 0
0
0
0
[39 empty] | 0 |  | 0 |  | 0 | #REF! |  |  | Combined Cost Per Metre 40: no drilling completed; PLOD LINK 41: LINK; Comments 42: Travel Kununurra to Daly Waters
[39 empty] | 0 |  | 0 |  | 0
[39 empty] | 0 |  | 0 |  | 0
[39 empty] | 0 |  | 0 |  | 0
[39 empty] | 0 |  | 0
Note on P2: Thomas Pilote: Won't charge us extra for the triple tube
Note on V2: Thomas Pilote: Won't charge us extra for the triple tube
Note on AO2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NEW Column, please fill
Note on Y3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: make sure you fill down. check the cost against coreplan.
Note on AT10: Thomas Pilote: PQ TOOL WAS NOT INCLUDED HENCE DISPARITY EVERY DS
Note on AH13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ensure you seperate out inactive hours (ie non drilling but productive) vs standby (ie non drilling and unproductive)
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Stephen Walsh The cut sheet says there should be 6 people under accom we are getting charged 7. Please advise.
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think we should change the hole ID to SPF for when we drill at Sandover
Note on AI21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Matthew Draddy What is this standby for? Hole move at night? Please fill out corresponding column
Note on AI37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Stephen Walsh @Jeremy Simpson This 6 hours relate to standby due to no rig moves at night? Is this a new condition I was not aware of? Are we able to move rig at night if all controls (i.e. lighting) are inplace? Reply: @Matthew Draddy can you provide clarity on this?
Note on AI41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @George Manton @Matthew Draddy Please provide clarity here
Note on F42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Felix Moore Please get familiar with this tracker and fill out to align with Core plan. Link to CP in column AQ. Let me know if you have trouble with access.
Note on AT103: Thomas Pilote: Ignore please, spread the cost across rows for cost of PQ tooling
Note on Y141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rate changes to $150/m past 200m
Note on Y142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rate changes to $150/m past 200m

## STR RIG 18
[9 empty] | Accom | 35758 | [9 empty] | 632806.75 | [12 empty] | 44030 | 87230 | 205591 |  | 212295.46 | 1217660.21 |  |  |  | 86.4059 |  | Productivity metric Average
|  | RIG 18 |  | Holes Completed: |  |  | 115 |  |  | Drill Costs | [32 empty] | EXT | 78.2267
|  |  |  | Hole 1 | Hole 2 | Hole 3 | Hole 4 |  |  | 130 | 40 | 45 | 50 | 55 | 60 | 65 | 185.4211 |  | 575 |  | 110 | 110 | 175 | 420 | 575 | 575 | 360 | 360 | 0 | [8 empty] | 15032.4964 |  |  |  |  | INF | 84.5753
| Purpose | Hole Purpose | Date | Hole ID | Hole ID | Hole ID | Hole ID | Driller Name | Personel (incl driller) | Accom Cost | 0-50m | 50m-100m | 100m-150m | 150m-200m | 200m-250m | 250m-300m | Total Daily Meters | Drilling Cost | Drill Time | Charged Drilling Cost | Booster (p/hr) | Aux Compressor (p/hr) | Azi Aligner (p/day) | Gyro (p/day) | Drill Time | Active Rate Total hours | Inactive Total | Standby Total Hours | non-charged Hours | Maintenance | Total (Fix if not 12hrs) | Comment | Total Tooling Cost | Total Auxillary Equipment Cost | Total Activity hours Cost | ***Insert Total Consumable Costs*** | Total Consumables Cost (-Accom) | Total Costs | Plod Cost Comparison |  | 28.76% | Cummulative Cost | EOM Cummulative Cost | Combined Cost Per Metre | Provide context on Maintenance | PLOD LINK | Comments
|  | Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | 23 | 24 | 25 | [6 empty] | 26 |  | 27 | 28 |  |  |  | 29 | 30 | 31 |  | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
#N/A |  | INF | 2025-06-22 |  |  |  |  | Tim Leaman | [10 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 9.5 | 2 |  | 0.5 |  | 12 |  | 0 | 0 | 6182.5 |  |  | 6182.5 | 6182.5 | 0 | 100% | 6182.5 | 6182.5 | No drilling completed today, if maintenance provide context ->
#N/A |  | INF | 2025-06-23 |  |  |  |  | Tim Leaman | 3 | 390 | [9 empty] | 0 |  |  |  |  | 0 | 7.75 |  |  | 4.25 |  | 12 |  | 0 | 0 | 4456.25 |  |  | 4846.25 | 4846.25 | 390 | 91.95% | 11028.75 | 11028.75 | No drilling completed today, if maintenance provide context -> |  | Comments 41: 88.4749
M 80/268 | A Vein RC | INF | 2025-06-24 | SF25_RCRD027 |  |  |  | Tim Leaman | 3 | 390 | 46 | [5 empty] | 46 | 1840 | 3.25 | 1868.75 | 2 | 2 | 1 | 1 | 3.25 | 8 |  | 0.5 | 0.25 |  | 12 |  | 595 | 440 | 4780 |  | 444.97 | 8518.72 | 8518.72 | 3298.72 | 61.28% | 19547.47 | 19547.47 | 185.1896 |  | PLOD LINK 32: LINK; Comments 33: water intersected @ 6m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 24; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250624D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-06-25 | SF25_RCRD027 | SF25_RCRD028 |  |  | Tim Leaman | 3 | 390 | 54 | 46 |  |  |  |  | 100 | 4230 | 6.5 | 4230 | 5 | 5 | 1 | 1 | 6.5 | 2.5 | 0.75 |  | 2.25 |  | 12 |  | 595 | 1100 | 1707.5 |  | 444.97 | 8467.47 | 8467.47 | 5659.97 | 33.16% | 28014.94 | 28014.94 | 84.6747 |  | PLOD LINK 32: LINK; Comments 33: water intersected @ 6m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 25; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250625D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-06-26 | SF25_RCRD028 | SF25_RCRD029 |  |  | Tim Leaman | 3 | 390 | 50 | 62 | 48 |  |  |  | 160 | 7190 | 4.75 | 7190 | 6 | 6 | 1 | 1 | 4.75 | 2.5 | 1.25 |  | 3.5 |  | 12 |  | 595 | 1320 | 1887.5 |  | 1396.82 | 12779.32 | 12779.32 | 9571.82 | 25.1% | 40794.26 | 40794.26 | 79.8708 |  | PLOD LINK 32: LINK; Comments 33: ground water intersected at 6m Maintenance- track maintenance on rig walker (2.75hrs); Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 26; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250626D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-06-27 | SF25_RCRD030 | SF25_RCRD031 |  |  | Tim Leaman | 3 | 390 | 100 | 58 | 48 |  |  |  | 206 | 9010 | 7 | 9010 | 6 | 6 | 1 | 1 | 7 | 3.5 | 0.25 |  | 1.25 |  | 12 |  | 595 | 1320 | 2102.5 |  | 798.37 | 14215.87 | 14215.87 | 10793.37 | 24.08% | 55010.13 | 55010.13 | 69.0091 |  | PLOD LINK 32: LINK; Comments 33: SF25_RCRD058 ground water intersected at 6m SF25_RCRD060 ground water intersected at 5m Maintenance-finish off track maintenance on rig walker (0.5hrs); Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 27; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250627D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-06-28 | SF25_RCRD032 | SF25_RCRD033 | SF25_RCRD034 |  | Tim Leaman | 3 | 390 | 138 | 50 |  |  |  |  | 188 | 7770 | 5.75 | 7770 | 5 | 5 | 1 | 1 | 5.75 | 3.5 | 2 |  | 0.75 |  | 12 |  | 595 | 1100 | 2732.5 |  | 1125.57 | 13713.07 | 13713.07 | 9880.57 | 27.95% | 68723.2 | 68723.2 | 72.9419 |  | PLOD LINK 32: LINK; Comments 33: SF25_RCRD061 ground water intersected at 50m SF25_RCRD062 ground water intersected at 5m , inspected and signed off next 10 drill pads with client; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 28; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250628D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-06-29 | SF25_RCRD034 | SF25_RCRD035 | SF25_RCRD036 |  | Tim Leaman | 3 | 390 | 106 | 58 | 48 |  |  |  | 212 | 9250 | 7.25 | 9250 | 6 | 6 | 1 | 1 | 7.25 | 2.75 | 1 | 0.25 | 0.75 |  | 12 |  | 595 | 1320 | 2031.25 | 59214.69 | 58824.69 | 72410.94 | 72410.94 | 69059.69 | 4.628% | 141134.14 | 141134.14 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 29; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250629D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-06-30 | SF25_RCRD036 | SF25_RCRD037 |  |  | Tim Leaman | 3 | 390 | 54 | 100 | 27 |  |  |  | 181 | 8010 | 7.25 | 8010 | 7 | 7 | 1 | 1 | 7.25 | 2.75 | 1.25 |  | 0.75 |  | 12 |  | 595 | 1540 | 2031.25 |  | 613.68 | 13179.93 | 13179.93 | 9608.68 | 27.1% | 154314.07 | 154314.07 | 72.8173 |  | PLOD LINK 32: LINK; Comments 33: SF25_RCRD066 ground water intersected at 52m Bulk water intersected at 72m SF25_RCRD066 unable to contain water and sample turned wet inform client and end of hole was called; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 06; Comments 37: 30; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250630D; Comments 40: 2025-06
M 80/268 | A Vein RC | INF | 2025-07-01 | SF25_RCRD038 | SF25_RCRD039 |  |  | Tim Leaman | 4 | 520 | 98 | 50 |  |  |  |  | 148 | 6170 | 4.5 | 6170 | 2 | 2 | 1 | 1 | 4.5 | 2 | 0.75 | 0 | 4.75 |  | 12 |  | 595 | 440 | 1420 |  | 798.37 | 9943.37 | 9943.37 | 8083.37 | 18.71% | 164257.44 | 9943.37 | 67.1849 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 01; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250701D; Comments 40: 2025-07
M 80/268 | A Vein RC | INF | 2025-07-02 | SF25_RCRD039 | SF25_RCRD081 | SF25_RCRD082 |  | Tim Leaman | 4 | 520 | 100 | 52 | 35 |  |  |  | 187 | 8090 | 6.5 | 8090 | 7 | 7 | 1 | 1 | 6.5 | 3.25 | 1.5 |  | 0.75 |  | 12 |  | 595 | 1540 | 2408.75 |  | 798.37 | 13952.12 | 13952.12 | 10003.37 | 28.3% | 178209.56 | 23895.49 | 74.6103 |  | PLOD LINK 32: LINK; Comments 33: SF25-RCRD081 ground water intersection at 28m SF25-RCRD082 ground water intersection 34m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 02; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250702D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-07-03 | SF25_RCRD083 | SF25_RCRD084 |  |  | Tim Leaman | 4 | 520 | 100 | 58 | 42 |  |  |  | 200 | 8710 | 6 | 8710 | 7 | 7 | 1 | 1 | 6 | 2.75 | 0.75 |  | 2.5 |  | 12 |  | 595 | 1540 | 1851.25 |  | 798.37 | 14014.62 | 14014.62 | 10623.37 | 24.2% | 192224.18 | 37910.11 | 70.0731 |  | PLOD LINK 32: LINK; Comments 33: Plod rejected due to accomodation cost not matching people on site - SF25-RCRD082 ground water intersection 34m SF25_RCRC083 ground water intersection at 76m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 03; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250703D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-07-04 | SF25_RCRD084 |  |  |  | Hugh Reynolds | 4 | 520 |  | 42 | 30 |  |  |  | 72 | 3390 | 5 | 3390 | 4 | 4 | 1 | 1 | 5 | 0.25 | 0 |  | 6.75 |  | 12 |  | 595 | 880 | 143.75 |  | 143.97 | 5672.72 | 5672.72 | 4648.97 | 18.05% | 197896.9 | 43582.83 | 78.7878 |  | PLOD LINK 32: LINK; Comments 33: 6 hours breakdown; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 04; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250704D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-07-05 | SF25_RCRD084 | SF25_RCRD085 |  |  | Hugh Reynolds | 3 | 390 | 50 | 14 | 20 | 34 |  |  | 118 | 5500 | 5.25 | 5500 | 5 | 5 | 1 | 1 | 5.25 | 4 | 1.5 | 0 | 1.25 |  | 12 |  | 595 | 1100 | 2840 |  | 613.68 | 11038.68 | 11038.68 | 7098.68 | 35.69% | 208935.58 | 54621.51 | 93.5481 |  | PLOD LINK 32: LINK; Comments 33: Spent a lot of active time due to hitting bulk water; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 05; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250705D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-07-06 | SF25_RCRD086 | SF25_RCRD087 |  |  | Hugh Reynolds | 3 | 390 | 100 | 100 | 42 |  |  |  | 242 | 10600 | 6.75 | 10600 | 6 | 6 | 1 | 1 | 6.75 | 3.5 | 1 |  | 0.75 |  | 12 |  | 595 | 1320 | 2372.5 |  | 798.37 | 16075.87 | 16075.87 | 12383.37 | 22.97% | 225011.45 | 70697.38 | 66.4292 |  | PLOD LINK 32: LINK; Comments 33: Active time being charged at higher rate than listed on this sheet - follow up; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 06; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250706D; Comments 40: 2025-07
M 80/268 | Infill | EXT | 2025-07-07 | SF25_RCRD088 |  |  |  | Hugh Reynolds | 3 | 390 | 50 | 50 | 50 | 40 |  |  | 190 | 8950 | 6 | 8950 | 5 | 5 | 1 | 1 | 6 | 1.75 | 1.75 |  | 2.5 |  | 12 |  | 595 | 1100 | 1636.25 |  | 613.68 | 13284.93 | 13284.93 | 10548.68 | 20.6% | 238296.38 | 83982.31 | 69.9207 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 07; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250707D; Comments 40: 2025-07
M 80/268 | Infill | EXT | 2025-07-08 | SF25_RCRD088 |  |  |  | Hugh Reynolds | 3 | 390 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 2.5 | 0 |  | 9.5 |  | 12 |  | 595 | 0 | 1437.5 |  | 0 | 2422.5 | 2422.5 | 985 | 59.34% | 240718.88 | 86404.81 | No drilling completed today, if maintenance provide context -> | repair slipped drill rig track | PLOD LINK 32: LINK; Comments 33: Maintenance- repair slipped drill rig track.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 08; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250708D; Comments 40: 2025-07
M 80/268 | Infill | EXT | 2025-07-09 | SF25_RCRD088 |  |  |  | Hugh Reynolds | 3 | 390 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0.5 | 0.5 |  | 11 |  | 12 |  | 595 | 0 | 467.5 |  | 0 | 1452.5 | 1452.5 | 985 | 32.19% | 242171.38 | 87857.31 | No drilling completed today, if maintenance provide context -> |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 09; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250709D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-10 | SF25_RCRD002 |  |  |  | Hugh Reynolds | 3 | 390 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0.5 | 0 |  | 11.5 |  | 12 |  | 595 | 0 | 287.5 |  |  | 1272.5 | 1272.5 | 985 | 22.59% | 243443.88 | 89129.81 | No drilling completed today, if maintenance provide context -> |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 10; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250710D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-11 | SF25_RCRD002 | SF25_RCRD001 |  |  | Hugh Reynolds | 3 | 390 | 96 | 50 | 6 | 0 |  |  | 152 | 6390 | 6.5 | 6390 | 7 | 7 | 1 | 1 | 6.5 | 3.25 | 0.5 |  | 1.75 |  | 12 |  | 595 | 1540 | 2048.75 |  | 798.37 | 11762.12 | 11762.12 | 8173.37 | 30.51% | 255206 | 100891.93 | 77.3824 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 11; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250711D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-12 | SF25_RCRD001 | SF25_RCRD005 | SF25_RCRD004 |  | Hugh Reynolds | 3 | 390 | 90 | 20 | 36 |  |  |  | 146 | 6300 | 5.5 | 6300 | 6 | 6 | 1 | 1 | 5.5 | 4.25 | 1.5 |  | 0.75 |  | 12 |  | 595 | 1320 | 2983.75 |  | 798.37 | 12387.12 | 12387.12 | 8083.37 | 34.74% | 267593.12 | 113279.05 | 84.8433 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 12; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250712D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-13 | SF25_RCRD004 | SF25_RCRD003 |  |  | Hugh Reynolds | 3 | 390 | 50 | 74 | 30 |  |  |  | 154 | 6830 | 6 | 6830 | 8 | 8 | 1 | 1 | 6 | 3.5 | 1.75 |  | 0.75 |  | 12 |  | 595 | 1760 | 2642.5 |  | 471.17 | 12688.67 | 12688.67 | 8286.17 | 34.7% | 280281.79 | 125967.72 | 82.394 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 13; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250713D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-14 | SF25_RCRD006 | SF25_RCRD007 |  |  | Hugh Reynolds | 3 | 390 | 96 | 44 |  |  |  |  | 140 | 5820 | 3.75 | 5820 | 6 | 6 | 1 | 1 | 3.75 | 4.5 | 0.75 |  | 3 |  | 12 |  | 595 | 1320 | 2857.5 |  | 798.37 | 11780.87 | 11780.87 | 7603.37 | 35.46% | 292062.66 | 137748.59 | 84.1491 |  | PLOD LINK 32: LINK; Comments 33: SF25_RCRD006 no water intersection. SF25_RCRD007 water intersection at 34m and another heavy water table at 66m Maintenance- swap out hydraulic pump.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 14; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250714D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-15 | SF25_RCRD008 |  |  |  | Hugh Reynolds | 4 | 520 | 50 | 50 | 24 |  |  |  | 124 | 5450 | 4.5 | 5450 | 6 | 6 | 1 | 1 | 4.5 | 3 | 1 |  | 3.5 |  | 12 |  | 595 | 1320 | 2085 |  | 6069.4 | 16039.4 | 16039.4 | 12634.4 | 21.23% | 308102.06 | 153787.99 | 129.35 |  | PLOD LINK 32: LINK; Comments 33: SF25_RCRD008 water intersection at 22m Maintenance- on going maintenance regarding hydraulics and replace sample hose.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 15; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250715D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-16 | SF25_RCRD009 |  |  |  | Hugh Reynolds | 3 | 390 | 46 | [5 empty] | 46 | 1840 | 1.25 | 1840 | 0 | 0 | 1 | 1 | 1.25 | 4.25 | 0.25 |  | 6.25 |  | 12 |  | 595 | 0 | 2533.75 | 1017.37 | 627.37 | 5986.12 | 5986.12 | 3452.37 | 42.33% | 314088.18 | 159774.11 | 130.133 |  | PLOD LINK 32: LINK; Comments 33: Clean up fuel spill and write up witness statements in the morning. Maintenance - Fitter onsite to assist in diagnosing AUX pump function issues. SF25_RCRC009 - Groundwater from 22m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 16; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250716D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-17 | SF25_RCRD010 | SF25_RCRD011 |  |  | Kane Barton | 3 | 390 | 60 | 50 | 40 |  |  |  | 150 | 6650 | 3.5 | 6650 | 4 | 4 | 1 | 1 | 3.5 | 5.25 | 0.75 |  | 0.75 | 1.75 | 12 | Planned maintenance | 595 | 880 | 3288.75 |  | 548.31 | 12352.06 | 12352.06 | 8183.31 | 33.75% | 326440.24 | 172126.17 | 82.3471 |  | PLOD LINK 32: LINK; Comments 33: RC010- Groundwater from 22M, Sump filled at 70M. Active work rate allocated to setting up & pumping sump to allow drilling to continue. Maintenance- Cyclone knuckle plate repaired, Breakout solenoids replaced, Hydralic oil drained.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 17; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250717D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-18 | SF25_RCRD011 | SF25_RCRD012 | SF25_RCRD013 |  | Kane Barton | 3 | 390 | 136 | 64 |  |  |  |  | 200 | 8320 | 5 | 8320 | 5 | 5 | 1 | 1 | 5 | 3.25 | 0.75 |  | 3 |  | 12 |  | 595 | 1100 | 2138.75 | 1685.3 | 1295.3 | 13839.05 | 13839.05 | 10600.3 | 23.4% | 340279.29 | 185965.22 | 69.1953 |  | PLOD LINK 32: LINK; Comments 33: RC11 - Groundwater from 40M RC12- Groundwater from 22m, increasing significantly from 60M RC13- Groundwater from 22M, increasing from 50M 3200L diesel taken from fuel farm.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 18; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250718D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-19 | SF25_RCRD013 | SF25_RCRD014 | SF25_RCRD015 | SF25_RCRD016 | Kane Barton | 3 | 390 | 106 | 74 | 36 |  |  |  | 216 | 9370 | 4 | 9370 | 5 | 5 | 1 | 1 | 4 | 5.5 | 2 |  | 0.5 |  | 12 |  | 595 | 1100 | 3882.5 |  | 759.2 | 16096.7 | 16096.7 | 11114.2 | 30.95% | 356375.99 | 202061.92 | 74.5218 |  | PLOD LINK 32: LINK; Comments 33: RC14 - Groundwater from 40m RC15- Groundwater from 30M increasing significantly from 60m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 19; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250719D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-20 | SF25_RCRD016 | SF25_RCRD017 | SF25_RCRD018 |  | Kane Barton | 3 | 390 | 136 | 100 | 48 |  |  |  | 284 | 12340 | 7.25 | 12340 | 8 | 8 | 1 | 1 | 7.25 | 3.25 | 0.75 |  | 0.75 |  | 12 |  | 595 | 1760 | 2138.75 | 1082.28 | 692.28 | 17916.03 | 17916.03 | 14017.28 | 21.76% | 374292.02 | 219977.95 | 63.0846 |  | PLOD LINK 32: LINK; Comments 33: RC16 - Groundwater from 40m increasing with depth, difficulty retaining dry sample from 124m onward. RC17 - Groundwater from 34m. RC18 - Groundwater from 18M. Increasing with depth.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 20; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250720D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-21 | SF25_RCRD018 | SF25_RCRD019 | SF25_RCRD020 | SF25_RCRD021 | Kane Barton | 3 | 390 | 146 | 42 | 24 |  |  |  | 212 | 8930 | 5.25 | 8930 | 6 | 6 | 1 | 1 | 5.25 | 4 | 1.25 |  | 1.5 |  | 12 |  | 595 | 1320 | 2750 | 1293.17 | 903.17 | 14888.17 | 14888.17 | 10818.17 | 27.34% | 389180.19 | 234866.12 | 70.2272 |  | PLOD LINK 32: LINK; Comments 33: RC18 - Groundwater from 18M. Increasing with depth. Significant volumes from 70m. RC20 - groundwater from 30m. RC21 - Groundwater from 10M. Maintenance - Auxiliary 250Hr service completed.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 21; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250721D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-22 | SF25_RCRD021 | SF25_RCRD022 | SF25_RCRD023 |  | Kane Barton | 4 | 520 | 96 | 70 | 36 |  |  |  | 202 | 8790 | 5.5 | 8790 | 5 | 5 | 1 | 1 | 5.5 | 5 | 1 |  | 0.5 |  | 12 |  | 595 | 1100 | 3235 |  | 903.17 | 15143.17 | 15143.17 | 10808.17 | 28.63% | 404323.36 | 250009.29 | 74.9662 |  | PLOD LINK 32: LINK; Comments 33: RC21 - groundwater from 10m, Large volumes from 120m RC22 - Groundwater from 10M RC22 - Groundwater from 10M, Sump filled @ 50M. 2340L diesel taken from fuel farm.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 22; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250722D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-23 | SF25_RCRD023 | SF25_RCRD024 | SF25_RCRD025 |  | Kane Barton | 4 | 520 | 72 | 68 | 36 |  |  |  | 176 | 7740 | 4.5 | 7740 | 5 | 5 | 1 | 1 | 4.5 | 3.5 | 1.25 |  | 2.75 |  | 12 |  | 595 | 1100 | 2462.5 |  | 850.77 | 13268.27 | 13268.27 | 9705.77 | 26.85% | 417591.63 | 263277.56 | 75.3879 |  | PLOD LINK 32: LINK; Comments 33: RC24 - Groundwater from 10M. Large volumes from 80M. 2 sumps filled to complete hole. RC25 - Groundwater from 16M. - Starter rod inner tube replaced due to wear - Top hammer tube replaced.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 23; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250723D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-24 | SF25_RCRD025 |  |  |  | Kane Barton | 4 | 520 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 12 |  | 0 | 0 | 0 |  | 182.12 | 702.12 | 702.12 | 702.12 | 0% | 418293.75 | 263979.68 | No drilling completed today, if maintenance provide context -> | Rod handler Stripped down and fixed | PLOD LINK 32: LINK; Comments 33: Breakdown awaiting parts. - Rig service completed. - Mast inspection & Lube completed. - Rod handler stripped down. - Fleet washed. - Assorted maintenance jobs completed on equipment. - Genset service completed.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 24; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250724D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-25 | SF25_RCRD025 |  |  |  | Kane Barton | 4 | 520 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 |  | 12 |  | 0 | 0 | 0 |  | 0 | 520 | 520 | 520 | 0% | 418813.75 | 264499.68 | No drilling completed today, if maintenance provide context -> | SDR18 RHS Track repaired, seals replaced within tensioning cylinder, Brake pack replaced on rod handler, cup & Arm re mounted | PLOD LINK 32: LINK; Comments 33: SDR18 RHS Track repaired, seals replaced within tensioning cylinder, Brake pack replaced on rod handler, cup & Arm re mounted.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 25; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250725D; Comments 40: 2025-07
M 80/268 | A Vein RC | EXT | 2025-07-26 | SF25_RCRD025 | SF25_RCRD026 | SF25_RCRD115 |  | Kane Barton | 4 | 520 | 108 | 50 | 36 |  |  |  | 194 | 8370 | 4.75 | 8370 | 4.25 | 4.25 | 1 | 1 | 4.75 | 6 | 0.75 |  | 0.5 |  | 12 |  | 595 | 935 | 3720 |  | 1045.68 | 15185.68 | 15185.68 | 10530.68 | 30.65% | 433999.43 | 279685.36 | 78.2767 |  | PLOD LINK 32: LINK; Comments 33: RC026 - Groundwater from 10M. Large volumes from 60m, 3 sumps filled. Drilled 16m long drop in camp.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 26; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250726D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-07-27 | SF25_RCRD115 | SF25_RCRD162 |  |  | Kane Barton | 4 | 520 | 82 | 100 | 50 | 10 |  |  | 242 | 10830 | 7.25 | 10830 | 7 | 7 | 1 | 1 | 7.25 | 2.5 | 0.75 |  | 1.5 |  | 12 |  | 595 | 1540 | 1707.5 |  | 549.77 | 15742.27 | 15742.27 | 12494.77 | 20.63% | 449741.7 | 295427.63 | 65.0507 |  | PLOD LINK 32: LINK; Comments 33: RC115- Groundwater from 60M. Large volumes from 140m. RC162 - Groundwater from 10m. Increasing with depth. Sample hose repaired, Rotation lever replaced on rig. Unable to tram to RC164 as requested, approach angle to steep, set up on RC162; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 27; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250727D; Comments 40: 2025-07
M 80/269 | Infill | INF | 2025-07-28 | SF25_RCRD162 | SF25_RCRD158 |  |  | Kane Barton | 4 | 520 | 50 | 50 | 98 | 22 |  |  | 220 | 10360 | 6.25 | 10360 | 7 | 7 | 1 | 1 | 6.25 | 4 | 1.25 |  | 0.5 |  | 12 |  | 595 | 1540 | 2750 | 1643.28 | 1123.28 | 16888.28 | 16888.28 | 12598.28 | 25.4% | 466629.98 | 312315.91 | 76.7649 |  | PLOD LINK 32: LINK; Comments 33: RC162 - Groundwater from 10m. Increasing with depth. Large volumes from 100m. Hole ended early due to historic hole within pad vicinity discharging toward work area creating unsafe working conditions.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 28; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250728D; Comments 40: 2025-07
M 80/269 | Infill | INF | 2025-07-29 | SF25_RCRD158 | SF25_RCRD160 |  |  | Kane Barton | 4 | 520 | 50 | 50 | 26 | 10 |  |  | 136 | 6100 | 4 | 6100 | 4 | 4 | 1 | 1 | 4 | 6.75 | 0.75 |  | 0.5 |  | 12 |  | 595 | 880 | 4151.25 | 1643.28 | 1123.28 | 13369.53 | 13369.53 | 8338.28 | 37.63% | 479999.51 | 325685.44 | 98.3054 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 29; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250729D; Comments 40: 2025-07
M 80/269 | Infill | INF | 2025-07-30 | SF25_RCRD160 | SF25_RCRD149 |  |  | Kane Barton | 4 | 520 | 34 |  | 12 |  |  |  | 46 | 1960 | 1.75 | 1960 | 2 | 2 | 1 | 1 | 1.75 | 9 | 0.75 |  | 0.5 |  | 12 |  | 595 | 440 | 5445 | 1029.88 | 509.88 | 9469.88 | 9469.88 | 3584.88 | 62.14% | 489469.39 | 335155.32 | 205.867 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 30; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250730D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-07-31 | SF25_RCRD149 | SF25_RCRD145 |  |  | Hugh Reynolds | 3 | 390 | 66 | 52 | 50 | 22 |  |  | 190 | 8690 | 6.75 | 8690 | 6 | 6 | 1 | 1 | 6.75 | 4.25 | 0.5 |  | 0.5 |  | 12 |  | 595 | 1320 | 2623.75 | 24048.14 | 23658.14 | 37276.89 | 37276.89 | 33333.14 | 10.58% | 526746.28 | 372432.21 | 196.1942 |  | PLOD LINK 32: LINK; Comments 33: SF25_RCRD0149 ground water intersection at 34m Consumable Downhole hammer tube - monthly expenses added; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 07; Comments 37: 31; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250731D; Comments 40: 2025-07
M 80/268 | Infill | INF | 2025-08-01 | SF25_RCRD145 | SF25_RCRD133 |  |  | Hugh Reynolds | 3 | 390 | 50 | 98 | 56 | 10 |  |  | 214 | 9760 | 7.5 | 9760 | 7 | 7 | 1 | 1 | 7.5 | 3.25 | 0.75 |  | 0.5 |  | 12 |  | 595 | 1540 | 2138.75 | 887.37 | 497.37 | 14921.12 | 14921.12 | 11242.37 | 24.65% | 541667.4 | 14921.12 | 69.7249 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 01; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250801D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-02 | SF25_RCRD133 | SF25_RCRD136 |  |  | Hugh Reynolds | 3 | 390 | 50 | 50 | 44 | 40 |  |  | 184 | 8650 | 6 | 8650 | 6 | 6 | 1 | 1 | 6 | 3.5 | 1 |  | 0.5 | 1 | 12 |  | 595 | 1320 | 2372.5 | 1029.88 | 639.88 | 13967.38 | 13967.38 | 10274.88 | 26.44% | 555634.78 | 28888.5 | 75.9097 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 02; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250802D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-03 | SF25_RCRD136 |  |  |  | Hugh Reynolds | 3 | 390 | 0 | 0 | 50 | 46 |  |  | 96 | 5030 | 6.25 | 5030 | 7 | 7 | 1 | 1 | 6.25 | 4.5 | 0.25 |  | 0.5 | 0.5 | 12 | Repair blown sample hosee | 595 | 1540 | 2677.5 | 728.88 | 338.88 | 10571.38 | 10571.38 | 6353.88 | 39.9% | 566206.16 | 39459.88 | 110.1185 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 03; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250803D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-04 | SF25_RCRD136 | SF25_RCRD140 |  |  | Hugh Reynolds | 3 | 390 | 50 | 50 | 50 | 44 |  |  | 194 | 9170 | 6 | 9170 | 7 | 7 | 1 | 1 | 6 | 3.75 | 1 |  | 1.25 |  | 12 |  | 595 | 1540 | 2516.25 | 1029.88 | 639.88 | 14851.13 | 14851.13 | 10794.88 | 27.31% | 581057.29 | 54311.01 | 76.5522 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 04; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250804D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-05 | SF25_RCRD143 |  |  |  | Hugh Reynolds | 5 | 650 | 50 | 50 | 50 | 30 |  |  | 180 | 8400 | 5 | 8400 | 6 | 6 | 1 | 1 | 5 | 3 | 2 |  | 2 |  | 12 |  | 595 | 1320 | 2445 | 1289.88 | 639.88 | 14049.88 | 14049.88 | 10284.88 | 26.8% | 595107.17 | 68360.89 | 78.0549 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 05; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250805D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-06 | SF25_RCRD146 |  |  |  | Kane Barton | 3 | 390 | 50 | 50 | 50 | 50 | 2 |  | 202 | 9620 | 5.5 | 9620 | 6 | 6 | 1 | 1 | 5.5 | 4.25 | 0.75 |  | 0.5 | 1 | 12 | Cyclone removed to replace worn bolts | 595 | 1320 | 2713.75 | 1029.88 | 639.88 | 15278.63 | 15278.63 | 11244.88 | 26.4% | 610385.8 | 83639.52 | 75.6368 |  | PLOD LINK 32: LINK; Comments 33: SF146 ground water intersection at 70m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 06; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250806D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-07 | SF25_RCRD131 |  |  |  | Kane Barton | 4 | 520 | 50 | 2 |  |  |  |  | 52 | 2090 | 1 | 2090 | 1 | 1 | 1 | 1 | 1 | 1.5 | 0 | 0 | 0.5 | 9 | 12 | Replace all cyclone rotation bolts and attach cyclone. Await parts until 11:30am | 595 | 220 | 862.5 | 1121.56 | 601.56 | 4889.06 | 4889.06 | 3806.56 | 22.14% | 615274.86 | 88528.58 | 94.0204 |  | PLOD LINK 32: LINK; Comments 33: SF131 ground water intersection at 28m William Howard to be added to this plod- Offsider.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 07; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250807D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-08 | SF25_RCRD131 | SF25_RCRD127 |  |  | Kane Barton | 4 | 520 | 50 | 98 | 78 |  |  |  | 226 | 10310 | 6.5 | 10310 | 6 | 6 | 1 | 1 | 6.5 | 4.25 | 0.75 | 0 | 0.5 |  | 12 | Bit change and break down hammer due to abrasive ground conditions | 595 | 1320 | 2713.75 | 1121.56 | 601.56 | 16060.31 | 16060.31 | 12026.56 | 25.12% | 631335.17 | 104588.89 | 71.0633 |  | PLOD LINK 32: LINK; Comments 33: SF127 ground water intersection at 60M William Howard to be added to this plod- Offsider.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 08; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250808D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-09 | SF25_RCRD127 | SF25_RCRD123 | SF25_RCRD120 |  | Kane Barton | 4 | 520 | 60 | 50 | 64 | 68 |  |  | 242 | 11590 | 5.75 | 11590 | 5 | 5 | 1 | 1 | 5.75 | 4.25 | 1.5 | 0 | 0.5 |  | 12 |  | 595 | 1100 | 2983.75 | 1370.77 | 850.77 | 17639.52 | 17639.52 | 13555.77 | 23.15% | 648974.69 | 122228.41 | 72.8906 |  | PLOD LINK 32: LINK; Comments 33: SF127 ground water intersection at 60M SF123 Groumdwater from 80M.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 09; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250809D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-10 | SF25_RCRD120 | SF25_RCRD054 |  |  | Kane Barton | 4 | 520 | 90 | 100 | 86 | 22 |  |  | 298 | 13610 | 7.25 | 13610 | 7 | 7 | 1 | 1 | 7.25 | 3.5 | 0.75 |  | 0.5 |  | 12 |  | 595 | 1540 | 2282.5 | 1069.77 | 549.77 | 19097.27 | 19207.27 | 15274.77 | 20.02% | 668071.96 | 141325.68 | 64.0848 |  | PLOD LINK 32: LINK; Comments 33: Toolbox meeting @ end of shift. SF120 Large volumes of groundwater from 140m SF054 Slight Groundwater from 90M; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 10; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250810D; Comments 40: 2025-08
M 80/268 | G Vein RC | INF | 2025-08-11 | SF25_RCRD054 | SF25_RCRD055 | SF25_RCRD056 |  | Kane Barton | 3 | 390 | 100 | 52 | 32 | 40 |  |  | 224 | 10140 | 4.25 | 10140 | 4 | 4 | 1 | 1 | 4.25 | 3.25 | 4 |  | 0.5 |  | 12 | Travel Half way to Doon Doon to assist offsider with tyre change. | 595 | 880 | 3308.75 | 549.77 | 159.77 | 15473.52 | 15473.52 | 11284.77 | 27.07% | 683545.48 | 156799.2 | 69.0782 |  | PLOD LINK 32: LINK; Comments 33: SF054 Slight Groundwater from 90m SF055 Groundwater from 30m SF056 Groundwater from 30m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 11; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250811D; Comments 40: 2025-08
M 80/268 | G Vein RC | INF | 2025-08-12 | SF25_RCRD058 | SF25_RCRD300 |  |  | Kane Barton | 3 | 390 | 100 | 94 | 50 | 50 | 8 |  | 302 | 13960 | 6 | 13960 | 6 | 6 | 1 | 1 | 6 | 3.75 | 1.75 |  | 0.5 |  | 12 |  | 595 | 1320 | 2786.25 | 939.77 | 549.77 | 19601.02 | 19601.02 | 15494.77 | 20.95% | 703146.5 | 176400.22 | 64.904 |  | PLOD LINK 32: LINK; Comments 33: SF057 Groundwater from 10M. SF300 Groundwater from 40m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 12; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250812D; Comments 40: 2025-08
M 80/268 | G Vein RC | INF | 2025-08-13 | SF25_RCRD300 | SF25_RCRD058 | SF25_RCRD059 |  | Kane Barton | 3 | 390 | 100 | 88 | 72 |  |  |  | 260 | 11560 | 5.5 | 11560 | 5 | 5 | 1 | 1 | 5.5 | 4.25 | 1.75 |  | 0.5 |  | 12 |  | 595 | 1100 | 3073.75 | 939.77 | 549.77 | 17268.52 | 17268.52 | 13094.77 | 24.17% | 720415.02 | 193668.74 | 66.4174 |  | PLOD LINK 32: LINK; Comments 33: SF300 Groundwater from 40m SF58 Groundwater from 10M SF59 Small amounts of Groundwater from 30M; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 13; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250813D; Comments 40: 2025-08
M 80/269 | G Vein RC | INF | 2025-08-14 | SF25_RCRD060 | SF25_RCRD061 | SF25_RCRD062 |  | Kane Barton | 4 | 520 | 146 | 88 | 18 |  |  |  | 252 | 10700 | 5.5 | 10700 | 5 | 5 | 1 | 1 | 5.5 | 3.75 | 1 |  | 0.5 | 1.25 | 12 | Cyclone removed to replace worn bolts | 595 | 1100 | 2516.25 | 1370.77 | 850.77 | 16282.02 | 16282.02 | 12665.77 | 22.21% | 736697.04 | 209950.76 | 64.6112 |  | PLOD LINK 32: LINK; Comments 33: SF60 slight groundwater from 10m SF61 Groundwater from 30M increasing significantly from 58M. SF62 slight groundwater from 60M; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 14; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250814D; Comments 40: 2025-08
M 80/268 | G Vein RC | INF | 2025-08-15 | SF25_RCRD063 | SF25_RCRD064 | SF25_RCRD066 |  | Kane Barton | 4 | 520 | 146 | 94 | 18 |  |  |  | 258 | 10970 | 5.75 | 10970 | 5 | 5 | 1 | 1 | 5.75 | 2.75 | 1.5 |  | 0.5 | 1.5 | 12 | Completed cyclone maintenance | 595 | 1100 | 2121.25 | 1370.77 | 850.77 | 16157.02 | 14035.77 | 12935.77 | 19.94% | 752854.06 | 226107.78 | 62.6241 |  | PLOD LINK 32: LINK; Comments 33: SF63 Groumdwater from 30m. Large volumes from 88m. 1 sump filled. SF64 No noticeable amounts of groundwater whilst drilling. SF66 No noticeable amounts of groundwater whilst drilling.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 15; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250815D; Comments 40: 2025-08
M 80/268 | G Vein RC | INF | 2025-08-16 | SF25_RCRD065 | SF25_RCRD068 | SF25_RCRD067 |  | Kane Barton | 4 | 520 | 128 | 52 | 50 | 22 |  |  | 252 | 11170 | 6.5 | 11170 | 6 | 6 | 1 | 1 | 6.5 | 3.25 | 0.75 |  | 0.5 | 1 | 12 | Cross over pipe removed & insert replaced | 595 | 1320 | 2138.75 | 1513.28 | 993.28 | 16737.03 | 16737.03 | 13278.28 | 20.67% | 769591.09 | 242844.81 | 66.4168 |  | PLOD LINK 32: LINK; Comments 33: SF65 Groundwater from 10M. Large volumes from 80M. SF68 Groundwater from 24M. SF67 Groundwater from 10M.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 16; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250816D; Comments 40: 2025-08
M 80/268 | G Vein RC | INF | 2025-08-17 | SF25_RCRD067 | SF25_RCRD080 | SF25_RCRD079 |  | Kane Barton | 4 | 520 | 122 | 108 | 30 |  |  |  | 260 | 11240 | 6.25 | 11240 | 6 | 6 | 1 | 1 | 6.25 | 3.75 | 1 |  | 1 |  | 12 | weekly toolbox | 595 | 1320 | 2516.25 | 1370.77 | 850.77 | 17042.02 | 17042.02 | 13205.77 | 22.51% | 786633.11 | 259886.83 | 65.5462 |  | PLOD LINK 32: LINK; Comments 33: SF67 Groundwater from 10M. SF80 Groundwater from 46M. SF79 Groundwater from 10M; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 17; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250817D; Comments 40: 2025-08
M 80/269 | G Vein RC | INF | 2025-08-18 | SF25_RCRD079 | SF25_RCRD078 | SF25_RCRD077 |  | Kane Barton | 4 | 520 | 100 | 112 | 42 |  |  |  | 254 | 11140 | 7.5 | 11140 | 7 | 7 | 1 | 1 | 7.5 | 3 | 1 |  | 0.5 |  | 12 |  | 595 | 1540 | 2085 | 1370.77 | 850.77 | 16730.77 | 16730.77 | 13105.77 | 21.67% | 803363.88 | 276617.6 | 65.8692 |  | PLOD LINK 32: LINK; Comments 33: SF79 Groundwater from 10M, volumes increasing significantly from 80M. Aquifer intercepted @ 106M through ground transition, 4 sumps filled between 106M-136M. Unable to contain water to reach end of hole depth. SF78 Groundwater from 16M, Increasing with depth from 30M onward. SF77 Groundwater from 16M, Increasing significantly from 82M.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 18; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250818D; Comments 40: 2025-08
M 80/269 | G Vein RC | INF | 2025-08-19 | SF25_RCRD077 | SF25_RCRD076 | SF25_RCRD074 |  | Kane Barton | 4 | 520 | 100 | 82 | 80 | 40 |  |  | 302 | 13890 | 7.5 | 13890 | 7 | 7 | 1 | 1 | 7.5 | 3 | 1 |  | 0.5 |  | 12 |  | 595 | 1540 | 2085 | 1761.44 | 1241.44 | 19871.44 | 19871.44 | 16246.44 | 18.24% | 823235.32 | 296489.04 | 65.7995 |  | PLOD LINK 32: LINK; Comments 33: SF76 Groundwater from 18M. SF74 Groundwater from 18M.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 19; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250819D; Comments 40: 2025-08
M 80/269 | G Vein RC | INF | 2025-08-20 | SF25_RCRD074 | SF25_RCRD075 | SF25_RCRD220 |  | Kane Barton | 5 | 650 | 100 | 88 | 74 | 46 |  |  | 308 | 14190 | 7.5 | 14190 | 7 | 7 | 1 | 1 | 7.5 | 3.25 | 0.75 |  | 0.5 |  | 12 |  | 595 | 1540 | 2138.75 | 1370.77 | 720.77 | 19834.52 | 19834.52 | 16155.77 | 18.55% | 843069.84 | 316323.56 | 64.3978 |  | PLOD LINK 32: LINK; Comments 33: SF74 Groundwater from 18M. Significant volumes from 184M. SF75 Groundwater from 16M Significant volumes from 82M. SF220 Groundwater from 34M.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 20; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250820D; Comments 40: 2025-08
M 80/269 | Infill | INF | 2025-08-21 | SF25_RCRD220 | SF25_RCRD212 |  |  | Kane Barton | 4 | 520 | 50 | 80 | 74 | 50 | 2 |  | 256 | 12170 | 6.5 | 12170 | 6 | 6 | 1 | 1 | 6.5 | 4 | 1 |  | 0.5 |  | 12 |  | 595 | 1320 | 2660 | 2051.37 | 1531.37 | 18796.37 | 18796.37 | 14816.37 | 21.17% | 861866.21 | 335119.93 | 73.4233 |  | PLOD LINK 32: LINK; Comments 33: SF220 Groundwater from 34M. Bit change @ 112M. SF212 Groundwater from 6M, Hole cased 24M to competent ground due to expectations for large amounts of groundwater. Aquifer intersected @ 106M filling one sump.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 21; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250821D; Comments 40: 2025-08
M 80/269 | Infill | INF | 2025-08-22 | SF25_RCRD212 | SF25_RCRD221 | SF25_RCRD222 |  | Kane Barton | 4 | 520 | 100 | 70 | 50 | 50 | 10 |  | 280 | 13000 | 7.5 | 13000 | 6 | 6 | 1 | 1 | 7.5 | 3 | 1 |  | 0.5 |  | 12 |  | 595 | 1320 | 2085 | 1212.28 | 692.28 | 18212.28 | 18158.53 | 14807.28 | 18.7% | 880078.49 | 353332.21 | 65.0439 |  | PLOD LINK 32: LINK; Comments 33: SF212 Groundwater from 6M, Hole cased 24M to competent ground due to expectations for large amounts of groundwater. Aquifer intersected @ 106M filling one sump. Large volumes of water to EOH. SF221 Groundwater from 34M. SF222 Groundwater from 12M.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 22; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250822D; Comments 40: 2025-08
M 80/269 | Infill | INF | 2025-08-23 | SF25_RCRD214 | SF25_RCRD073 | SF25_RCRD072 |  | Kane Barton | 4 | 520 | 146 | 64 |  |  |  |  | 210 | 8720 | 4.75 | 8720 | 5 | 5 | 1 | 1 | 4.75 | 3 | 1.75 |  | 0.5 | 2 | 12 | 250 hr service | 595 | 1100 | 2355 | 1069.77 | 549.77 | 13839.77 | 13839.77 | 10384.77 | 24.96% | 893918.26 | 367171.98 | 65.9037 |  | PLOD LINK 32: LINK; Comments 33: SF214 Groundwater from 30M SF73 Groundwater from 16M SS72 Groundwater from 16M increasing significantly by EOH.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 23; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250823D; Comments 40: 2025-08
M 80/269 | G Vein RC | EXT | 2025-08-24 | SF25_RCRD071 | SF25_RCRD053 | SF25_RCRD052 |  | Kane Barton | 4 | 520 | 146 | 88 | 24 |  |  |  | 258 | 11000 | 4.5 | 11000 | 5 | 5 | 1 | 1 | 4.5 | 6.25 | 0.75 |  | 0.5 |  | 12 |  | 595 | 1100 | 3863.75 | 1069.77 | 549.77 | 17628.52 | 17628.52 | 12664.77 | 28.16% | 911546.78 | 384800.5 | 68.3276 |  | PLOD LINK 32: LINK; Comments 33: SF071 ground water intersection at 18m SF053 ground water intersection at 18m SF052 ground water intersection at 24m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 24; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250824D; Comments 40: 2025-08
M 80/268 | G Vein RC | EXT | 2025-08-25 | SF25_RCRD050 |  |  |  | Kane Barton | 5 | 650 | 50 | 50 | 50 | 50 | 20 |  | 220 | 10700 | 5.25 | 10700 | 6 | 6 | 1 | 1 | 5.25 | 3.5 | 1.25 |  | 0.5 | 1.5 | 12 |  | 595 | 1320 | 2462.5 | 1173.57 | 523.57 | 16251.07 | 16251.07 | 12468.57 | 23.28% | 927797.85 | 401051.57 | 73.8685 |  | PLOD LINK 32: LINK; Comments 33: SF050 ground water intersection at 70m. Maintenance - replaced blown mast dump water injection hose - replace leaking traverse cylinder fitting in the mast - replace leaking breakout hose; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 25; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250825D; Comments 40: 2025-08
M 80/268 | G Vein RC | EXT | 2025-08-26 | SF25_RCRD051 | SF25_RCRD049 | SF25_RCRD048 |  | Kane Barton | 5 | 650 | 150 | 114 | 36 |  |  |  | 300 | 12930 | 5.5 | 12930 | 6 | 6 | 1 | 1 | 5.5 | 5 | 1 |  | 0.5 |  | 12 |  | 595 | 1320 | 3235 | 1854.17 | 1204.17 | 19934.17 | 19934.17 | 15379.17 | 22.85% | 947732.02 | 420985.74 | 66.4472 |  | PLOD LINK 32: LINK; Comments 33: SF051 ground water intersection at 28m SF049 ground water intersection at 64m SF048 ground water intersection at 84m Oliver Carlyle to be added to the plod for 12hrs; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 26; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250826D; Comments 40: 2025-08
M 80/268 | G Vein RC | EXT | 2025-08-27 | SF25_RCRD048 | SF25_RCRD047 | SF25_RCRD046 |  | Hugh Reynolds | 4 | 520 | 90 | 62 | 86 | 50 | 14 |  | 302 | 14280 | 5.5 | 14280 | 6 | 6 | 1 | 1 | 5.5 | 4.5 | 1.5 |  | 0.5 |  | 12 |  | 595 | 1320 | 3127.5 | 1370.77 | 850.77 | 20693.27 | 20693.27 | 16245.77 | 21.49% | 968425.29 | 441679.01 | 68.5208 |  | PLOD LINK 32: LINK; Comments 33: F048 ground water intersection at 84m SF047 ground water intersection at 30m Oliver Carlyle to be added to the plod for 12hrs; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 27; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250827D; Comments 40: 2025-08
M 80/268 | G Vein RC | EXT | 2025-08-28 | SF25_RCRD046 | SF25_RCRD045 |  |  | Hugh Reynolds | 4 | 520 | 60 | 100 | 56 | 22 |  |  | 238 | 10910 | 5.75 | 10910 | 7 | 7 | 1 | 1 | 5.75 | 4.5 | 1.25 |  | 0.5 |  | 12 |  | 595 | 1540 | 3037.5 | 1043.57 | 523.57 | 17126.07 | 17126.07 | 12548.57 | 26.73% | 985551.36 | 458805.08 | 71.9583 |  | PLOD LINK 32: LINK; Comments 33: SF046 ground water intersection at 70m SF045 ground water intersection at 58m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 28; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250828D; Comments 40: 2025-08
M 80/268 | G Vein RC | EXT | 2025-08-29 | SF25_RCRD044 |  |  |  | Hugh Reynolds | 4 | 520 | 50 | 50 | 50 | 50 | 50 |  | 250 | 12500 | 6.25 | 12500 | 7 | 7 | 1 | 1 | 6.25 | 3.25 | 1 |  | 0.5 | 1 | 12 |  | 595 | 1540 | 2228.75 | 1043.57 | 523.57 | 17907.32 | 17907.32 | 14138.57 | 21.05% | 1003458.68 | 476712.4 | 71.6293 |  | PLOD LINK 32: LINK; Comments 33: SF044 ground water intersection at 40m Maintenance - replace rotation motor on rod loader.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 29; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250829D; Comments 40: 2025-08
M 80/268 | G Vein RC | EXT | 2025-08-30 | SF25_RCRD043 | SF25_RCRD042 | SF25_RCRD109 |  | Hugh Reynolds | 3 | 390 | 150 | 86 |  |  |  |  | 236 | 9870 | 4.25 | 9870 | 6 | 6 | 1 | 1 | 4.25 | 6 | 1.25 |  | 0.5 |  | 12 |  | 595 | 1320 | 3900 | 1293.17 | 903.17 | 16978.17 | 16978.17 | 11758.17 | 30.75% | 1020436.85 | 493690.57 | 71.9414 |  | PLOD LINK 32: LINK; Comments 33: SF043 ground water intersection at 28m SF042 ground water intersection at 36m SF109 ground water intersection at 34m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 30; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250830D; Comments 40: 2025-08
M 80/268 | Infill | INF | 2025-08-31 | SF25_RCRD203 | SF25_RCRD110 |  |  | Hugh Reynolds | 3 | 390 | 80 | 50 | 50 | 22 |  |  | 202 | 9160 | 4.5 | 9160 | 6 | 6 | 1 | 1 | 4.5 | 6.25 | 0.75 |  | 0.5 |  | 12 |  | 595 | 1320 | 3863.75 | 22415.95 | 22025.95 | 37354.7 | 37354.7 | 32170.95 | 13.88% | 1057791.55 | 531045.27 | 184.9243 |  | PLOD LINK 32: LINK; Comments 33: MONTHLY: FLIGHTS $10475.91 - FREIGHT $ 10699.27 -SF203 no ground water intersections SF110 ground water intersection at 46m; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 08; Comments 37: 31; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250831D; Comments 40: 2025-08
M 80/269 | Infill | INF | 2025-09-01 | SF25_RCRD233 | SF25_RCRD229 |  |  | Hugh Reynolds | 3 | 390 | 100 | 76 | 42 |  |  |  | 218 | 9520 | 7 | 9520 | 7 | 7 | 1 | 1 | 7 | 3.75 | 0.75 |  | 0.5 |  | 12 |  | 595 | 1540 | 2426.25 | 1240.77 | 850.77 | 15322.02 | 15322.02 | 11355.77 | 25.89% | 1073113.57 | 15322.02 | 70.2845 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 01; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250901D; Comments 40: 2025-09
M 80/269 | Infill | INF | 2025-09-02 | SF25_RCRD229 | SF25_RCRD182 |  |  | Hugh Reynolds | 4 | 520 | 50 | 74 | 86 | 4 |  |  | 214 | 9850 | 6.5 | 9850 | 7 | 7 | 1 | 1 | 6.5 | 4.5 | 0.5 |  | 0.5 |  | 12 |  | 595 | 1540 | 2767.5 | 1017.37 | 497.37 | 15769.87 | 15769.87 | 11462.37 | 27.31% | 1088883.44 | 31091.89 | 73.691 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 02; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250902D; Comments 40: 2025-09
M 80/269 | Infill | INF | 2025-09-03 | SF25_RCRD182 | SF25_RCRD174 |  |  | Hugh Reynolds | 4 | 520 | 50 | 50 | 56 | 50 |  |  | 206 | 9800 | 5.25 | 9800 | 6 | 6 | 1 | 1 | 5.25 | 5.25 | 1 |  | 0.5 |  | 12 |  | 595 | 1320 | 3378.75 | 1159.88 | 639.88 | 16253.63 | 16253.63 | 11554.88 | 28.91% | 1105137.07 | 47345.52 | 78.9011 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 03; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250903D; Comments 40: 2025-09
M 80/269 | Infill | INF | 2025-09-04 | SF25_RCRD174 | SF25_RCRD168 |  |  | Kane Barton | 3 | 390 | 34 |  | 8 | 50 | 10 |  | 102 | 5110 | 3 | 5110 | 4 | 4 | 1 | 1 | 3 | 6.75 | 1.75 |  | 0.5 |  | 12 |  | 595 | 880 | 4511.25 | 1029.88 | 639.88 | 12126.13 | 12126.13 | 6734.88 | 44.46% | 1117263.2 | 59471.65 | 118.8836 |  | PLOD LINK 32: LINK; Comments 33: SF174 Groundwater from 18M. Aquifer intersected @ 88M, large volumes of groundwater. Volumes increasing until EOH. Sump continually pumped to complete hole. SF168 Groundwater @ 30M; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 04; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250904D; Comments 40: 2025-09
M 80/269 | Infill | INF | 2025-09-05 | SF25_RCRD168 |  |  |  | Kane Barton | 3 | 390 | 16 | 50 | 50 | 50 | 10 |  | 176 | 8740 | 0 | 8740 | 5.5 | 5.5 | 1 | 1 | 4.75 | 5 | 1.75 |  | 0.5 |  | 12 |  | 595 | 1210 | 3505 | 924.64 | 534.64 | 14974.64 | 14974.64 | 10259.64 | 31.49% | 1132237.84 | 74446.29 | 85.0832 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 05; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250905D; Comments 40: 2025-09
M 80/269 | Infill | INF | 2025-09-06 | SF25_RCRD157 | SF25_RCRD070 |  |  | Kane Barton | 3 | 390 | 90 | 50 | 50 | 34 |  |  | 224 | 10220 | 5.25 | 10220 | 5.5 | 5.5 | 1 | 1 | 5.25 | 5.25 | 1 |  | 0.5 |  | 12 |  | 595 | 1210 | 3378.75 | 1240.77 | 850.77 | 16644.52 | 16644.52 | 12055.77 | 27.57% | 1148882.36 | 91090.81 | 74.3059 |  | PLOD LINK 32: LINK; Comments 33: SF157 Groundwater from 30M, Large volumes from 90M. SF70 No groundwater intercepted.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 06; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250906D; Comments 40: 2025-09
M 80/269 | G Vein RC | INF | 2025-09-07 | SF25_RCRD069 |  |  |  | Kane Barton | 3 | 390 | 50 | 50 | 50 | 10 |  |  | 160 | 7300 | 4.75 | 7300 | 5.25 | 5.25 | 1 | 1 | 4.75 | 2.75 | 0.75 |  | 3.75 |  | 12 |  | 595 | 1155 | 1851.25 |  | -390 | 10901.25 | 939.77 | 7895 | 27.58% | 1159783.61 | 101992.06 | 68.1328 |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 07; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250907D; Comments 40: 2025-09
#N/A | Demob |  | 2025-09-08 |  |  |  |  | Kane Barton | 3 | 390 | [6 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 11.75 |  | 0.25 |  | 12 |  | 0 | 0 | 4230 |  | -390 | 4230 | 4230 | 0 | 100% | 1164013.61 | 106222.06 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 08; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250908D; Comments 40: 2025-09
#N/A | Demob |  | 2025-09-09 |  |  |  |  | Kane Barton | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 0 |  | 12 |  | 12 | demob | 0 | 0 | 0 | 53618.6 | 53618.6 | 53618.6 | 53618.6 | 53618.6 | 0% | 1217632.21 | 159840.66 |  |  | PLOD LINK 32: LINK; Comments 33: Demobilisation, Tramming/floating equipment off site & packing up lay down.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 09; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250909D; Comments 40: 2025-09
#N/A | Demob |  | 2025-09-10 |  |  |  |  | Kane Barton | [8 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 12 |  | 12 | completed demob | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 159840.66 |  |  | PLOD LINK 32: LINK; Comments 33: Completed floating booster off site and packed up laydown; all equipment driven off-site in the afternoon.; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 09; Comments 37: 10; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-250910D; Comments 40: 2025-09
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A | [45 empty] | Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 00; Comments 36: 01; Comments 37: 00; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-000100D; Comments 40: 1900-01
#N/A |  |  | 2025-10-01 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 01; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251001D; Comments 40: 2025-10
#N/A |  |  | 2025-10-02 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 02; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251002D; Comments 40: 2025-10
#N/A |  |  | 2025-10-03 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 03; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251003D; Comments 40: 2025-10
#N/A |  |  | 2025-10-04 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 04; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251004D; Comments 40: 2025-10
#N/A |  |  | 2025-10-05 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 05; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251005D; Comments 40: 2025-10
#N/A |  |  | 2025-10-06 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 06; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251006D; Comments 40: 2025-10
#N/A |  |  | 2025-10-07 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 07; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251007D; Comments 40: 2025-10
#N/A |  |  | 2025-10-08 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 08; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251008D; Comments 40: 2025-10
#N/A |  |  | 2025-10-09 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 09; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251009D; Comments 40: 2025-10
#N/A |  |  | 2025-10-10 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 10; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251010D; Comments 40: 2025-10
#N/A |  |  | 2025-10-11 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 11; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251011D; Comments 40: 2025-10
#N/A |  |  | 2025-10-12 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 12; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251012D; Comments 40: 2025-10
#N/A |  |  | 2025-10-13 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 13; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251013D; Comments 40: 2025-10
#N/A |  |  | 2025-10-14 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 14; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251014D; Comments 40: 2025-10
#N/A |  |  | 2025-10-15 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 15; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251015D; Comments 40: 2025-10
#N/A |  |  | 2025-10-16 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 16; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251016D; Comments 40: 2025-10
#N/A |  |  | 2025-10-17 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 17; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251017D; Comments 40: 2025-10
#N/A |  |  | 2025-10-18 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 18; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251018D; Comments 40: 2025-10
#N/A |  |  | 2025-10-19 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 19; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251019D; Comments 40: 2025-10
#N/A |  |  | 2025-10-20 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 20; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251020D; Comments 40: 2025-10
#N/A |  |  | 2025-10-21 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 21; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251021D; Comments 40: 2025-10
#N/A |  |  | 2025-10-22 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 22; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251022D; Comments 40: 2025-10
#N/A |  |  | 2025-10-23 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 23; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251023D; Comments 40: 2025-10
#N/A |  |  | 2025-10-24 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 24; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251024D; Comments 40: 2025-10
#N/A |  |  | 2025-10-25 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 25; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251025D; Comments 40: 2025-10
#N/A |  |  | 2025-10-26 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 26; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251026D; Comments 40: 2025-10
#N/A |  |  | 2025-10-27 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 27; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251027D; Comments 40: 2025-10
#N/A |  |  | 2025-10-28 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 28; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251028D; Comments 40: 2025-10
#N/A |  |  | 2025-10-29 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 34: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174; Comments 35: 25; Comments 36: 10; Comments 37: 29; Comments 38: 4; Comments 39: https://www.coreplan.io/app/ddh1-drilling/speewah-mining-speewah-fluorite-project-strike/plods/6174-251029D; Comments 40: 2025-10
#N/A |  |  | 2025-10-30 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 35: 25; Comments 36: 10; Comments 37: 30; Comments 38: 4; Comments 39: -251030D; Comments 40: 2025-10
#N/A |  |  | 2025-10-31 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK; Comments 35: 25; Comments 36: 10; Comments 37: 31; Comments 38: 4; Comments 39: -251031D; Comments 40: 2025-10
#N/A |  |  | 2025-11-01 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-02 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-03 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-04 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-05 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-06 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-07 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-08 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-09 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-10 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-11 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-12 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-13 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-14 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-15 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-16 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-17 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-18 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-19 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-20 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-21 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-22 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-23 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-24 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-25 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-26 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-27 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-28 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-29 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-11-30 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-01 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-02 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-03 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-04 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-05 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-06 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-07 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-08 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-09 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-10 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-11 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-12 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-13 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-14 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-15 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-16 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-17 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-18 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-19 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-20 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-21 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-22 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-23 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-24 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-25 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-26 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-27 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-28 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-29 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-30 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2025-12-31 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-01 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-02 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-03 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-04 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-05 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-06 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-07 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-08 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-09 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-10 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-11 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-12 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-13 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-14 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-15 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-16 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-17 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-18 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-19 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-20 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-21 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-22 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-23 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-24 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-25 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-26 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-27 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-28 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-29 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-30 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-01-31 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-01 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-02 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-03 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-04 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-05 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-06 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-07 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-08 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-09 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-10 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-11 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-12 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-13 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-14 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-15 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-16 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-17 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-18 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-19 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-20 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-21 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-22 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-23 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-24 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-25 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-26 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-27 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-02-28 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-03-01 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-03-02 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-03-03 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-03-04 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
#N/A |  |  | 2026-03-05 | [13 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 | 0 |  | 0 | 0 |  |  |  | 1217632.21 | 0 |  |  | PLOD LINK 32: LINK
[5 empty] | A Vein RC | 42
[5 empty] | Infill | 38
[5 empty] | G Vein RC | 38
Note on AA3: Aaron Stowe: $460 rate doesn't show up on Strikes contract within Coreplan - it's either $360-$575 or $0
Note on AK4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Type total consumable costs here and will automatically deduct accom costs and output cost on adjacent column
Note on AK13: Thomas Pilote: Low Loader (float) cost on this day - Part of Mob Cost

## HYD RIG 16
Rig16 | [7 empty] | Drill Costs | [38 empty] | Productivity metric Average
[9 empty] | PB collar | PB | MB collar | MB | [34 empty] | 914.7514
|  | Hole 1 | Hole 2 | Hole 3 | Hole 4 |  |  | 180 | 295 | 185 | 295 | 135 | 0 | 0 |  |  | 950 |  | 0 | 0 | 0 | 950 | 950 |  | 360 | 420 | 0 |  |  |  | 32 | 44 | 187 | 176 | 925 | 600 | 28.5 | 78 | 650 | 187
| Date | Hole ID | Hole ID | Hole ID | Hole ID | Driller Name | Personel (incl driller) | Accom Cost | 14.5" (381mm) | 12.5" (312mm) | 9.5" (230mm) | 6" (150mm) |  |  | Total Daily Meters | Drilling Cost | Drill Time | Charged Drilling Cost | Booster (p/hr) | Aux Compressor (p/hr) | Azi Aligner (p/day) | Survey camera (p/day) | Active Rate Total hours (Worktime) | Comment if worktime & Drill time is less than 11hours | Inactive Total | Standby Total Hours | non-charged Hours | Maintenance | Total (Fix if not 12hrs) | Total Activity hours Cost | 100mm Class 12 PVC Casing plan | 100mm Class 12 PVC Slotted cas | 200mm Top cap and End cap | Steel casing 350 NB | Steel well cover power coated lockable | Concrete Plinth | Gravel Pack material | Casing centraliser | Drilling Fluids | Bentonite Palets | Cement bag | Other Consumables | Total Consumables Cost (-Accom) | Total Costs | Cummulative Cost | EOM Cummulative Cost | Combined Cost Per Metre | Provide context on Maintenance | Comments
Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 12 | 12 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 |  |  |  | 26 | [12 empty] | 27 | 28 | 29 | 30 | 31 |  | 33 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
2025-07-08
2025-07-09
| 2025-07-10 | [48 empty] | 25 | 07 | 10 | 4 | -250710D | 2025-07
| 2025-07-11 | [48 empty] | 25 | 07 | 11 | 4 | -250711D | 2025-07
| 2025-07-12 | [48 empty] | 25 | 07 | 12 | 4 | -250712D | 2025-07
| 2025-07-13 | [48 empty] | 25 | 07 | 13 | 4 | -250713D | 2025-07
| 2025-07-14 | [48 empty] | 25 | 07 | 14 | 4 | -250714D | 2025-07
| 2025-07-15 | [48 empty] | 25 | 07 | 15 | 4 | -250715D | 2025-07
| 2025-07-16 | [48 empty] | 25 | 07 | 16 | 4 | -250716D | 2025-07
| 2025-07-17 | [48 empty] | 25 | 07 | 017 | 4 | -2507017D | 2025-07
| 2025-07-18 | [48 empty] | 25 | 07 | 018 | 4 | -2507018D | 2025-07
| 2025-07-19 | [48 empty] | 25 | 07 | 019 | 4 | -2507019D | 2025-07
| 2025-07-20 | [6 empty] | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [13 empty] | 0 | 0 | 0 | No drilling completed today, if maintenance provide context -> | Mobilisation: AWAITING PLOD |  | 25 | 07 | 020 | 4 | -2507020D | 2025-07
| 2025-07-21 | PL_SF25_RHYD008 |  |  |  | Riley T | 2 | 360 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  | 8 |  | 12 | 3800 | [12 empty] | 0 | 4160 | 4160 | 4160 | No drilling completed today, if maintenance provide context -> | rig maintenance, no offsider to start drilling. Set up at TSF1 |  | 25 | 07 | 021 | 4 | -2507021D | 2025-07
| 2025-07-22 | PL_SF25_RHYD008 | PL_SF25_RHYD009 |  |  | Riley T | 2 | 360 |  |  | 9 | 31 |  |  | 40 | 6840 | 2 | 6840 | 0 | 0 | 0 | 0 | 7.75 |  |  |  | 2.25 |  | 12 | 7362.5 | 1 | 1 | [10 empty] | 76 | 14638.5 | 18798.5 | 18798.5 | 365.9625 | TSF1 - install 100mm PVC. TSF2 - collared hole, 10" stell installed, blow hydraulic hose |  | 25 | 07 | 022 | 4 | -2507022D | 2025-07
| 2025-07-23 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | [5 empty] | 12 | 11400 | [12 empty] | 0 | 11940 | 30738.5 | 30738.5 | No drilling completed today, if maintenance provide context -> | Gravel packing on 6 bores |  | 25 | 07 | 023 | 4 | -2507023D | 2025-07
| 2025-07-24 | PL_SF25_RHYD009 | PL_SF25_RHYD010 |  |  | Riley T | 3 | 540 |  |  | 6 | 13 |  |  | 19 | 3525 | 3.25 | 3525 | 0 | 0 | 0 | 0 | 8.75 | [5 empty] | 12 | 8312.5 | [12 empty] | 0 | 12377.5 | 43116 | 43116 | 651.4474 | TSF1 - cement seal, TSF2 - water strike at 16m, gravel from 23-5m, 1m bento seal. TSF3 - collar hole |  | 25 | 07 | 024 | 4 | -2507024D | 2025-07
| 2025-07-25 | PL_SF25_RHYD008 |  |  |  | Riley T | 3 | 540 |  |  |  | 17 |  |  | 17 | 2295 | 1 | 2295 | 0 | 0 | 0 | 0 | 11 | [5 empty] | 12 | 10450 | [12 empty] | 0 | 13285 | 56401 | 56401 | 781.4706 | water strike 20m, install PVC, gravel from 23-5m. 1m bento seal. Maintenance on access roads |  | 25 | 07 | 025 | 4 | -2507025D | 2025-07
| 2025-07-26 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [12 empty] | 0 | 540 | 56941 | 56941 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 07 | 26 | 4 | -250726D | 2025-07
| 2025-07-27 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [12 empty] | 0 | 540 | 57481 | 57481 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 07 | 27 | 4 | -250727D | 2025-07
| 2025-07-28 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | [12 empty] | 0 | 540 | 58021 | 58021 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 07 | 28 | 4 | -250728D | 2025-07
| 2025-07-29 |  |  |  |  | Maurice | 2 | 360 | [6 empty] | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | [12 empty] | 0 | 360 | 58381 | 58381 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 07 | 29 | 4 | -250729D | 2025-07
| 2025-07-30 |  |  |  |  | Maurice | 2 | 360 | [6 empty] | 0 | 0 | 0 | 0 | 3.5 |  |  |  | 8 | Rig at camp, crew doing headworks |  |  |  | 4 | 12 | 7600 | [6 empty] | 0.5 |  |  | 1 |  |  | 201.25 | 8161.25 | 66542.25 | 0 | No drilling completed today, if maintenance provide context ->
| 2025-07-31 | PL_SF25_HYD027 |  |  |  | Maurice | 2 | 360 | [6 empty] | 0 | 0 | 0 | 0 | [5 empty] | Travel to KNX to pick up compressor, tyresd and monuments | 12 |  |  |  | 12 | 4320 | [12 empty] | 0 | 4680 | 71222.25 | 63061 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 07 | 31 | 4 | -250731D | 2025-07
| 2025-08-01 | PL_SF25_HYD027 |  |  |  | Maurice | 2 | 360 | [6 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 12 | Rig at camp, crew doing other works, should this be inactive rate? | [5 empty] | 11400 | [6 empty] | 2 |  |  | 2 |  |  | 431 | 12191 | 83413.25 | 12191 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 1 | 4 | -25081D | 2025-08
| 2025-08-02 |  |  |  |  | Maurice | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 5 | Rig 16 at camp, why maurice has RDO and it says 10hr of work? revise with iDrilling | [5 empty] | 4750 | [10 empty] | 15 |  | 0 | 5290 | 88703.25 | 17481 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 2 | 4 | -25082D | 2025-08
| 2025-08-03 | PL_SF25_HYD002 |  |  |  | Maurice | 3 | 540 |  |  | 8 |  |  |  | 8 | 2360 | 0 | 2360 |  | 2 |  |  | 11.5 | [6 empty] | 10925 |  |  |  | 6 | [8 empty] | 1056 | 14881 | 103584.25 | 32362 | 1860.125 |  |  | 25 | 08 | 3 | 4 | -25083D | 2025-08
| 2025-08-04 |  |  |  |  | Maurice | 2 | 360 | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 | 360 | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 4 | 4 | -25084D | 2025-08
| 2025-08-05 | [6 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 5 | 4 | -25085D | 2025-08
| 2025-08-06 | [6 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 6 | 4 | -25086D | 2025-08
| 2025-08-07 | [6 empty] | 0 | [6 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 7 | 4 | -25087D | 2025-08
| 2025-08-08 | [13 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 8 | 4 | -25088D | 2025-08
| 2025-08-09 | [13 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 9 | 4 | -25089D | 2025-08
| 2025-08-10 | [13 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 10 | 4 | -250810D | 2025-08
| 2025-08-11 | [13 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 11 | 4 | -250811D | 2025-08
| 2025-08-12 | [13 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 12 | 4 | -250812D | 2025-08
| 2025-08-13 | [13 empty] | 0 | 0 | 0 | 0 | [11 empty] | 0 | [12 empty] | 0 |  | 103944.25 | 32722 | No drilling completed today, if maintenance provide context -> |  |  | 25 | 08 | 13 | 4 | -250813D | 2025-08
| 2025-08-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 14 | 4 | -250814D | 2025-08
| 2025-08-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 15 | 4 | -250815D | 2025-08
| 2025-08-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 16 | 4 | -250816D | 2025-08
| 2025-08-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 017 | 4 | -2508017D | 2025-08
| 2025-08-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 018 | 4 | -2508018D | 2025-08
| 2025-08-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 019 | 4 | -2508019D | 2025-08
| 2025-08-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 020 | 4 | -2508020D | 2025-08
| 2025-08-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 021 | 4 | -2508021D | 2025-08
| 2025-08-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 022 | 4 | -2508022D | 2025-08
| 2025-08-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 023 | 4 | -2508023D | 2025-08
| 2025-08-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 024 | 4 | -2508024D | 2025-08
| 2025-08-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 025 | 4 | -2508025D | 2025-08
| 2025-08-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 26 | 4 | -250826D | 2025-08
| 2025-08-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 27 | 4 | -250827D | 2025-08
| 2025-08-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 28 | 4 | -250828D | 2025-08
| 2025-08-29 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 29 | 4 | -250829D | 2025-08
| 2025-08-30 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 30 | 4 | -250830D | 2025-08
| 2025-08-31 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 32722 |  |  |  | 25 | 08 | 31 | 4 | -250831D | 2025-08
| 2025-09-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 1 | 4 | -25091D | 2025-09
| 2025-09-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 2 | 4 | -25092D | 2025-09
| 2025-09-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 3 | 4 | -25093D | 2025-09
| 2025-09-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 4 | 4 | -25094D | 2025-09
| 2025-09-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 5 | 4 | -25095D | 2025-09
| 2025-09-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 6 | 4 | -25096D | 2025-09
| 2025-09-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 7 | 4 | -25097D | 2025-09
| 2025-09-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 8 | 4 | -25098D | 2025-09
| 2025-09-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 9 | 4 | -25099D | 2025-09
| 2025-09-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 10 | 4 | -250910D | 2025-09
| 2025-09-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 11 | 4 | -250911D | 2025-09
| 2025-09-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 12 | 4 | -250912D | 2025-09
| 2025-09-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 13 | 4 | -250913D | 2025-09
| 2025-09-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 14 | 4 | -250914D | 2025-09
| 2025-09-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 15 | 4 | -250915D | 2025-09
| 2025-09-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 16 | 4 | -250916D | 2025-09
| 2025-09-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 017 | 4 | -2509017D | 2025-09
| 2025-09-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 018 | 4 | -2509018D | 2025-09
| 2025-09-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 019 | 4 | -2509019D | 2025-09
| 2025-09-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 020 | 4 | -2509020D | 2025-09
| 2025-09-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 021 | 4 | -2509021D | 2025-09
| 2025-09-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 022 | 4 | -2509022D | 2025-09
| 2025-09-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 023 | 4 | -2509023D | 2025-09
| 2025-09-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 024 | 4 | -2509024D | 2025-09
| 2025-09-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 025 | 4 | -2509025D | 2025-09
| 2025-09-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 26 | 4 | -250926D | 2025-09
| 2025-09-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 27 | 4 | -250927D | 2025-09
| 2025-09-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 28 | 4 | -250928D | 2025-09
| 2025-09-29 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 29 | 4 | -250929D | 2025-09
| 2025-09-30 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 09 | 30 | 4 | -250930D | 2025-09
| 2025-10-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 1 | 4 | -250101D | 2025-10
| 2025-10-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 2 | 4 | -250102D | 2025-10
| 2025-10-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 3 | 4 | -250103D | 2025-10
| 2025-10-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 4 | 4 | -250104D | 2025-10
| 2025-10-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 5 | 4 | -250105D | 2025-10
| 2025-10-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 6 | 4 | -250106D | 2025-10
| 2025-10-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 7 | 4 | -250107D | 2025-10
| 2025-10-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 8 | 4 | -250108D | 2025-10
| 2025-10-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 9 | 4 | -250109D | 2025-10
| 2025-10-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 10 | 4 | -2501010D | 2025-10
| 2025-10-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 11 | 4 | -2501011D | 2025-10
| 2025-10-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 12 | 4 | -2501012D | 2025-10
| 2025-10-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 13 | 4 | -2501013D | 2025-10
| 2025-10-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 14 | 4 | -2501014D | 2025-10
| 2025-10-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 15 | 4 | -2501015D | 2025-10
| 2025-10-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 010 | 16 | 4 | -2501016D | 2025-10
| 2025-10-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 017 | 4 | -2510017D | 2025-10
| 2025-10-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 018 | 4 | -2510018D | 2025-10
| 2025-10-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 019 | 4 | -2510019D | 2025-10
| 2025-10-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 020 | 4 | -2510020D | 2025-10
| 2025-10-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 021 | 4 | -2510021D | 2025-10
| 2025-10-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 022 | 4 | -2510022D | 2025-10
| 2025-10-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 023 | 4 | -2510023D | 2025-10
| 2025-10-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 024 | 4 | -2510024D | 2025-10
| 2025-10-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 025 | 4 | -2510025D | 2025-10
| 2025-10-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 26 | 4 | -251026D | 2025-10
| 2025-10-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 27 | 4 | -251027D | 2025-10
| 2025-10-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 28 | 4 | -251028D | 2025-10
| 2025-10-29 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 29 | 4 | -251029D | 2025-10
| 2025-10-30 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 30 | 4 | -251030D | 2025-10
| 2025-10-31 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 10 | 31 | 4 | -251031D | 2025-10
| 2025-11-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 1 | 4 | -25111D | 2025-11
| 2025-11-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 2 | 4 | -25112D | 2025-11
| 2025-11-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 3 | 4 | -25113D | 2025-11
| 2025-11-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 4 | 4 | -25114D | 2025-11
| 2025-11-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 5 | 4 | -25115D | 2025-11
| 2025-11-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 6 | 4 | -25116D | 2025-11
| 2025-11-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 7 | 4 | -25117D | 2025-11
| 2025-11-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 8 | 4 | -25118D | 2025-11
| 2025-11-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 9 | 4 | -25119D | 2025-11
| 2025-11-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 10 | 4 | -251110D | 2025-11
| 2025-11-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 11 | 4 | -251111D | 2025-11
| 2025-11-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 12 | 4 | -251112D | 2025-11
| 2025-11-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 13 | 4 | -251113D | 2025-11
| 2025-11-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 14 | 4 | -251114D | 2025-11
| 2025-11-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 15 | 4 | -251115D | 2025-11
| 2025-11-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0 |  |  |  | 25 | 11 | 16 | 4 | -251116D | 2025-11
| 2025-11-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-29 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-11-30 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-29 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-30 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2025-12-31 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-29 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-30 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-01-31 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-22 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-23 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-24 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-25 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-26 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-27 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-02-28 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-01 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-02 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-03 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-04 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-05 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-06 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-07 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-08 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-09 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-10 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-11 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-12 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-13 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-14 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-15 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-16 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-17 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-18 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-19 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-20 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
| 2026-03-21 | [13 empty] | 0 | 0 | 0 | 0 | [24 empty] | 0 |  | 103944.25 | 0
Formulas:
Drill Costs = IF([Date]<TODAY(),[Personel (incl driller)]*I3,"")
Total (Fix if not 12hrs) = IF([Date]<TODAY(),([Drill Time]+[Active Rate Total hours (Worktime)]+[Inactive Total]+[Standby Total Hours]+[non-charged Hours]+[Maintenance]),"")
Total Activity hours Cost = IF([Date]<TODAY(),(([Booster (p/hr)]*T3)+([Aux Compressor (p/hr)]*U3)+([Azi Aligner (p/day)]*V3)+([Active Rate Total hours (Worktime)]*X3)+([Inactive Total]*Z3)+([Standby Total Hours]*AA3)+([Survey camera (p/day)]*W3)),"")
Cummulative Cost = IF([Date]<TODAY(),SUM(AT6:[Total Costs]),"")
EOM Cummulative Cost = IF([Date]<TODAY(), SUMIFS(AT8:[Total Costs], BG8:BG19, BG19), "")
Productivity metric Average = IF([Date]>TODAY()-1,"",(IF([Total Daily Meters]=0,"No drilling completed today, if maintenance provide context ->",[Total Costs]/[Total Daily Meters])))
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: rcheal@srk.com.au Reply: Could you please check rates?
Note on AQ3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check rate
Note on I4: Richard Cheal: Includes 1 x SRK field Hydro staying in iDrilling camp
Note on AM4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check rate, we are using 1m3 gravel bags
Note on C19: Richard Cheal: set up on pad
Note on C20: Richard Cheal: collar only
Note on C23: Richard Cheal: set up on pad

## HYD RIG 18
Rig18 | [7 empty] | Drill Costs | [43 empty] | Productivity metric Average
[9 empty] | PB collar | PB | MB collar | MB | [39 empty] | 655.9757
|  | Hole 1 | Hole 2 | Hole 3 | Hole 4 |  |  | 180 | 295 | 185 | 295 | 135 | 0 | 0 |  |  | 950 | 0 | 0 | 0 | 950 | 950 |  | 360 | 420 | 0 | 0 |  |  |  | 121 | 130 | 32 | 44 | 22 | 50 | 200 | 146 | 925 | 600 | 28.5 | 78 | 650 | 187 | 2350 | 18
| Date | Hole ID | Hole ID | Hole ID | Hole ID | Driller Name | Personel (incl driller) | Accom Cost | 14.5" (381mm) | 12.5" (312mm) | 9.5" (230mm) | 6" (150mm) |  |  | Total Daily Meters | Drilling Cost | Drill Time | Booster (p/hr) | Aux Compressor (p/hr) | Azi Aligner (p/day) | Survey camera (p/day) | Active Rate Total hours (Worktime) | Comments | Inactive Total | Standby Total Hours | non-charged Hours | Maintenance | Comments | Total (Fix if not 12hrs) | Total Activity hours Cost | 200mm Class 12 PVC Casing Plain | 200mm Class 12 PVC Casing Slotted | 100mm Class 12 PVC Casing plan | 100mm Class 12 PVC Slotted cas | 100mm Top cap and End cap | 200mm Top cap and End cap | Steel casing 350 NB | Steel casing 250 NB | Steel well cover power coated lockable | Concrete Plinth | Gravel Pack material | Casing centraliser | Drilling Fluids | Bentonite Palets | Mobilisation per bore | Run Casing | Other | Total Consumables Cost (-Accom) | Total Costs | Cummulative Cost | EOM Cummulative Cost | Combined Cost Per Metre | Provide context on Maintenance | Comments
Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 12 | 12 | 14 | 15 | 16 | 17 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 |  |  |  |  | 26 | [17 empty] | 27 | 28 | 29 | 30 | 31 |  | 33 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
| 2025-07-08 |  |  |  |  | Riley T | 3 | 540 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 10 |  | 0 | 0 | 2 |  |  | 12 | 9500 | [16 empty] | 55000 | 55000 | 65040 | 65040 | 65040 | No drilling completed today, if maintenance provide context -> | Mobilisation |  | 35: 25; 36: 07; 37: 8; 38: 4; 39: -25078D; 40: 2025-07
| 2025-07-09 |  |  |  |  | Riley T | 3 | 540 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 10 |  | 0 | 0 | 2 |  |  | 12 | 9500 | [17 empty] | 0 | 10040 | 75080 | 75080 | No drilling completed today, if maintenance provide context -> | Mobilisation |  | 35: 25; 36: 07; 37: 9; 38: 4; 39: -25079D; 40: 2025-07
| 2025-07-10 | PL_SF25_RHYD006 |  |  |  | Riley T | 3 | 540 |  |  | 6 | 66 |  |  | 72 | 10680 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 6 |  |  | 12 | 0 |  |  | 21 | 84 | 1 | [7 empty] | 1 |  | 1 | 105 |  | 9280 | 20500 | 95580 | 95580 | 284.7222 |  |  | 35: 25; 36: 07; 37: 10; 38: 4; 39: -250710D; 40: 2025-07
| 2025-07-11 | PL_SF25_RHYD006 |  |  |  | Riley T | 3 | 540 |  |  |  | 36 |  |  | 36 | 4860 | 4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3.5 | 4.5 |  |  | 12 | 1470 | [17 empty] | 0 | 6870 | 102450 | 102450 | 190.8333 | install 100mm PVC, Drill pad not ready |  | 35: 25; 36: 07; 37: 11; 38: 4; 39: -250711D; 40: 2025-07
| 2025-07-12 | PL_SF25_RHYD004 |  |  |  | Riley T | 3 | 540 |  |  | 6 |  |  |  | 6 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4 | 8 |  |  | 12 | 1680 |  |  | 36 | 84 | 1 |  |  | 6 |  |  |  | 10 | 1 |  | 1 | 120 |  | 10810 | 14800 | 117250 | 117250 | 2466.6667 |  |  | 35: 25; 36: 07; 37: 12; 38: 4; 39: -250712D; 40: 2025-07
| 2025-07-13 | PL_SF25_RHYD004 |  |  |  | Riley T | 4 | 720 |  |  |  | 90 |  |  | 90 | 12150 | 7.75 | 0 | 0 | 0 | 0 | 2 |  | 0 | 0 | 2.25 |  |  | 12 | 1900 | [17 empty] | 0 | 14770 | 132020 | 132020 | 164.1111 |  |  | 35: 25; 36: 07; 37: 13; 38: 4; 39: -250713D; 40: 2025-07
| 2025-07-14 | PL_SF25_RHYD016 |  |  |  | Riley T | 4 | 720 |  |  | 6 | 24 |  |  | 30 | 5010 | 4.5 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 7.5 |  |  | 12 | 0 |  |  | 36 | 66 | 1 |  |  | 6 |  |  |  | 11 | 1 |  | 1 | 101 |  | 9754 | 15484 | 147504 | 147504 | 516.1333 |  |  | 35: 25; 36: 07; 37: 14; 38: 4; 39: -250714D; 40: 2025-07
| 2025-07-15 | PL_SF25_RHYD017 |  |  |  | Riley T | 4 | 720 |  |  |  | 125 |  |  | 125 | 16875 | 7.5 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 4.5 |  |  | 12 | 0 |  |  | 12 | 18 | 1 | [6 empty] | 2 | 1 |  | 1 | 30 |  | 4894 | 22489 | 169993 | 169993 | 179.912 |  |  | 35: 25; 36: 07; 37: 15; 38: 4; 39: -250715D; 40: 2025-07
| 2025-07-16 | PL_SF25_RHYD018 | PL_SF25_RHYD003 |  |  | Riley T | 4 | 720 |  |  | 6 | 90 |  |  | 96 | 13920 | 5.25 | 0 | 0 | 0 | 0 | 6.25 |  | 0.5 | 0 | 0 |  |  | 12 | 6117.5 | 1 | [16 empty] | 0 | 20757.5 | 190750.5 | 190750.5 | 216.224 |  |  | 35: 25; 36: 07; 37: 16; 38: 4; 39: -250716D; 40: 2025-07
| 2025-07-17 | PL_SF25_RHYD004 |  |  |  | Riley T | 4 | 720 |  |  |  | 63 |  |  | 63 | 8505 | 6.25 | 0 | 0 | 0 | 0 | 5.75 |  | 0 | 0 | 0 |  |  | 12 | 5462.5 |  |  | 27 | 96 | 1 | [7 empty] | 1 |  | 1 |  |  | 8110 | 22797.5 | 213548 | 213548 | 361.8651 |  |  | 35: 25; 36: 07; 37: 017; 38: 4; 39: -2507017D; 40: 2025-07
| 2025-07-18 | PL_SF25_RHYD004 |  |  |  | Riley T | 4 | 720 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 12 |  |  | 12 | 0 | [17 empty] | 0 | 720 | 214268 | 214268 | No drilling completed today, if maintenance provide context -> | RDO day for Crew, fitter carrying out maintenance on rig |  | 35: 25; 36: 07; 37: 018; 38: 4; 39: -2507018D; 40: 2025-07
| 2025-07-19 | PL_SF25_RHYD011 |  |  |  | Riley T | 4 | 720 | [6 empty] | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 8 |  | 0 | 0 | 0 | 3.5 |  | 12 | 7600 |  |  | 6 | 12 | 1 | [7 empty] | 1 |  | 1 |  |  | 3742 | 12062 | 226330 | 226330 | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 07; 37: 019; 38: 4; 39: -2507019D; 40: 2025-07
| 2025-07-20 | PL_SF25_RHYD011 |  |  |  | Riley T | 4 | 720 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 |  | 0 | 0 | 9.5 |  |  | 12 | 2375 | [17 empty] | 0 | 3095 | 229425 | 229425 | No drilling completed today, if maintenance provide context -> | Late arrival of Rig16. All day travel to site. |  | 35: 25; 36: 07; 37: 020; 38: 4; 39: -2507020D; 40: 2025-07
| 2025-07-21 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | [17 empty] | 0 | 540 | 229965 | 229965 | No drilling completed today, if maintenance provide context -> | Rod handler broken - awaiting spares from Perth |  | 35: 25; 36: 07; 37: 021; 38: 4; 39: -2507021D; 40: 2025-07
| 2025-07-22 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 |  |  | 4 | 1 | [13 empty] | 172 | 712 | 230677 | 230677 | No drilling completed today, if maintenance provide context -> | Rod handler broken - awaiting spares from Perth |  | 35: 25; 36: 07; 37: 022; 38: 4; 39: -2507022D; 40: 2025-07
| 2025-07-23 |  |  |  |  | Riley T | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | [17 empty] | 0 | 540 | 231217 | 231217 | No drilling completed today, if maintenance provide context -> | Rod handler broken - awaiting spares from Perth |  | 35: 25; 36: 07; 37: 023; 38: 4; 39: -2507023D; 40: 2025-07
| 2025-07-24 |  |  |  |  | Aaron | 3 | 540 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 0 | 0 | [17 empty] | 0 | 540 | 231757 | 231757 | No drilling completed today, if maintenance provide context -> | Rod handler broken - awaiting spares from Perth |  | 35: 25; 36: 07; 37: 024; 38: 4; 39: -2507024D; 40: 2025-07
| 2025-07-25 | PL_SF25_RHYD011 |  |  |  | Aaron | 3 | 540 |  |  |  | 3 |  |  | 3 | 405 | 0.75 | 0 | 0 | 0 | 0 | 5.25 |  | 0 | 0 | 0 | 6 |  | 12 | 4987.5 | [6 empty] | 1 | [10 empty] | 200 | 6132.5 | 237889.5 | 237889.5 | 2044.1667 | HYD25-003 moved 3m away from sump |  | 35: 25; 36: 07; 37: 025; 38: 4; 39: -2507025D; 40: 2025-07
| 2025-07-26 | PL_SF25_RHYD011 |  |  |  | Aaron | 3 | 540 |  |  |  | 27 |  |  | 27 | 3645 | 3.25 | 0 | 0 | 0 | 0 | 8.75 |  | 0 | 0 | 0 |  |  | 12 | 8312.5 | [17 empty] | 0 | 12497.5 | 250387 | 250387 | 462.8704 |  |  | 35: 25; 36: 07; 37: 26; 38: 4; 39: -250726D; 40: 2025-07
| 2025-07-27 | PL_SF25_RHYD011 |  |  |  | Aaron | 3 | 540 |  |  |  | 70 |  |  | 70 | 9450 | 6.5 | 0 | 0 | 0 | 0 | 4.5 |  | 0 | 1 | 0 |  |  | 12 | 4695 | [17 empty] | 0 | 14685 | 265072 | 265072 | 209.7857 | Smoking ceremony |  | 35: 25; 36: 07; 37: 27; 38: 4; 39: -250727D; 40: 2025-07
| 2025-07-28 | PL_SF25_RHYD012 | PL_SF25_RHYD013 |  |  | Aaron | 3 | 540 |  |  | 2 | 22 |  |  | 24 | 3560 | 1.5 | 0 | 0 | 0 | 0 | 10.5 |  | 0 | 0 | 0 |  |  | 12 | 9975 | [14 empty] | 1 |  |  | 2350 | 16425 | 281497 | 281497 | 684.375 |  |  | 35: 25; 36: 07; 37: 28; 38: 4; 39: -250728D; 40: 2025-07
| 2025-07-29 | PL_SF25_RHYD013 |  |  |  | Aaron | 3 | 540 | [6 empty] | 0 | 0 | 0 | [11 empty] | 0 | 0 |  |  | 1 | 4 | [13 empty] | 208 | 748 | 282245 | 282245 | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 07; 37: 29; 38: 4; 39: -250729D; 40: 2025-07
| 2025-07-30 | PL_SF25_RHYD014 | PL_SF25_RHYD015 |  |  | Aaron | 3 | 540 |  |  | 2 | 32 |  |  | 34 | 4910 | 3.75 |  |  |  |  | 7.25 |  |  |  |  | 1 |  | 12 | 6887.5 |  |  | 2 | 8 |  |  | 2 | [7 empty] | 1 |  |  | 3166 | 15503.5 | 297748.5 | 297748.5 | 455.9853 |  |  | 35: 25; 36: 07; 37: 30; 38: 4; 39: -250730D; 40: 2025-07
| 2025-07-31 | PL_SF25_RHYD028 |  |  |  | Aaron | 3 | 540 |  |  | 2 | 72 |  |  | 74 | 10310 | 6.25 | 1 | 5 |  |  | 5.75 |  | 0 | 0 | 0 | 0 |  | 12 | 5462.5 |  |  | 3 | 12 | [13 empty] | 624 | 16936.5 | 314685 | 314685 | 228.8716 | Note rig in use until 2pm, then at camp for maintenance |  | 35: 25; 36: 07; 37: 31; 38: 4; 39: -250731D; 40: 2025-07
| 2025-08-01 | PL_SF25_RHYD028 | PL_SF25_RHYD027 |  |  | Aaron | 3 | 540 |  |  | 2 | 26 |  |  | 28 | 4100 | 4.75 |  | 3.25 |  |  | 7.25 | [6 empty] | 12 | 6887.5 | [6 empty] | 2 | [7 empty] | 1 |  |  | 2750 | 14277.5 | 328962.5 | 14277.5 | 509.9107 |  |  | 35: 25; 36: 08; 37: 1; 38: 4; 39: -25081D; 40: 2025-08
| 2025-08-02 | PL_SF25_RHYD027 |  |  |  | Aaron | 3 | 540 |  |  | 7 | 23 |  |  | 30 | 5170 | 5 |  |  |  |  | 7 | [6 empty] | 12 | 6650 |  |  | 6 | 18 |  |  | 4 | [5 empty] | 1 |  | 1 |  |  | 4784 | 17144 | 346106.5 | 31421.5 | 571.4667 |  |  | 35: 25; 36: 08; 37: 2; 38: 4; 39: -25082D; 40: 2025-08
| 2025-08-03 |  |  |  |  | Aaron | 3 | 540 |  |  | 8 |  |  |  | 8 | 2360 | 0.75 |  | 2 |  |  | 10.25 |  |  |  |  | 1 |  | 12 | 9737.5 |  |  | 6 | [14 empty] | 192 | 12829.5 | 358936 | 44251 | 1603.6875 |  |  | 35: 25; 36: 08; 37: 3; 38: 4; 39: -25083D; 40: 2025-08
2025-08-04
| 2025-08-05 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 5; 38: 4; 39: -25085D; 40: 2025-08
| 2025-08-06 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 6; 38: 4; 39: -25086D; 40: 2025-08
| 2025-08-07 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 7; 38: 4; 39: -25087D; 40: 2025-08
| 2025-08-08 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 8; 38: 4; 39: -25088D; 40: 2025-08
| 2025-08-09 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 9; 38: 4; 39: -25089D; 40: 2025-08
| 2025-08-10 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> | Rod handler Stripped down and fixed |  | 35: 25; 36: 08; 37: 10; 38: 4; 39: -250810D; 40: 2025-08
| 2025-08-11 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> | SDR18 RHS Track repaired, seals replaced within tensioning cylinder, Brake pack replaced on rod handler, cup & Arm re mounted |  | 35: 25; 36: 08; 37: 11; 38: 4; 39: -250811D; 40: 2025-08
| 2025-08-12 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 12; 38: 4; 39: -250812D; 40: 2025-08
| 2025-08-13 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 13; 38: 4; 39: -250813D; 40: 2025-08
| 2025-08-14 | [13 empty] | 0 | 0 | 0 | [12 empty] | 0 | [17 empty] | 0 | #REF! | #REF! | #REF! | No drilling completed today, if maintenance provide context -> |  |  | 35: 25; 36: 08; 37: 14; 38: 4; 39: -250814D; 40: 2025-08
| 2025-08-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 15; 38: 4; 39: -250815D; 40: 2025-08
| 2025-08-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 16; 38: 4; 39: -250816D; 40: 2025-08
| 2025-08-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 17; 38: 4; 39: -250817D; 40: 2025-08
| 2025-08-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 018; 38: 4; 39: -2508018D; 40: 2025-08
| 2025-08-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 019; 38: 4; 39: -2508019D; 40: 2025-08
| 2025-08-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 020; 38: 4; 39: -2508020D; 40: 2025-08
| 2025-08-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 021; 38: 4; 39: -2508021D; 40: 2025-08
| 2025-08-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 022; 38: 4; 39: -2508022D; 40: 2025-08
| 2025-08-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 023; 38: 4; 39: -2508023D; 40: 2025-08
| 2025-08-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 024; 38: 4; 39: -2508024D; 40: 2025-08
| 2025-08-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 025; 38: 4; 39: -2508025D; 40: 2025-08
| 2025-08-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 026; 38: 4; 39: -2508026D; 40: 2025-08
| 2025-08-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 27; 38: 4; 39: -250827D; 40: 2025-08
| 2025-08-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 28; 38: 4; 39: -250828D; 40: 2025-08
| 2025-08-29 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 29; 38: 4; 39: -250829D; 40: 2025-08
| 2025-08-30 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 30; 38: 4; 39: -250830D; 40: 2025-08
| 2025-08-31 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | #REF! |  |  |  | 35: 25; 36: 08; 37: 31; 38: 4; 39: -250831D; 40: 2025-08
| 2025-09-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 1; 38: 4; 39: -25091D; 40: 2025-09
| 2025-09-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 2; 38: 4; 39: -25092D; 40: 2025-09
| 2025-09-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 3; 38: 4; 39: -25093D; 40: 2025-09
| 2025-09-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 4; 38: 4; 39: -25094D; 40: 2025-09
| 2025-09-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 5; 38: 4; 39: -25095D; 40: 2025-09
| 2025-09-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 6; 38: 4; 39: -25096D; 40: 2025-09
| 2025-09-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 7; 38: 4; 39: -25097D; 40: 2025-09
| 2025-09-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 8; 38: 4; 39: -25098D; 40: 2025-09
| 2025-09-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 9; 38: 4; 39: -25099D; 40: 2025-09
| 2025-09-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 10; 38: 4; 39: -250910D; 40: 2025-09
| 2025-09-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 11; 38: 4; 39: -250911D; 40: 2025-09
| 2025-09-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 12; 38: 4; 39: -250912D; 40: 2025-09
| 2025-09-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 13; 38: 4; 39: -250913D; 40: 2025-09
| 2025-09-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 14; 38: 4; 39: -250914D; 40: 2025-09
| 2025-09-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 15; 38: 4; 39: -250915D; 40: 2025-09
| 2025-09-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 16; 38: 4; 39: -250916D; 40: 2025-09
| 2025-09-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 17; 38: 4; 39: -250917D; 40: 2025-09
| 2025-09-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 018; 38: 4; 39: -2509018D; 40: 2025-09
| 2025-09-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 019; 38: 4; 39: -2509019D; 40: 2025-09
| 2025-09-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 020; 38: 4; 39: -2509020D; 40: 2025-09
| 2025-09-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 021; 38: 4; 39: -2509021D; 40: 2025-09
| 2025-09-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 022; 38: 4; 39: -2509022D; 40: 2025-09
| 2025-09-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 023; 38: 4; 39: -2509023D; 40: 2025-09
| 2025-09-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 024; 38: 4; 39: -2509024D; 40: 2025-09
| 2025-09-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 025; 38: 4; 39: -2509025D; 40: 2025-09
| 2025-09-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 026; 38: 4; 39: -2509026D; 40: 2025-09
| 2025-09-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 27; 38: 4; 39: -250927D; 40: 2025-09
| 2025-09-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 28; 38: 4; 39: -250928D; 40: 2025-09
| 2025-09-29 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 29; 38: 4; 39: -250929D; 40: 2025-09
| 2025-09-30 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 09; 37: 30; 38: 4; 39: -250930D; 40: 2025-09
| 2025-10-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 1; 38: 4; 39: -250101D; 40: 2025-10
| 2025-10-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 2; 38: 4; 39: -250102D; 40: 2025-10
| 2025-10-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 3; 38: 4; 39: -250103D; 40: 2025-10
| 2025-10-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 4; 38: 4; 39: -250104D; 40: 2025-10
| 2025-10-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 5; 38: 4; 39: -250105D; 40: 2025-10
| 2025-10-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 6; 38: 4; 39: -250106D; 40: 2025-10
| 2025-10-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 7; 38: 4; 39: -250107D; 40: 2025-10
| 2025-10-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 8; 38: 4; 39: -250108D; 40: 2025-10
| 2025-10-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 9; 38: 4; 39: -250109D; 40: 2025-10
| 2025-10-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 10; 38: 4; 39: -2501010D; 40: 2025-10
| 2025-10-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 11; 38: 4; 39: -2501011D; 40: 2025-10
| 2025-10-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 12; 38: 4; 39: -2501012D; 40: 2025-10
| 2025-10-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 13; 38: 4; 39: -2501013D; 40: 2025-10
| 2025-10-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 14; 38: 4; 39: -2501014D; 40: 2025-10
| 2025-10-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 15; 38: 4; 39: -2501015D; 40: 2025-10
| 2025-10-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 16; 38: 4; 39: -2501016D; 40: 2025-10
| 2025-10-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 010; 37: 17; 38: 4; 39: -2501017D; 40: 2025-10
| 2025-10-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 018; 38: 4; 39: -2510018D; 40: 2025-10
| 2025-10-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 019; 38: 4; 39: -2510019D; 40: 2025-10
| 2025-10-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 020; 38: 4; 39: -2510020D; 40: 2025-10
| 2025-10-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 021; 38: 4; 39: -2510021D; 40: 2025-10
| 2025-10-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 022; 38: 4; 39: -2510022D; 40: 2025-10
| 2025-10-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 023; 38: 4; 39: -2510023D; 40: 2025-10
| 2025-10-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 024; 38: 4; 39: -2510024D; 40: 2025-10
| 2025-10-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 025; 38: 4; 39: -2510025D; 40: 2025-10
| 2025-10-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 026; 38: 4; 39: -2510026D; 40: 2025-10
| 2025-10-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 27; 38: 4; 39: -251027D; 40: 2025-10
| 2025-10-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 28; 38: 4; 39: -251028D; 40: 2025-10
| 2025-10-29 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 29; 38: 4; 39: -251029D; 40: 2025-10
| 2025-10-30 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 30; 38: 4; 39: -251030D; 40: 2025-10
| 2025-10-31 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 10; 37: 31; 38: 4; 39: -251031D; 40: 2025-10
| 2025-11-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 1; 38: 4; 39: -25111D; 40: 2025-11
| 2025-11-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 2; 38: 4; 39: -25112D; 40: 2025-11
| 2025-11-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 3; 38: 4; 39: -25113D; 40: 2025-11
| 2025-11-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 4; 38: 4; 39: -25114D; 40: 2025-11
| 2025-11-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 5; 38: 4; 39: -25115D; 40: 2025-11
| 2025-11-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 6; 38: 4; 39: -25116D; 40: 2025-11
| 2025-11-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 7; 38: 4; 39: -25117D; 40: 2025-11
| 2025-11-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 8; 38: 4; 39: -25118D; 40: 2025-11
| 2025-11-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 9; 38: 4; 39: -25119D; 40: 2025-11
| 2025-11-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 10; 38: 4; 39: -251110D; 40: 2025-11
| 2025-11-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 11; 38: 4; 39: -251111D; 40: 2025-11
| 2025-11-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 12; 38: 4; 39: -251112D; 40: 2025-11
| 2025-11-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 13; 38: 4; 39: -251113D; 40: 2025-11
| 2025-11-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 14; 38: 4; 39: -251114D; 40: 2025-11
| 2025-11-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 15; 38: 4; 39: -251115D; 40: 2025-11
| 2025-11-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 16; 38: 4; 39: -251116D; 40: 2025-11
| 2025-11-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0 |  |  |  | 35: 25; 36: 11; 37: 17; 38: 4; 39: -251117D; 40: 2025-11
| 2025-11-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-29 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-11-30 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-29 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-30 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2025-12-31 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-29 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-30 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-01-31 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-23 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-24 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-25 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-26 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-27 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-02-28 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-01 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-02 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-03 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-04 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-05 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-06 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-07 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-08 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-09 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-10 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-11 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-12 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-13 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-14 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-15 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-16 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-17 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-18 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-19 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-20 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-21 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
| 2026-03-22 | [13 empty] | 0 | 0 | 0 | [30 empty] | 0 |  |  | 0
Formulas:
EOM Cummulative Cost = IF([Date]<TODAY(), SUMIFS([Total Costs]:AX6, BK6:BK6, BK6), "")
EOM Cummulative Cost = IF([Date]<TODAY(), SUMIFS(AX6:[Total Costs], BK6:BK7, BK7), "")
Productivity metric Average = IF([Date]>TODAY()-1,"",(IF([Total Daily Meters]=0,"No drilling completed today, if maintenance provide context ->",[Total Costs]/[Total Daily Meters])))
Note on AF3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check rate
Note on AG3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check rate
Note on AK3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check rate
Note on AL3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: check rate
Note on AH8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HYD25-006A
Note on L10: Richard Cheal: Drilled with 12in. Charged at 9.5in
Note on AH10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HYD25-010B

## Template
RIG 41 | [11 empty] | Hole 1 | [5 empty] | Hole 2
|  |  | Hole 1 | Hole 2 | Hole 1 | Hole 1 | Hole 2 | Hole 2 |  |  | 130 | Diameter 1 |  |  | Diameter 2 |  |  | Diameter 1 |  |  | Diameter 2 |  |  | 175 |  |  | 155 | 420 |  | 460 | 360 | 360
| Date | Shift | Hole ID | Hole ID | Diameter (1) | Diameter (2) | Diameter (1) | Diameter (2) | Driller Name | Personel (incl driller) | Accom Cost | Depth From | Depth To | Length | Depth From | Depth To | Length | Depth From | Depth To | Length | Depth From | Depth To | Length | Drilling Cost | Cost per metre | Charged Drilling Cost | Ori Tool | Gyro Tool | Tool ID | Active Rate Total hours | Inactive Total | Standby Total Hours | Total Activity hours Cost | Total Consumables Cost | Comments
Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
| 2025-06-01 05:00 | DS 5am
| 2025-06-01 17:00 | NS 5pm
| 2025-06-02 05:00 | DS 5am
| 2025-06-02 17:00 | NS 5pm
| 2025-06-03 05:00 | DS 5am
| 2025-06-03 17:00 | NS 5pm
| 2025-06-04 05:00 | DS 5am
| 2025-06-04 17:00 | NS 5pm
| 2025-06-05 05:00 | DS 5am
| 2025-06-05 17:00 | NS 5pm
| 2025-06-06 05:00 | DS 5am
| 2025-06-06 17:00 | NS 5pm
| 2025-06-07 05:00 | DS 5am
| 2025-06-07 17:00 | NS 5pm
| 2025-06-08 05:00 | DS 5am
| 2025-06-08 17:00 | NS 5pm
| 2025-06-09 05:00 | DS 5am
| 2025-06-09 17:00 | NS 5pm
| 2025-06-10 05:00 | DS 5am
| 2025-06-10 17:00 | NS 5pm
| 2025-06-11 05:00 | DS 5am
| 2025-06-11 17:00 | NS 5pm
| 2025-06-12 05:00 | DS 5am
| 2025-06-12 17:00 | NS 5pm
| 2025-06-13 05:00 | DS 5am
| 2025-06-13 17:00 | NS 5pm
| 2025-06-14 05:00 | DS 5am
| 2025-06-14 17:00 | NS 5pm
| 2025-06-15 05:00 | DS 5am
| 2025-06-15 17:00 | NS 5pm
| 2025-06-16 05:00 | DS 5am
| 2025-06-16 17:00 | NS 5pm
| 2025-06-17 05:00 | DS 5am
| 2025-06-17 17:00 | NS 5pm
| 2025-06-18 05:00 | DS 5am
| 2025-06-18 17:00 | NS 5pm
| 2025-06-19 05:00 | DS 5am
| 2025-06-19 17:00 | NS 5pm
| 2025-06-20 05:00 | DS 5am
| 2025-06-20 17:00 | NS 5pm
| 2025-06-21 05:00 | DS 5am
| 2025-06-21 17:00 | NS 5pm
| 2025-06-22 05:00 | DS 5am
| 2025-06-22 17:00 | NS 5pm
| 2025-06-23 05:00 | DS 5am
| 2025-06-23 17:00 | NS 5pm
| 2025-06-24 05:00 | DS 5am
| 2025-06-24 17:00 | NS 5pm
| 2025-06-25 05:00 | DS 5am
| 2025-06-25 17:00 | NS 5pm
| 2025-06-26 05:00 | DS 5am
| 2025-06-26 17:00 | NS 5pm
| 2025-06-27 05:00 | DS 5am
| 2025-06-27 17:00 | NS 5pm
| 2025-06-28 05:00 | DS 5am
| 2025-06-28 17:00 | NS 5pm
| 2025-06-29 05:00 | DS 5am
| 2025-06-29 17:00 | NS 5pm
| 2025-06-30 05:00 | DS 5am
| 2025-06-30 17:00 | NS 5pm
| 2025-07-01 05:00 | DS 5am
| 2025-07-01 17:00 | NS 5pm
| 2025-07-02 05:00 | DS 5am
| 2025-07-02 17:00 | NS 5pm
| 2025-07-03 05:00 | DS 5am
| 2025-07-03 17:00 | NS 5pm
| 2025-07-04 05:00 | DS 5am
| 2025-07-04 17:00 | NS 5pm
| 2025-07-05 05:00 | DS 5am
| 2025-07-05 17:00 | NS 5pm
| 2025-07-06 05:00 | DS 5am
| 2025-07-06 17:00 | NS 5pm
| 2025-07-07 05:00 | DS 5am
| 2025-07-07 17:00 | NS 5pm
| 2025-07-08 05:00 | DS 5am
| 2025-07-08 17:00 | NS 5pm
| 2025-07-09 05:00 | DS 5am
| 2025-07-09 17:00 | NS 5pm
| 2025-07-10 05:00 | DS 5am
| 2025-07-10 17:00 | NS 5pm
| 2025-07-11 05:00 | DS 5am
| 2025-07-11 17:00 | NS 5pm
| 2025-07-12 05:00 | DS 5am
| 2025-07-12 17:00 | NS 5pm
| 2025-07-13 05:00 | DS 5am
| 2025-07-13 17:00 | NS 5pm
| 2025-07-14 05:00 | DS 5am
| 2025-07-14 17:00 | NS 5pm
| 2025-07-15 05:00 | DS 5am
| 2025-07-15 17:00 | NS 5pm
| 2025-07-16 05:00 | DS 5am
| 2025-07-16 17:00 | NS 5pm
| 2025-07-17 05:00 | DS 5am
| 2025-07-17 17:00 | NS 5pm
| 2025-07-18 05:00 | DS 5am
| 2025-07-18 17:00 | NS 5pm
| 2025-07-19 05:00 | DS 5am
| 2025-07-19 17:00 | NS 5pm
| 2025-07-20 05:00 | DS 5am
| 2025-07-20 17:00 | NS 5pm
| 2025-07-21 05:00 | DS 5am
| 2025-07-21 17:00 | NS 5pm
| 2025-07-22 05:00 | DS 5am
| 2025-07-22 17:00 | NS 5pm
| 2025-07-23 05:00 | DS 5am
| 2025-07-23 17:00 | NS 5pm
| 2025-07-24 05:00 | DS 5am
| 2025-07-24 17:00 | NS 5pm
| 2025-07-25 05:00 | DS 5am
| 2025-07-25 17:00 | NS 5pm
| 2025-07-26 05:00 | DS 5am
| 2025-07-26 17:00 | NS 5pm
| 2025-07-27 05:00 | DS 5am
| 2025-07-27 17:00 | NS 5pm
| 2025-07-28 05:00 | DS 5am
| 2025-07-28 17:00 | NS 5pm
| 2025-07-29 05:00 | DS 5am
| 2025-07-29 17:00 | NS 5pm
| 2025-07-30 05:00 | DS 5am
| 2025-07-30 17:00 | NS 5pm
| 2025-07-31 05:00 | DS 5am
| 2025-07-31 17:00 | NS 5pm
| 2025-08-01 05:00 | DS 5am
| 2025-08-01 17:00 | NS 5pm
| 2025-08-02 05:00 | DS 5am
| 2025-08-02 17:00 | NS 5pm
| 2025-08-03 05:00 | DS 5am
| 2025-08-03 17:00 | NS 5pm
| 2025-08-04 05:00 | DS 5am
| 2025-08-04 17:00 | NS 5pm
| 2025-08-05 05:00 | DS 5am
| 2025-08-05 17:00 | NS 5pm
| 2025-08-06 05:00 | DS 5am
| 2025-08-06 17:00 | NS 5pm
| 2025-08-07 05:00 | DS 5am
| 2025-08-07 17:00 | NS 5pm
| 2025-08-08 05:00 | DS 5am
| 2025-08-08 17:00 | NS 5pm
| 2025-08-09 05:00 | DS 5am
| 2025-08-09 17:00 | NS 5pm
| 2025-08-10 05:00 | DS 5am
| 2025-08-10 17:00 | NS 5pm
| 2025-08-11 05:00 | DS 5am
| 2025-08-11 17:00 | NS 5pm
| 2025-08-12 05:00 | DS 5am
| 2025-08-12 17:00 | NS 5pm
| 2025-08-13 05:00 | DS 5am
| 2025-08-13 17:00 | NS 5pm
| 2025-08-14 05:00 | DS 5am
| 2025-08-14 17:00 | NS 5pm
| 2025-08-15 05:00 | DS 5am
| 2025-08-15 17:00 | NS 5pm
| 2025-08-16 05:00 | DS 5am
| 2025-08-16 17:00 | NS 5pm
| 2025-08-17 05:00 | DS 5am
| 2025-08-17 17:00 | NS 5pm
| 2025-08-18 05:00 | DS 5am
| 2025-08-18 17:00 | NS 5pm
| 2025-08-19 05:00 | DS 5am
| 2025-08-19 17:00 | NS 5pm
| 2025-08-20 05:00 | DS 5am
| 2025-08-20 17:00 | NS 5pm
| 2025-08-21 05:00 | DS 5am
| 2025-08-21 17:00 | NS 5pm
| 2025-08-22 05:00 | DS 5am
| 2025-08-22 17:00 | NS 5pm
| 2025-08-23 05:00 | DS 5am
| 2025-08-23 17:00 | NS 5pm
| 2025-08-24 05:00 | DS 5am
| 2025-08-24 17:00 | NS 5pm
| 2025-08-25 05:00 | DS 5am
| 2025-08-25 17:00 | NS 5pm
| 2025-08-26 05:00 | DS 5am
| 2025-08-26 17:00 | NS 5pm
| 2025-08-27 05:00 | DS 5am
| 2025-08-27 17:00 | NS 5pm
| 2025-08-28 05:00 | DS 5am
| 2025-08-28 17:00 | NS 5pm
| 2025-08-29 05:00 | DS 5am
| 2025-08-29 17:00 | NS 5pm
| 2025-08-30 05:00 | DS 5am
| 2025-08-30 17:00 | NS 5pm
| 2025-08-31 05:00 | DS 5am
| 2025-08-31 17:00 | NS 5pm
| 2025-09-01 05:00 | DS 5am
| 2025-09-01 17:00 | NS 5pm
| 2025-09-02 05:00 | DS 5am
| 2025-09-02 17:00 | NS 5pm
| 2025-09-03 05:00 | DS 5am
| 2025-09-03 17:00 | NS 5pm
| 2025-09-04 05:00 | DS 5am
| 2025-09-04 17:00 | NS 5pm
| 2025-09-05 05:00 | DS 5am
| 2025-09-05 17:00 | NS 5pm
| 2025-09-06 05:00 | DS 5am
| 2025-09-06 17:00 | NS 5pm
| 2025-09-07 05:00 | DS 5am
| 2025-09-07 17:00 | NS 5pm
| 2025-09-08 05:00 | DS 5am
| 2025-09-08 17:00 | NS 5pm
| 2025-09-09 05:00 | DS 5am
| 2025-09-09 17:00 | NS 5pm
| 2025-09-10 05:00 | DS 5am
| 2025-09-10 17:00 | NS 5pm
| 2025-09-11 05:00 | DS 5am
| 2025-09-11 17:00 | NS 5pm
| 2025-09-12 05:00 | DS 5am
| 2025-09-12 17:00 | NS 5pm
| 2025-09-13 05:00 | DS 5am
| 2025-09-13 17:00 | NS 5pm
| 2025-09-14 05:00 | DS 5am
| 2025-09-14 17:00 | NS 5pm
| 2025-09-15 05:00 | DS 5am
| 2025-09-15 17:00 | NS 5pm
| 2025-09-16 05:00 | DS 5am
| 2025-09-16 17:00 | NS 5pm
| 2025-09-17 05:00 | DS 5am
| 2025-09-17 17:00 | NS 5pm
| 2025-09-18 05:00 | DS 5am
| 2025-09-18 17:00 | NS 5pm
| 2025-09-19 05:00 | DS 5am
| 2025-09-19 17:00 | NS 5pm
| 2025-09-20 05:00 | DS 5am
| 2025-09-20 17:00 | NS 5pm
| 2025-09-21 05:00 | DS 5am
| 2025-09-21 17:00 | NS 5pm
| 2025-09-22 05:00 | DS 5am
| 2025-09-22 17:00 | NS 5pm
| 2025-09-23 05:00 | DS 5am
| 2025-09-23 17:00 | NS 5pm
| 2025-09-24 05:00 | DS 5am
| 2025-09-24 17:00 | NS 5pm
| 2025-09-25 05:00 | DS 5am
| 2025-09-25 17:00 | NS 5pm
| 2025-09-26 05:00 | DS 5am
| 2025-09-26 17:00 | NS 5pm
| 2025-09-27 05:00 | DS 5am
| 2025-09-27 17:00 | NS 5pm
| 2025-09-28 05:00 | DS 5am
| 2025-09-28 17:00 | NS 5pm
| 2025-09-29 05:00 | DS 5am
| 2025-09-29 17:00 | NS 5pm
| 2025-09-30 05:00 | DS 5am
| 2025-09-30 17:00 | NS 5pm
| 2025-10-01 05:00 | DS 5am
| 2025-10-01 17:00 | NS 5pm
| 2025-10-02 05:00 | DS 5am
| 2025-10-02 17:00 | NS 5pm
| 2025-10-03 05:00 | DS 5am
| 2025-10-03 17:00 | NS 5pm
| 2025-10-04 05:00 | DS 5am
| 2025-10-04 17:00 | NS 5pm
| 2025-10-05 05:00 | DS 5am
| 2025-10-05 17:00 | NS 5pm
| 2025-10-06 05:00 | DS 5am
| 2025-10-06 17:00 | NS 5pm
| 2025-10-07 05:00 | DS 5am
| 2025-10-07 17:00 | NS 5pm
| 2025-10-08 05:00 | DS 5am
| 2025-10-08 17:00 | NS 5pm
| 2025-10-09 05:00 | DS 5am
| 2025-10-09 17:00 | NS 5pm
| 2025-10-10 05:00 | DS 5am
| 2025-10-10 17:00 | NS 5pm
| 2025-10-11 05:00 | DS 5am
| 2025-10-11 17:00 | NS 5pm
| 2025-10-12 05:00 | DS 5am
| 2025-10-12 17:00 | NS 5pm
| 2025-10-13 05:00 | DS 5am
| 2025-10-13 17:00 | NS 5pm
| 2025-10-14 05:00 | DS 5am
| 2025-10-14 17:00 | NS 5pm
| 2025-10-15 05:00 | DS 5am
| 2025-10-15 17:00 | NS 5pm
| 2025-10-16 05:00 | DS 5am
| 2025-10-16 17:00 | NS 5pm
| 2025-10-17 05:00 | DS 5am
| 2025-10-17 17:00 | NS 5pm
| 2025-10-18 05:00 | DS 5am
| 2025-10-18 17:00 | NS 5pm
| 2025-10-19 05:00 | DS 5am
| 2025-10-19 17:00 | NS 5pm
| 2025-10-20 05:00 | DS 5am
| 2025-10-20 17:00 | NS 5pm
| 2025-10-21 05:00 | DS 5am
| 2025-10-21 17:00 | NS 5pm
| 2025-10-22 05:00 | DS 5am
| 2025-10-22 17:00 | NS 5pm
| 2025-10-23 05:00 | DS 5am
| 2025-10-23 17:00 | NS 5pm
| 2025-10-24 05:00 | DS 5am
| 2025-10-24 17:00 | NS 5pm
| 2025-10-25 05:00 | DS 5am
| 2025-10-25 17:00 | NS 5pm
| 2025-10-26 05:00 | DS 5am
| 2025-10-26 17:00 | NS 5pm
| 2025-10-27 05:00 | DS 5am
| 2025-10-27 17:00 | NS 5pm
| 2025-10-28 05:00 | DS 5am
| 2025-10-28 17:00 | NS 5pm
| 2025-10-29 05:00 | DS 5am
| 2025-10-29 17:00 | NS 5pm
| 2025-10-30 05:00 | DS 5am
| 2025-10-30 17:00 | NS 5pm

## Planned_Metres_Data
Budget | Hole Type | Campaign | Planned Holes | Planned Metres
DFS Met Sample collection (24 no. Holes, 2,045m) | DD | MET | 24 | 2045
Geotechnical drilling (12 no. HQ Holes, 1040m) | DD | GT | 12 | 1040
Infill Drilling | DD | INF | 8 | 1260
Infill Drilling | RC | INF | 155 | 18025
G-Vein Resource Extension | RC | RD | 39 | 4935
G-Vein Resource Extension | DD | RD | 5 | 581
A-Vein Resource Extension | DD | RD | 5 | 450
A-Vein Resource Extension | RC | RD | 42 | 3735
Dingo Vein Exploration | RC | EXP | 7 | 630
Southern Veins Exploration | RC | EXP | 10 | 900

## Budget Recon (hidden)
DD38
Row Labels | Sum of Total Activity Hours Cost | Sum of Charged Drilling Cost | Sum of Total Costs | Sum of Total Consumables Cost (-accom) | Sum of Accom Cost | Count of Date
GT | 37710 | 48535 | 99913.94 | 1863.94 | 6630 | 17
MET | 53160 | 124760 | 208734.04 | 7389.04 | 13650 | 34
Grand Total | 90870 | 173295 | 308647.98 | 9252.98 | 20280 | 51
DD41
Row Labels | Sum of Total Activity Hours Cost | Sum of Charged Drilling Cost | Sum of Total Costs | Sum of Total Consumables Cost (-Accom) | Sum of Accom Cost | Count of Date
GT | 22975 | 74968.5 | 111026.32 | 887.82 | 7020 | 18
MET | 114930 | 258602.5 | 447310.89 | 22658.39 | 30420 | 72
Grand Total | 137905 | 333571 | 558337.21 | 23546.21 | 37440 | 90
Row Labels | Sum of Total Activity hours Cost | Sum of Charged Drilling Cost | Sum of Accom Cost | Sum of Total Costs | Count of Date | Sum of Booster (p/hr) | Sum of Aux Compressor (p/hr)
INF | 141265 | 231128.75 | 16250 | 419218.17 | 37 | 166.25 | 167.25
Grand Total | 141265 | 231128.75 | 16250 | 419218.17 | 37 | 166.25 | 167.25
Output from | 2026-03-27 | [8 empty] | Out of budget
Row Labels | Sum of Total Activity Hours Cost | Sum of Total Costs | Sum of Total Consumables Cost (-accom) | Sum of Accom Cost | Count of Date |  | Tool Hire | Auxillary Equipment Cost | In budget | Activity costs
GT | 37710 | 99913.94 | 1863.94 | 6630 | 17 | 9 | 5175 |  | 62203.94 | 37710
MET | 53160 | 208734.04 | 7389.04 | 13650 | 34 | 17 | 9775 |  | 155574.04 | 53160
DD41
Row Labels | Sum of Total Activity Hours Cost | Sum of Total Costs | Sum of Total Consumables Cost (-Accom) | Sum of Accom Cost | Count of Date
GT | 22975 | 111026.32 | 887.82 | 7020 | 18 | 9 | 5175 |  | 88051.32 | 22975
MET | 114930 | 447310.89 | 22658.39 | 30420 | 72 | 36 | 20700 |  | 332380.89 | 114930
Row Labels | Sum of Total Activity hours Cost | Sum of Charged Drilling Cost |  | Sum of Accom Cost | Sum of Total Costs | Count of Date
INF | 141265 | 231128.75 | 32094.13 | 16250 | 419218.17 | 37 | 37 | 22015 | 36795 | 89863.75 | 141265
Grand total across all rigs | 370040 | 1098113.94 | 49049.19 | 476938.17 | 178 |  |  |  | 728073.94 | 370040
|  | In Budget | Out of Budget | Total | Comments
Civil Support (2025) | 1244828.0008
Road Allignment Survey & Pickup of 2024 collars | 49300 | ???
Historic Drill Collar pickups | 8000
Access Tracks, Pads, Sumps, Testpits | 600000 | 523975 |  | 523975 | In budget includes demob
New Access Road allignment clearing & Testpits | 200000 | 130568 |  | 130568
Camp/Accommodation | 100000 | 50160 |  | 50160
Rehabilitation (5% of Direct) | 177645.715 |  |  | 0
Final Survey of New Collars | 56000 | 10752.3 |  | 10752.3 | Not yet complete. Tivan asset acquired.
Contingnency (5%) | 53882.2858 |  |  | 0
Hydrogeological Drilling (2025) | 1543401.8 |  |  | 0 | Total Activity Hours
Preliminaries | 130000 |  |  | 0
27 x Monitoring / TSF Bores | 788436 | 106825 |  | 106825
1 x Production Bore | 71357 |  |  | 0
Pump Testing 1 x Bore | 39000 |  |  | 0
Ancillary Equipment & Materials | 185378.8 | 59818 |  | 59818
SRK Supervision | 329230 |  |  | 0 |  | Projected Required Budget
Resource & Geotech Drilling (20250221) | 3326536.8648 |  |  | 1304924.39 |  | 3179182.8861
DFS Met Sample collection (24 no. Holes, 2,045m) | 518076.875 | 383362.5 | 168090 | 551452.5 | 33375.625 | 71708.7415 | 200m left to drill @ 359$/m
[BL1] Infill Drilling (163 no. Holes, 19,285m) | 1356547.5 | 289155.07 | 141265 | 430420.07 | -926127.43 | 1893868.2452 | Assuming 100$/m RC rates and 359$/m diamond.
G-Vein Resource Extension Drilling (44 no. Holes, 5,516m) | 387408.175 |  |  | 0 | Not yet started | 658538.51 | Assuming 100$/m RC rates and 359$/m diamond.
A-Vein Resource Extension Drilling (47 no. Holes, 4,185m) | 334698.75 |  |  | 0 | Not yet started | 193860 | Assuming 100$/m RC rates and 359$/m diamond.
[BL1] Dingo Vein Wide Spacing (7 no. Holes, 630m) | 39690 |  |  | 0 | Not yet started | 63092.0139 | Assuming 100$/m RC rates
[BL1] Southern Veins Wide Spacing (10 no. Holes, 900m) | 56700 |  |  | 0 | Not yet started | 90131.4484 | Assuming 100$/m RC rates
Geotechnical drilling (12 no. HQ Holes, 1040m) | 186550 | 123503.5 | 60685 | 184188.5 | -2361.5
Consumables (5% of Drilling & Assay Costs) | 331678.7128 | 64893.32 |  | 64893.32 | -266785.3928
Accommodation & Messing (4% of Direct) | 115186.852 | 73970 |  | 73970 | -41216.852 | 207983.9271
Transport ($600 per 50m per pallet) | 268808 |  |  | 0
Laboratory Assays | 2894109.9559 |  |  | 0
[BL1] Laboratory Assays (Monitoring Bores) | 12038.0757 |  |  | 0
[BL1] Laboratory Assays (Met Sample) | 374712.1561 |  |  | 0
[BL1] Laboratory Assays (Infill Sample) | 1561131.95 |  |  | 0
[BL1] Laboratory Assays (G-Vein Sample) | 460019.876 |  |  | 0
[BL1] Laboratory Assays (A-Vein Sample) | 352347.7012 |  |  | 0
[BL1] Laboratory Assays (Dingo-Vein Sample) | 55118.9045 |  |  | 0
[BL1] Laboratory Assays (Southern-Vein Sample) | 78741.2922 |  |  | 0
[5 empty] | 28.5 | 28.1
Average Cost per Metre | MET | GT | INF
DD | 358.5437 | 309.8202
RC |  |  | 100.1461
| Budget | Cost to date | Forecast for Remaining Work | Estimated Cost at Completion |  |  | 0.67751 | 623161.2415 |  | 105084.3665
DFS Met Sample collection (24 no. Holes, 2,045m) | 518076.875 | 651448 | 71708.7415 | 723156.7415 |  |  |  | 3165114.5825 |  | 1808567.0825
[BL1] Infill Drilling (163 no. Holes, 19,285m) | 1356547.5 | 262907 | 1893868.2452 | 2156775.2452 |  |  |  | 658538.51
G-Vein Resource Extension Drilling (44 no. Holes, 5,516m) | 387408.175 |  | 658538.51 | 658538.51 |  |  |  | 558360
A-Vein Resource Extension Drilling (47 no. Holes, 4,185m) | 334698.75 | 183051 | 193860 | 376911 |  |  |  | 63092.0139
[BL1] Dingo Vein Wide Spacing (7 no. Holes, 630m) | 39690 |  | 63092.0139 | 63092.0139 |  |  |  | 90131.4484
[BL1] Southern Veins Wide Spacing (10 no. Holes, 900m) | 56700 |  | 90131.4484 | 90131.4484 | 1190000 | 830000 | 360000 | 186550 |  | 0
Geotechnical drilling (12 no. HQ Holes, 1040m) | 186550 | 229629 |  | 186550 | 3690000 | 2510000 | 1180000 | 331678.7128 | 224714.5751 | 106964.1377
Consumables (5% of Drilling & Assay Costs) | 331678.7128 | 113043 |  | 331678.7128 |  |  |  | 366326.7658 | 248188.8657 | -133002.0137
Accommodation & Messing (4% of Direct) | 115186.852 | 81908 | 207983.9271 | 289891.9271 | 83300
Total | 3330000 | 1530000 | 3180000 | 4880000 | 3606700 | 1550000
22.67%
| Cost to date | Cost of Activity Hours | RC | DD
DFS Met Sample collection (24 no. Holes, 2,045m) | 551452.5 | 157715.415 |  | 1
[BL1] Infill Drilling (163 no. Holes, 19,285m) | 262907 | 81026.8285 | 0.93439 | 0.065608 | 0.31 | 0.2825
G-Vein Resource Extension Drilling (44 no. Holes, 5,516m) |  | 0 | 0.88554 | 0.11446 | 0.31 | 0.2825
A-Vein Resource Extension Drilling (47 no. Holes, 4,185m) | 183051 | 56096.2742 | 0.87097 | 0.12903 | 0.31 | 0.2825
[BL1] Dingo Vein Wide Spacing (7 no. Holes, 630m) |  | 0 | 1 |  | 0.31 | 0.2825
[BL1] Southern Veins Wide Spacing (10 no. Holes, 900m) |  | 0 | 1 |  | 0.31 | 0.2825
Geotechnical drilling (12 no. HQ Holes, 1040m) | 184188.5 | 52033.2512 |  | 1 | 0.31 | 0.2825
| 1181599 | 346871.769 | 0.29356
|  | Recommendation for Award |  |  |  | Actual to Date |  |  |  | Forecast Remaining |  |  |  | Estimate at Completion
Description | Drilling | No. Holes | m | All-in | Total | No. | m | All-in | Total | No. | m | All-in | Total | No. | m | All-in | Total
Metallurgy
| PQ | 51 | 2045 | 377047 |  |  |  |  | 195890 |  |  |  |  | 51 | 2045 | 723156.7415
Geotech
| HQ | 12 | 1040 | 186550 |  |  |  |  | 124935 |  |  |  |  | 12 | 1040 | 186550
Infill
| RC | 155 | 17945 | 820755 |  |  |  |  | 249817 |  |  |  |  | 155 | 17945 | 1796294.5
| HQ | 8 | 1260 | 168683 |  |  |  |  | 0 |  |  |  |  | 8 | 1260 | 452340
G-Vein
| RC | 39 | 4495.1 | 202279.5 |  |  |  |  | 0 |  |  |  |  | 39 | 4495.1 | 449959.51
| HQ | 5 | 581 | 75530 |  |  |  |  | 0 |  |  |  |  | 5 | 581 | 208579
A-Vein
| RC | 41 | 3645 | 177350 |  |  |  |  | 183051 |  |  |  |  | 41 | 3645 | 183051
| HQ | 6 | 540 | 75117.38 |  |  |  |  | 0 |  |  |  |  | 6 | 540 | 193860
Southern
| RC | 10 | 900 | 40500 |  |  |  |  | 0 |  |  |  |  | 10 | 900 | 323100
Dingo
| RC | 7 | 630 | 28350 |  |  |  |  | 0 |  |  |  |  | 7 | 630 | 226170
Consumables |  |  |  | 264843.525 |  |  |  |  | 113043 | [6 empty] | 331678.7128
Accomodation |  |  |  | 214285.89 |  |  |  |  | 81908 | [6 empty] | 289891.9271
|  |  |  | 2631291.295 | [11 empty] | 4743060.7515

## Purpose
Hole number | Purpose
SF25_DDGT001 | Geotech
SF25_DDGT002 | Geotech
SF25_DDGT003 | Geotech
SF25_DDGT004 | Geotech
SF25_DDGT005 | Geotech
SF25_DDGT006 | Geotech
SF25_DDGT007 | Geotech
SF25_DDGT008 | Geotech
SF25_DDGT009 | Geotech
SF25_DDGT010 | Geotech
SF25_DDGT011 | Geotech
SF25_DDGT012 | Geotech
SF25_DDRD001 | A Vein DD
SF25_DDRD002 | A Vein DD
SF25_DDRD003 | A Vein DD
SF25_DDRD004 | A Vein DD
SF25_DDRD005 | A Vein DD
SF25_DDRD006 | A Vein DD
SF25_DDRD008 | G Vein DD
SF25_DDRD009 | G Vein DD
SF25_DDRD010 | G Vein DD
SF25_DDRD011 | G Vein DD
SF25_DDRD012 | Infill
SF25_DDRD013 | Infill
SF25_DDRD014 | Infill
SF25_DDRD015 | Infill
SF25_DDRD016 | Infill
SF25_DDRD017 | Infill
SF25_DDRD018 | Infill
SF25_DDRD019 | Infill
SF25_DMET001 | Met
SF25_DMET002 | Met
SF25_DMET003 | Met
SF25_DMET004 | Met
SF25_DMET005 | Met
SF25_DMET006 | Met
SF25_DMET007 | Met
SF25_DMET008 | Met
SF25_DMET009 | Met
SF25_DMET010 | Met
SF25_DMET011 | Met
SF25_DMET012 | Met
SF25_DMET013 | Met
SF25_DMET014 | Met
SF25_DMET015 | Met
SF25_DMET016 | Met
SF25_DMET017 | Met
SF25_DMET018 | Met
SF25_DMET019 | Met
SF25_DMET020 | Met
SF25_DMET021 | Met
SF25_DMET022 | Met
SF25_DMET023 | Met
SF25_DMET024 | Met
SF25_RCRD001 | A Vein RC
SF25_RCRD002 | A Vein RC
SF25_RCRD003 | A Vein RC
SF25_RCRD004 | A Vein RC
SF25_RCRD005 | A Vein RC
SF25_RCRD006 | A Vein RC
SF25_RCRD007 | A Vein RC
SF25_RCRD008 | A Vein RC
SF25_RCRD009 | A Vein RC
SF25_RCRD010 | A Vein RC
SF25_RCRD011 | A Vein RC
SF25_RCRD012 | A Vein RC
SF25_RCRD013 | A Vein RC
SF25_RCRD014 | A Vein RC
SF25_RCRD015 | A Vein RC
SF25_RCRD016 | A Vein RC
SF25_RCRD017 | A Vein RC
SF25_RCRD018 | A Vein RC
SF25_RCRD019 | A Vein RC
SF25_RCRD020 | A Vein RC
SF25_RCRD021 | A Vein RC
SF25_RCRD022 | A Vein RC
SF25_RCRD023 | A Vein RC
SF25_RCRD024 | A Vein RC
SF25_RCRD025 | A Vein RC
SF25_RCRD026 | A Vein RC
SF25_RCRD027 | A Vein RC
SF25_RCRD028 | A Vein RC
SF25_RCRD029 | A Vein RC
SF25_RCRD030 | A Vein RC
SF25_RCRD031 | A Vein RC
SF25_RCRD032 | A Vein RC
SF25_RCRD033 | A Vein RC
SF25_RCRD034 | A Vein RC
SF25_RCRD035 | A Vein RC
SF25_RCRD036 | A Vein RC
SF25_RCRD037 | A Vein RC
SF25_RCRD038 | A Vein RC
SF25_RCRD039 | A Vein RC
SF25_RCRD042 | G Vein RC
SF25_RCRD043 | G Vein RC
SF25_RCRD044 | G Vein RC
SF25_RCRD045 | G Vein RC
SF25_RCRD046 | G Vein RC
SF25_RCRD047 | G Vein RC
SF25_RCRD048 | G Vein RC
SF25_RCRD049 | G Vein RC
SF25_RCRD050 | G Vein RC
SF25_RCRD051 | G Vein RC
SF25_RCRD052 | G Vein RC
SF25_RCRD053 | G Vein RC
SF25_RCRD054 | G Vein RC
SF25_RCRD055 | G Vein RC
SF25_RCRD056 | G Vein RC
SF25_RCRD057 | G Vein RC
SF25_RCRD058 | G Vein RC
SF25_RCRD059 | G Vein RC
SF25_RCRD060 | G Vein RC
SF25_RCRD061 | G Vein RC
SF25_RCRD062 | G Vein RC
SF25_RCRD063 | G Vein RC
SF25_RCRD064 | G Vein RC
SF25_RCRD065 | G Vein RC
SF25_RCRD066 | G Vein RC
SF25_RCRD067 | G Vein RC
SF25_RCRD068 | G Vein RC
SF25_RCRD069 | G Vein RC
SF25_RCRD070 | G Vein RC
SF25_RCRD071 | G Vein RC
SF25_RCRD072 | G Vein RC
SF25_RCRD073 | G Vein RC
SF25_RCRD074 | G Vein RC
SF25_RCRD075 | G Vein RC
SF25_RCRD076 | G Vein RC
SF25_RCRD077 | G Vein RC
SF25_RCRD078 | G Vein RC
SF25_RCRD079 | G Vein RC
SF25_RCRD080 | G Vein RC
SF25_RCRD081 | Infill
SF25_RCRD082 | Infill
SF25_RCRD083 | Infill
SF25_RCRD084 | Infill
SF25_RCRD085 | Infill
SF25_RCRD086 | Infill
SF25_RCRD087 | Infill
SF25_RCRD088 | Infill
SF25_RCRD089 | Infill
SF25_RCRD090 | Infill
SF25_RCRD091 | Infill
SF25_RCRD092 | Infill
SF25_RCRD093 | Infill
SF25_RCRD094 | Infill
SF25_RCRD095 | Infill
SF25_RCRD096 | Infill
SF25_RCRD097 | Infill
SF25_RCRD098 | Infill
SF25_RCRD099 | Infill
SF25_RCRD100 | Infill
SF25_RCRD101 | Infill
SF25_RCRD102 | Infill
SF25_RCRD103 | Infill
SF25_RCRD104 | Infill
SF25_RCRD105 | Infill
SF25_RCRD106 | Infill
SF25_RCRD107 | Infill
SF25_RCRD108 | Infill
SF25_RCRD109 | Infill
SF25_RCRD110 | Infill
SF25_RCRD111 | Infill
SF25_RCRD112 | Infill
SF25_RCRD113 | Infill
SF25_RCRD114 | Infill
SF25_RCRD115 | Infill
SF25_RCRD116 | Infill
SF25_RCRD117 | Infill
SF25_RCRD118 | Infill
SF25_RCRD119 | Infill
SF25_RCRD120 | Infill
SF25_RCRD121 | Infill
SF25_RCRD122 | Infill
SF25_RCRD123 | Infill
SF25_RCRD124 | Infill
SF25_RCRD125 | Infill
SF25_RCRD126 | Infill
SF25_RCRD127 | Infill
SF25_RCRD128 | Infill
SF25_RCRD129 | Infill
SF25_RCRD130 | Infill
SF25_RCRD131 | Infill
SF25_RCRD132 | Infill
SF25_RCRD133 | Infill
SF25_RCRD134 | Infill
SF25_RCRD135 | Infill
SF25_RCRD136 | Infill
SF25_RCRD137 | Infill
SF25_RCRD138 | Infill
SF25_RCRD139 | Infill
SF25_RCRD140 | Infill
SF25_RCRD141 | Infill
SF25_RCRD142 | Infill
SF25_RCRD143 | Infill
SF25_RCRD144 | Infill
SF25_RCRD145 | Infill
SF25_RCRD146 | Infill
SF25_RCRD147 | Infill
SF25_RCRD148 | Infill
SF25_RCRD149 | Infill
SF25_RCRD150 | Infill
SF25_RCRD151 | Infill
SF25_RCRD152 | Infill
SF25_RCRD153 | Infill
SF25_RCRD154 | Infill
SF25_RCRD155 | Infill
SF25_RCRD156 | Infill
SF25_RCRD157 | Infill
SF25_RCRD158 | Infill
SF25_RCRD159 | Infill
SF25_RCRD160 | Infill
SF25_RCRD161 | Infill
SF25_RCRD162 | Infill
SF25_RCRD163 | Infill
SF25_RCRD164 | Infill
SF25_RCRD165 | Infill
SF25_RCRD166 | Infill
SF25_RCRD167 | Infill
SF25_RCRD168 | Infill
SF25_RCRD169 | Infill
SF25_RCRD170 | Infill
SF25_RCRD171 | Infill
SF25_RCRD172 | Infill
SF25_RCRD173 | Infill
SF25_RCRD174 | Infill
SF25_RCRD175 | Infill
SF25_RCRD176 | Infill
SF25_RCRD177 | Infill
SF25_RCRD178 | Infill
SF25_RCRD179 | Infill
SF25_RCRD180 | Infill
SF25_RCRD181 | Infill
SF25_RCRD182 | Infill
SF25_RCRD183 | Infill
SF25_RCRD184 | Infill
SF25_RCRD185 | Infill
SF25_RCRD186 | Infill
SF25_RCRD187 | Infill
SF25_RCRD188 | Infill
SF25_RCRD189 | Infill
SF25_RCRD190 | Infill
SF25_RCRD191 | Infill
SF25_RCRD192 | Infill
SF25_RCRD193 | Infill
SF25_RCRD194 | Infill
SF25_RCRD195 | Infill
SF25_RCRD196 | Infill
SF25_RCRD197 | Infill
SF25_RCRD198 | Infill
SF25_RCRD199 | Infill
SF25_RCRD200 | Infill
SF25_RCRD201 | Infill
SF25_RCRD202 | Infill
SF25_RCRD203 | Infill
SF25_RCRD204 | Infill
SF25_RCRD205 | Infill
SF25_RCRD206 | Infill
SF25_RCRD207 | Infill
SF25_RCRD208 | Infill
SF25_RCRD209 | Infill
SF25_RCRD210 | Infill
SF25_RCRD211 | Infill
SF25_RCRD212 | Infill
SF25_RCRD213 | Infill
SF25_RCRD214 | Infill
SF25_RCRD215 | Infill
SF25_RCRD216 | Infill
SF25_RCRD217 | Infill
SF25_RCRD218 | Infill
SF25_RCRD219 | Infill
SF25_RCRD220 | Infill
SF25_RCRD221 | Infill
SF25_RCRD222 | Infill
SF25_RCRD223 | Infill
SF25_RCRD224 | Infill
SF25_RCRD225 | Infill
SF25_RCRD226 | Infill
SF25_RCRD227 | Infill
SF25_RCRD228 | Infill
SF25_RCRD229 | Infill
SF25_RCRD230 | Infill
SF25_RCRD231 | Infill
SF25_RCRD232 | Infill
SF25_RCRD233 | Infill
SF25_RCRD234 | Infill
SF25_RCRD235 | Infill
SF25_RCRD300 | G Vein RC
SF25_REXP001 | Dingo
SF25_REXP002 | Dingo
SF25_REXP003 | Dingo
SF25_REXP004 | Dingo
SF25_REXP005 | Dingo
SF25_REXP006 | Dingo
SF25_REXP007 | Dingo
SF25_REXP008 | South
SF25_REXP009 | South
SF25_REXP010 | South
SF25_REXP011 | South
SF25_REXP012 | South
SF25_REXP013 | South
SF25_REXP014 | South
SF25_REXP015 | South
SF25_REXP016 | South
SF25_REXP017 | South
SF25_RHYD001 | Hydro
SF25_RHYD002 | Hydro
SF25_RHYD003 | Hydro
SF25_RHYD004 | Hydro
SF25_RHYD005 | Hydro
SF25_RHYD006 | Hydro
SF25_RHYD007 | Hydro
SF25_RHYD008 | Hydro
SF25_RHYD009 | Hydro
SF25_RHYD010 | Hydro
SF25_RHYD011 | Hydro
SF25_RHYD012 | Hydro
SF25_RHYD013 | Hydro
SF25_RHYD014 | Hydro
SF25_RHYD015 | Hydro
SF25_RHYD016 | Hydro
SF25_RHYD017 | Hydro
SF25_RHYD018 | Hydro
SF25_RHYD019 | Hydro
SF25_RHYD020 | Hydro
SF25_RHYD021 | Hydro
SF25_RHYD022 | Hydro
SF25_RHYD023 | Hydro
SF25_RHYD024 | Hydro
SF25_RHYD025 | Hydro
SF25_RHYD026 | Hydro
SF25_RHYD027 | Hydro
SF25_RHYD028 | Hydro

## Tenement Lookup
Completed Drillhole | Easting_original | Northing_original | Elevation | Azimuth | Dip | Lift Rate | Drift Rate | Distance | Extension | Target Depth | Comment | Status | Drill Type | Total Depth | Purpose | Clearance_Priority | Collar_Adjustment | Collar_Adjustment_Approval | Adjustment_comment | Date Modified | Drill_Complete_Date | Proc REQ | Old_hole_ID | Easting | Northing | X_Local | Y_Local | fid_2 | OBJECTID | TENID | TYPE | SURVSTATUS | TENSTATUS | HOLDERCNT | HOLDER1 | ADDR1 | HOLDER2 | ADDR2 | HOLDER3 | ADDR3 | HOLDER4 | ADDR4 | HOLDER5 | ADDR5 | HOLDER6 | ADDR6 | HOLDER7 | ADDR7 | HOLDER8 | ADDR8 | HOLDER9 | ADDR9 | STARTDATE | STARTTIME | ENDDATE | ENDTIME | GRANTDATE | GRANTTIME | FMT_TENID | LEGAL_AREA | UNIT_OF_ME | SPECIAL_IN | EXTRACT_DA | COMBINED_R | ALL_HOLDER | SHAPE_Leng | SHAPE_Area
SF25_DDRD006 | 391362 | 8186979 | 178 | 288 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | DD | 90 | RD | 1 | [7 empty] | 391362 | 8186979 | 10032.8528 | 11998.6316 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD038 | 391339 | 8186987 | 182 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 1 |  |  |  |  | 2025-07-01 |  |  | 391339 | 8186987 | 10008.4944 | 11998.755 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD037 | 391411 | 8187046 | 174 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 1 |  |  |  |  | 2025-06-30 |  |  | 391411 | 8187046 | 10057.531 | 12077.9097 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD036 | 391388 | 8187054 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 1 |  |  |  |  | 2025-06-30 |  |  | 391388 | 8187054 | 10033.1726 | 12078.033 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD035 | 391365 | 8187062 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 1 | [7 empty] | 391365 | 8187062 | 10008.8142 | 12078.1563 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD034 | 391439 | 8187121 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 1 | [7 empty] | 391439 | 8187121 | 10059.7437 | 12157.9587 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD033 | 391416 | 8187129 | 173 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 1 | [7 empty] | 391416 | 8187129 | 10035.3853 | 12158.082 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD032 | 391394 | 8187137 | 173 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 1 | [7 empty] | 391394 | 8187137 | 10011.9733 | 12158.5292 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD003 | 391804 | 8188011 | 180 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | TRUE | TRUE | [5 empty] | 391741.2395 | 8188034.3457 | 10050.0221 | 13120.2451 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD002 | 391896 | 8188064 | 180 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | TRUE | TRUE | [5 empty] | 391825.0534 | 8188089.7712 | 10111.3971 | 13199.8425 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD001 | 391873 | 8188072 | 179 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | DD | 90 | RD | 3 | TRUE | TRUE | [5 empty] | 391803.2661 | 8188097.468 | 10088.2847 | 13200.0716 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD001 | 391850 | 8188080 | 179 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 140 | A Vein North Res Def | DC | RC | 140 | RD | 3 | TRUE | TRUE | [5 empty] | 391779.6598 | 8188105.468 | 10063.3524 | 13199.9985 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET001 | 391345 | 8186852 | 182 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 110 | Metallurgical Program | DC | DD | 110 | MET | 1 | [7 empty] | 391345 | 8186852 | 10057.89 | 11872.9307 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD012 | 391362 | 8186853 | 180 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | DC | DD | 160 | RD | 3 | [7 empty] | 391362 | 8186853 | 10073.6553 | 11879.3822 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD039 | 391384 | 8186971 | 174 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 1 |  |  |  |  | 2025-07-02 |  |  | 391384 | 8186971 | 10056.2648 | 11998.1845 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD083 | 391375 | 8186933 | 177 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | DC | RC | 140 | RD | 3 |  |  |  |  | 2025-07-03 |  |  | 391375.5558 | 8186935.4593 | 10059.7821 | 11961.8134 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD084 | 391393 | 8186927 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | DC | RC | 180 | RD | 3 |  |  |  |  | 2025-07-05 | RC Dup Calico |  | 391393 | 8186927 | 10079.0311 | 11959.4563 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD085 | 391325 | 8186908 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 60 | Infill | DC | RC | 60 | RD | 1 |  |  |  |  | 2025-07-05 |  |  | 391325 | 8186908 | 10020.827 | 11919.4538 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD086 | 391346 | 8186901 | 180 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 100 | Infill | DC | RC | 100 | RD | 3 |  |  |  |  | 2025-07-06 |  |  | 391346 | 8186901 | 10042.9687 | 11919.6293 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD087 | 391367 | 8186894 | 179 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | DC | RC | 140 | RD | 3 |  |  |  |  | 2025-07-06 |  |  | 391367 | 8186894 | 10065.1104 | 11919.8048 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD088 | 391389 | 8186886 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 190 | Infill | DC | RC | 190 | RD | 3 |  |  |  |  | 2025-07-07 |  |  | 391389 | 8186886 | 10088.5224 | 11919.3576 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD089 | 391207 | 8186822 | 183 | 99 | 58 | FALSE | FALSE | 10 | FALSE | 185 | Infill | PLN | RC | 170 | RD | 3 | TRUE | TRUE |  |  |  | RC Dup Calico |  | 391198.9522 | 8186811.2413 | 9932.8657 | 11787.061 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD090 | 391365 | 8186810 | 179 | 284 | 60 | FALSE | FALSE | 10 | FALSE | 200 | Infill | PLN | RC | 200 | RD | 3 | TRUE | TRUE | [5 empty] | 391363.1036 | 8186816.7444 | 10086.4404 | 11845.4265 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD031 | 391459 | 8187199 | 171 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 1 | [7 empty] | 391459 | 8187199 | 10053.4134 | 12238.2564 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD005 | 391436 | 8187207 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | DD | 90 | RD | 1 | [7 empty] | 391436 | 8187207 | 10029.055 | 12238.3797 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD030 | 391414 | 8187215 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 1 | [7 empty] | 391414 | 8187215 | 10005.6431 | 12238.8268 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD029 | 391485 | 8187269 | 171 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 1 | [7 empty] | 391485 | 8187269 | 10055.3524 | 12312.9256 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD028 | 391463 | 8187277 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 1 | [7 empty] | 391463 | 8187277 | 10031.9404 | 12313.3728 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD027 | 391440 | 8187285 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 1 | [7 empty] | 391440 | 8187285 | 10007.582 | 12313.4961 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD081 | 391333 | 81869489 | 179 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | DC | RC | 50 | RD | 3 |  |  |  |  | 2025-07-02 |  |  | 391333 | 8186948 | 10015.4452 | 11959.9014 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD082 | 391352 | 8186941 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 100 | Infill | DC | RC | 100 | RD | 3 |  |  |  |  | 2025-07-02 |  |  | 391352 | 8186941 | 10035.6941 | 11959.4292 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD023 | 390190 | 8185279 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-014 | DC | RC | 100 | HYD | 3 | [7 empty] | 390190 | 8185279 | 9474.1542 | 10010.1827 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
[28 empty] | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD056 | 391433 | 8186238 | 175 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 50 | G Vein Res Def | DC | RC | 50 | RD | 3 | [7 empty] | 391433 | 8186238 | 10340.0066 | 11320.3234 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD055 | 391395 | 8186251 | 174 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 114 | G Vein Res Def | DC | RC | 114 | RD | 3 | [7 empty] | 391395 | 8186251 | 10299.8327 | 11320.3214 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD054 | 391357 | 8186264 | 175 | 109 | 57 | FALSE | FALSE | 10 | FALSE | 190 | G Vein Res Def | DC | RC | 190 | RD | 3 | [7 empty] | 391357 | 8186264 | 10259.6588 | 11320.3194 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD053 | 391468 | 8186310 | 173 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 42 | G Vein Res Def | DC | RC | 42 | RD | 3 | [7 empty] | 391468 | 8186310 | 10349.8157 | 11399.7999 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD052 | 391430 | 8186323 | 173 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 84 | G Vein Res Def | DC | RC | 84 | RD | 3 | [7 empty] | 391430 | 8186323 | 10309.6418 | 11399.7979 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD051 | 391504 | 8186383 | 174 | 109 | 56 | FALSE | FALSE | 10 | FALSE | 133 | G Vein Res Def | DC | RC | 133 | RD | 3 | [7 empty] | 391504 | 8186383 | 10360.2474 | 11480.5468 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD091 | 391311 | 8186786 | 194 | 279 | 60 | FALSE | FALSE | 10 | FALSE | 85 | Infill | IMP | RC | 80 | RD | 3 | TRUE | TRUE | [5 empty] | 391317.7286 | 8186793.5218 | 10051.0167 | 11808.7542 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD092 | 391227 | 8186773 | 188 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 120 | Infill | PLN | RC | 120 | RD | 3 | [7 empty] | 391227 | 8186773 | 9971.7945 | 11759.9513 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD093 | 391194 | 8186742 | 187 | 104 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | TRUE | TRUE | [5 empty] | 391192.8678 | 8186731.8696 | 9952.8102 | 11709.9715 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDGT001 | 391325 | 8186910 | 183 | 20 | 65 | FALSE | FALSE | 10 | FALSE | 100 | Geotechnical Drilling | DC | DD | 100 | GT | 1 | [7 empty] | 391325 | 8186910 | 10020.1794 | 11921.3467 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD003 | 391168 | 8186979 | 170 | 0 | 90 | FALSE | FALSE | 10 | TRUE | 120 | HYD25-010a | DC | RC | 120 | HYD | 1 | [7 empty] | 391168 | 8186979 | 9849.2466 | 11935.8087 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD004 | 391184 | 8186957 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 120 | HYD25-010b | DC | RC | 120 | HYD | 1 | TRUE | TRUE | [5 empty] | 391189.8341 | 8186967.0915 | 9873.7672 | 11931.6087 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD005 | 391160 | 8186956 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 120 | HYD25-013 | DC | HGD | 120 | HYD | 1 | TRUE | TRUE | [5 empty] | 391158.029 | 8186957.2614 | 9846.8494 | 11912.0059 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD047 | 391454 | 8186484 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 210 | G Vein Res Def | DC | RC | 210 | RD | 3 | [7 empty] | 391454 | 8186484 | 10280.2194 | 11559.9441 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD106 | 391322 | 8186487 | 187 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | PLN | RC | 140 | RD | 3 | [7 empty] | 391322 | 8186487 | 10154.32 | 11520.0379 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD105 | 391355 | 8186518 | 203 | 329 | 55 | FALSE | FALSE | 10 | FALSE | 55 | Infill | PLN | RC | 50 | RD | 3 | TRUE | TRUE | [5 empty] | 391350.1535 | 8186496.7015 | 10177.8235 | 11538.3365 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD013 | 391272 | 8186503 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | DC | DD | 180 | RD | 3 | [7 empty] | 391272 | 8186503 | 10101.8175 | 11518.9892 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET004 | 391250 | 8186515 | 188 | 289 | 56 | FALSE | FALSE | 10 | FALSE | 120 | Metallurgical Program | DC | DD | 120 | MET | 1 |  |  |  |  | 2025-07-01 |  |  | 391250 | 8186515 | 10077.1102 | 11523.222 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET005 | 391251 | 8186515 | 188 | 289 | 58 | FALSE | FALSE | 10 | FALSE | 120 | Metallurgical Program | DC | DD | 120 | MET | 1 | [7 empty] | 391251 | 8186515 | 10078.0567 | 11523.5458 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDGT003 | 391251 | 8186516 | 188 | 110 | 80 | FALSE | FALSE | 10 | FALSE | 110 | Geotechnical Drilling | DC | DD | 110 | GT | 1 | [7 empty] | 391251 | 8186516 | 10077.7328 | 11524.4923 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD207 | 391496 | 8186512 | 177 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 60 | Infill | PLN | RC | 60 | RD | 3 | [7 empty] | 391496 | 8186512 | 10310.902 | 11600.0448 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD010 | 391466 | 8186396 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 133 | G Vein Res Def | DC | DD | 133 | RD | 3 | [7 empty] | 391466 | 8186396 | 10320.0735 | 11480.5447 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD050 | 391418 | 8186412 | 176 | 109 | 58 | FALSE | FALSE | 10 | FALSE | 220 | G Vein Res Def | DC | RC | 220 | RD | 3 | [7 empty] | 391418 | 8186412 | 10269.4639 | 11480.1437 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD017 | 391521 | 8186419 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Infill | DC | DD | 110 | RD | 3 | [7 empty] | 391521 | 8186419 | 10364.6788 | 11520.1231 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD109 | 391507 | 8186424 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Infill | DC | RC | 90 | RD | 3 | [5 empty] | RC Dup Calico |  | 391507 | 8186424 | 10349.8097 | 11520.3216 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD108 | 391235 | 8186432 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | [7 empty] | 391235 | 8186432 | 10089.7917 | 11439.8114 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD049 | 391529 | 8186458 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 71 | G Vein Res Def | DC | RC | 71 | RD | 3 | [7 empty] | 391529 | 8186458 | 10359.6208 | 11559.6243 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD107 | 391246 | 8186470 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | [7 empty] | 391246 | 8186470 | 10087.8969 | 11479.3376 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD048 | 391492 | 8186471 | 175 | 109 | 58 | FALSE | FALSE | 10 | FALSE | 135 | G Vein Res Def | DC | RC | 135 | RD | 3 | [7 empty] | 391492 | 8186471 | 10320.3933 | 11559.9461 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_REXP005 | 386840 | 8196701 | 256 | 94 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 386840 | 8196701 | 2604.8527 | 19735.4082 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_REXP006 | 386871 | 8196058 | 253 | 94 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 386871 | 8196058 | 2842.4142 | 19136.8963 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_REXP007 | 387000 | 8195453 | 242 | 274 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 387000 | 8195453 | 3160.4198 | 18606.0838 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD001 | 394830 | 8192774 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-001 | DC | RC | 100 | HYD | 3 | [7 empty] | 394830 | 8192774 | 11438.4588 | 18606.1994 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD002 | 393150 | 8189498 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-007 | DC | RC | 100 | HYD | 3 | [7 empty] | 393150 | 8189498 | 10909.3322 | 14961.6809 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD008 | 388599 | 8186829 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 24 | TSF1 | DC | HGD | 24 | HYD | 3 | TRUE | TRUE | [5 empty] | 388599 | 8186831.6359 | 7465.6042 | 10964.4217 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD009 | 388248 | 8186710 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 24 | TSF2 | DC | HGD | 24 | HYD | 3 | [7 empty] | 388248 | 8186710 | 7172.7987 | 10735.6383 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD010 | 388407 | 8186626 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 24 | TSF3 | DC | HGD | 24 | HYD | 3 | [7 empty] | 388407 | 8186626 | 7350.4818 | 10707.6276 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_DDGT002 | 388253 | 8186577 | 190 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 15 | Geotechnical Drilling | DC | DD | 15 | GT | 1 | TRUE | TRUE | [5 empty] | 388256.1408 | 8186590.9714 | 7219.0484 | 10625.6231 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_DDGT005 | 388560 | 8186401 | 190 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 15 | Geotechnical Drilling | DC | DD | 20 | GT | 1 | [7 empty] | 388560 | 8186401 | 7568.1463 | 10544.2282 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_DDGT006 | 388826 | 8186228 | 190 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 15 | Geotechnical Drilling | DC | DD | 15 | GT | 1 | [7 empty] | 388826 | 8186228 | 7875.9176 | 10466.6355 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_REXP001 | 386788 | 8199911 | 261 | 94 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 386776.5287 | 8199912.1823 | 1504.9062 | 22753.9942 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_REXP002 | 386822 | 8199267 | 261 | 94 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 386822 | 8199267 | 1756.8704 | 22158.1031 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_REXP003 | 386865 | 8198623 | 253 | 94 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 386865 | 8198623 | 2006.1129 | 21562.5308 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_REXP004 | 386867 | 8197341 | 258 | 94 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Dingo Vein Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 386868.7991 | 8197358.0805 | 2419.3268 | 20366.611 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD022 | 388246 | 8185493 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-002 | DC | RC | 100 | HYD | 3 | TRUE | FALSE | [5 empty] | 388259.6698 | 8185493.3535 | 7577.8294 | 9587.954 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD024 | 388122 | 8185243 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 48 | TSF11 | DC | HGD | 48 | HYD | 3 | FALSE | [6 empty] | 388122 | 8185243 | 7528.6073 | 9306.4319 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD028 | 387693 | 8180004 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-016 | DC | RC | 100 | HYD | 3 | [7 empty] | 387693 | 8180004 | 8819.1344 | 4209.1938 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD001 | 394830 | 8192774 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-001 | DC | RC | 100 | HYD | 3 | [7 empty] | 394830 | 8192774 | 11438.4588 | 18606.1994 | 3 | 16720 | L 8000043 | MISCELLANEOUS LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37973 | 13:10 | 45984 | 24:00 | 38315 | 0:00 | L 80/43 | 1854 | HA. |  | 45551 |  | SPEEWAH MINING PTY LTD | 0.61853 | 0.0015659
SF25_RHYD002 | 393150 | 8189498 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-007 | DC | RC | 100 | HYD | 3 | [7 empty] | 393150 | 8189498 | 10909.3322 | 14961.6809 | 3 | 16720 | L 8000043 | MISCELLANEOUS LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37973 | 13:10 | 45984 | 24:00 | 38315 | 0:00 | L 80/43 | 1854 | HA. |  | 45551 |  | SPEEWAH MINING PTY LTD | 0.61853 | 0.0015659
SF25_RCRD067 | 391240 | 8185797 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 129 | G Vein Res Def | DC | RC | 129 | RD | 3 | [7 empty] | 391240 | 8185797 | 10300.1556 | 10840.4513 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD065 | 391247 | 8185879 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 170 | G Vein Res Def | DC | RC | 170 | RD | 3 | [7 empty] | 391247 | 8185879 | 10280.2266 | 10920.3249 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD063 | 391301 | 8185945 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 118 | G Vein Res Def | DC | RC | 118 | RD | 3 | [7 empty] | 391301 | 8185945 | 10309.9607 | 11000.2757 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD011 | 388622 | 8186577 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-003 | DC | RC | 100 | HYD | 3 | [7 empty] | 388622 | 8186577 | 7569.8306 | 10730.8762 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD012 | 388633 | 8186569 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 24 | TSF4 | DC | HGD | 24 | HYD | 3 | [7 empty] | 388633 | 8186569 | 7582.8319 | 10726.8669 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD013 | 388767 | 8186508 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 24 | TSF5 | DC | HGD | 24 | HYD | 3 | [7 empty] | 388767 | 8186508 | 7729.4063 | 10712.5282 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD014 | 388890 | 8186446 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 24 | TSF6 | DC | HGD | 24 | HYD | 3 | [7 empty] | 388890 | 8186446 | 7865.8939 | 10693.681 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD015 | 387993 | 8186173 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 48 | TSF7 | DC | HGD | 48 | HYD | 3 | TRUE | FALSE | [5 empty] | 388200.9266 | 8186227.7423 | 7284.4167 | 10263.9743 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD019 | 388167 | 8185729 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 48 | Hydro | PLN | HGD | 48 | HYD | 3 | [7 empty] | 388167 | 8185729 | 7413.8152 | 9780.9662 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD020 | 388412 | 8185643 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 48 | Hydro | PLN | HGD | 48 | HYD | 3 | TRUE | FALSE | [5 empty] | 388327.6835 | 8185742.1646 | 7561.6268 | 9845.4597 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RHYD021 | 388239 | 8185511 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 48 | Hydro | PLN | HGD | 48 | HYD | 3 | TRUE | FALSE | [5 empty] | 388239.6187 | 8185516.9658 | 7551.2062 | 9603.8081 | 1 | 10658 | E 8002863 | EXPLORATION LICENCE | UNSURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 37292 | 9:00 | 45514 | 24:00 | 37844 | 0:00 | E 80/2863-I | 46 | BL. | I | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 1.1406 | 0.011499
SF25_RCRD025 | 391503 | 8187438 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | TRUE | TRUE | [5 empty] | 391501.6662 | 8187436.4994 | 10016.8844 | 12476.8481 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD024 | 391575 | 8187497 | 169 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | [7 empty] | 391575 | 8187497 | 10066.6974 | 12557.855 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD023 | 391552 | 8187505 | 171 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 3 | [7 empty] | 391552 | 8187505 | 10042.339 | 12557.9783 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD022 | 391530 | 8187513 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | TRUE | TRUE | [5 empty] | 391537.7408 | 8187511.4201 | 10026.7647 | 12559.4369 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD021 | 391607 | 8187571 | 173 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | [7 empty] | 391607 | 8187571 | 10073.0196 | 12638.2529 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD020 | 391584 | 8187579 | 173 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 3 | [7 empty] | 391584 | 8187579 | 10048.6612 | 12638.3762 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD019 | 391561 | 8187587 | 173 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | [7 empty] | 391566.9752 | 8187585.2512 | 10030.5242 | 12638.7793 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD018 | 391650 | 8187641 | 174 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | [7 empty] | 391650 | 8187641 | 10091.0477 | 12718.4272 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD061 | 391289 | 8186033 | 174 | 109 | 57 | FALSE | FALSE | 10 | FALSE | 115 | G Vein Res Def | DC | RC | 115 | RD | 3 | [7 empty] | 391289 | 8186033 | 10270.1066 | 11079.675 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD008 | 391327 | 8186020 | 174 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 110 | G Vein Res Def | DC | DD | 110 | RD | 3 | TRUE | TRUE | Nest in tree | 2025-07-05 |  |  |  | 391332.4192 | 8186036.2576 | 10310.1447 | 11096.8185 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD059 | 391343 | 8186099 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 78 | G Vein Res Def | DC | RC | 78 | RD | 3 | [7 empty] | 391343 | 8186099 | 10299.8408 | 11159.6258 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD058 | 391407 | 8186162 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 134 | G Vein Res Def | DC | RC | 134 | RD | 3 | [7 empty] | 391407 | 8186162 | 10340.0106 | 11239.9756 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD300 | 391369 | 8186175 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 134 | G Vein Res Def | DC | RC | 134 | RD | 3 | [7 empty] | 391369 | 8186175 | 10299.8367 | 11239.9736 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD057 | 391331 | 8186188 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 205 | G Vein Res Def | DC | RC | 205 | RD | 3 | [7 empty] | 391331 | 8186188 | 10259.6628 | 11239.9716 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD026 | 391548 | 8187422 | 171 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | [7 empty] | 391548 | 8187422 | 10065.4312 | 12478.1298 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD004 | 391526 | 8187430 | 172 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | DD | 90 | RD | 3 | TRUE | TRUE |  |  | 2025-08-08 |  |  | 391523.7989 | 8187427.0652 | 10040.8864 | 12475.0865 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD010 | 391767 | 8187854 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | FALSE | [6 empty] | 391767 | 8187854 | 10132.8037 | 12957.9036 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD002 | 391744 | 8187862 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | DD | 90 | RD | 3 | [7 empty] | 391744 | 8187862 | 10108.4453 | 12958.0269 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD009 | 391722 | 8187870 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | FALSE | [6 empty] | 391722 | 8187870 | 10085.0333 | 12958.474 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD008 | 391812 | 8187924 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | FALSE | [6 empty] | 391812 | 8187924 | 10152.7247 | 13038.7256 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD006 | 391766 | 8187939 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | TRUE | FALSE | [5 empty] | 391760.2574 | 8187925.3869 | 10103.3052 | 13023.2824 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD007 | 391789 | 8187931 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 3 | FALSE | [6 empty] | 391789 | 8187931 | 10128.6901 | 13037.9025 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD005 | 391850 | 8187995 | 183 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 35 | A Vein North Res Def | DC | RC | 35 | RD | 3 | TRUE | TRUE | [5 empty] | 391782.6917 | 8188020.1648 | 10093.8455 | 13120.2474 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD004 | 391827 | 8188003 | 181 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 3 | TRUE | TRUE | [5 empty] | 391764.8459 | 8188026.3457 | 10074.9543 | 13120.3181 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD003 | 391627 | 8187649 | 174 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | DD | 90 | RD | 3 | [7 empty] | 391627 | 8187649 | 10066.6894 | 12718.5505 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD017 | 391605 | 8187656 | 174 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | [7 empty] | 391605 | 8187656 | 10043.6012 | 12718.0512 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD016 | 391693 | 8187711 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | [7 empty] | 391693 | 8187711 | 10109.0759 | 12798.6016 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD015 | 391670 | 8187719 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 3 | [7 empty] | 391670 | 8187719 | 10084.7175 | 12798.7249 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD014 | 391647 | 8187726 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | [7 empty] | 391647 | 8187726 | 10060.683 | 12797.9018 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD013 | 391728 | 8187783 | 174 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 135 | A Vein North Res Def | DC | RC | 135 | RD | 3 | TRUE | TRUE | [5 empty] | 391726.6033 | 8187779.9572 | 10118.5485 | 12874.746 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD012 | 391705 | 8187791 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | A Vein North Res Def | DC | RC | 90 | RD | 3 | TRUE | TRUE | [5 empty] | 391700.8191 | 8187788.7195 | 10091.3082 | 12874.6892 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD011 | 391682 | 8187799 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 45 | A Vein North Res Def | DC | RC | 45 | RD | 3 | [7 empty] | 391682 | 8187799 | 10070.1682 | 12878.3248 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD127 | 391173 | 8186157 | 182 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | DC | RC | 180 | RD | 3 |  |  |  |  | 2025-08-09 |  |  | 391173 | 8186157 | 10120.1666 | 11159.4674 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD123 | 391177 | 8186198 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | DC | RC | 180 | RD | 3 |  |  |  |  | 2025-08-09 |  |  | 391177 | 8186198 | 10110.6753 | 11199.5661 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD120 | 391181 | 8186239 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | DC | RC | 170 | RD | 3 | [7 empty] | 391181 | 8186239 | 10101.1839 | 11239.6648 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET006 | 391188 | 8186489 | 193 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 80 | To be converted to a monitoring bore | DC | DD | 80 | MET | 1 |  |  |  |  | 2025-06-19 |  |  | 391188 | 8186489 | 10026.8515 | 11478.5376 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDGT004 | 391189 | 8186490 | 190 | 290 | 55 | FALSE | FALSE | 10 | FALSE | 110 | Geotechnical Drilling | DC | DD | 110 | GT | 1 | [7 empty] | 391189 | 8186490 | 10027.4741 | 11479.8078 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET007 | 391189 | 8186489 | 195 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 80 | To be converted to a monitoring bore | DC | DD | 80 | MET | 1 |  |  |  |  | 2025-06-21 |  |  | 391189 | 8186489 | 10027.7979 | 11478.8614 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD115 | 391207 | 8186315 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | DC | RC | 160 | RD | 3 | [7 empty] | 391207 | 8186315 | 10101.1799 | 11320.0125 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD110 | 391225 | 8186393 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | DC | RC | 170 | RD | 3 | [5 empty] | RC Dup Calico |  | 391225 | 8186393 | 10092.9568 | 11399.6625 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD131 | 391144 | 8186125 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | DC | RC | 140 | RD | 3 |  |  |  |  | 2025-08-09 |  |  | 391144 | 8186125 | 10103.0828 | 11119.7907 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD140 | 391148 | 8186039 | 181 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 190 | Infill | DC | RC | 190 | RD | 3 |  |  |  |  | 2025-08-09 |  |  | 391148 | 8186039 | 10134.7179 | 11039.6936 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD126 | 391148 | 8186166 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [7 empty] | 391148 | 8186166 | 10093.5915 | 11159.8894 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD119 | 391149 | 8186250 | 191 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Infill | PLN | RC | 110 | RD | 3 | [7 empty] | 391149 | 8186250 | 10067.3363 | 11239.7129 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD113 | 391151 | 8186334 | 200 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 80 | Infill | PLN | RC | 80 | RD | 3 | [5 empty] | RC Waste Samples |  | 391151 | 8186334 | 10042.0274 | 11319.8601 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD136 | 391167 | 8186075 | 180 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 200 | Infill | DC | RC | 200 | RD | 3 |  |  |  |  | 2025-08-09 |  |  | 391167 | 8186075 | 10141.0421 | 11079.9176 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD111 | 391171 | 8186369 | 197 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Infill | PLN | RC | 80 | RD | 3 | [7 empty] | 391171 | 8186369 | 10049.6219 | 11359.4616 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD133 | 391173 | 8186115 | 181 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 190 | Infill | DC | RC | 190 | RD | 3 |  |  |  |  | 2025-08-09 | RC Dup Calico |  | 391173 | 8186115 | 10133.7674 | 11119.7175 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_REXP008 | 390714 | 8184102 | 170 | 300 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390714 | 8184102 | 10351.2277 | 9065.9283 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD192 | 390514 | 8184734 | 193 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | IMP | RC | 140 | RD | 3 | TRUE | TRUE | Moved to avoid ridgeline with large boulders. 40m added to original total/target depths of 100m to account for move. |  |  |  |  | 390494.5149 | 8184733.7033 | 9938.9376 | 9592.7117 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD191 | 390660 | 8184769 | 210 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Infill | IMP | RC | 90 | RD | 3 | TRUE | TRUE | Moved 4m N to avoid flagged tree. |  |  |  |  | 390661.3883 | 8184773.2379 | 10084.0681 | 9684.1667 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD189 | 390609 | 8184787 | 200 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Infill | IMP | RC | 90 | RD | 3 | [7 empty] | 390609 | 8184787 | 10030.03 | 9680.2266 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD190 | 390528 | 8184772 | 190 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 110 | Infill | IMP | RC | 110 | RD | 3 | TRUE | TRUE | Moved to avoid stream, large rock wall and boulders. Total/target depth increased to 110 from 90m due to moving 10m back from target on surface. |  |  | RC Waste Samples |  | 390522.3292 | 8184788.1112 | 9947.6428 | 9653.2118 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD188 | 390593 | 8184856 | 201 | 289 | 50 | FALSE | FALSE | 10 | FALSE | 40 | Infill | PLN | RC | 30 | RD | 3 | TRUE | TRUE | [5 empty] | 390598.898 | 8184853.1748 | 9999.0398 | 9739.5847 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD187 | 390623 | 8184867 | 194 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 70 | Infill | IMP | RC | 70 | RD | 3 | TRUE | TRUE | Adjusted to avoid large tree, on suggestion of TOs |  |  | RC Dup Calico |  | 390624.6705 | 8184871.2201 | 10017.5879 | 9765.0092 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD186 | 390709 | 8184879 | 203 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 120 | Infill | EXC | RC | 120 | RD | 3 | [7 empty] | 390709 | 8184879 | 10094.88 | 9799.6806 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP016 | 389328 | 8181835 | 170 | 120 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 389328 | 8181835 | 9773.6057 | 6471.5574 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP015 | 389703 | 8182355 | 170 | 120 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 389703 | 8182355 | 9960.1233 | 7085.134 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP014 | 390243 | 8182798 | 170 | 300 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390243 | 8182798 | 10327.7358 | 7679.2678 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP013 | 390090 | 8183198 | 170 | 120 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390090 | 8183198 | 10053.4011 | 8008.2914 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP012 | 390577 | 8183308 | 170 | 300 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390577 | 8183308 | 10478.6883 | 8270.1031 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP011 | 390194 | 8183728 | 170 | 120 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390194 | 8183728 | 9980.1995 | 8543.5744 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP010 | 390889 | 8183900 | 170 | 300 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390889 | 8183900 | 10582.2655 | 8931.4209 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP009 | 390368 | 8183942 | 170 | 120 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 390368 | 8183942 | 10075.5778 | 8802.4555 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDRD009 | 391285 | 8185866 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 94 | G Vein Res Def | DC | DD | 94 | RD | 3 | [7 empty] | 391285 | 8185866 | 10320.4005 | 10920.3269 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD064 | 391339 | 8185932 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 43 | G Vein Res Def | DC | RC | 43 | RD | 3 | [7 empty] | 391339 | 8185932 | 10350.1346 | 11000.2777 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD062 | 391365 | 8186007 | 174 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 86 | G Vein Res Def | DC | RC | 86 | RD | 3 | [7 empty] | 391365 | 8186007 | 10350.4544 | 11079.679 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD060 | 391381 | 8186086 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 46 | G Vein Res Def | DC | RC | 46 | RD | 3 | [7 empty] | 391381 | 8186086 | 10340.0147 | 11159.6278 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD214 | 391211 | 8185553 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Infill | DC | RC | 90 | RD | 3 | TRUE | TRUE |  | 2025-07-06 |  | RC Waste Samples |  | 391241.3031 | 8185542.9188 | 10383.6679 | 10600.4047 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD219 | 391256 | 8185495 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | PLN | RC | 50 | RD | 3 | [7 empty] | 391256 | 8185495 | 10413.0949 | 10559.8125 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RHYD016 | 391477 | 8186040 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-009b | DC | RC | 100 | HYD | 3 | [7 empty] | 391477 | 8186040 | 10445.7675 | 11147.1799 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RHYD017 | 391477 | 8186038 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 30 | HYD25-009a | DC | RC | 30 | HYD | 3 | [7 empty] | 391477 | 8186038 | 10446.4152 | 11145.2871 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD185 | 390615 | 8184911 | 196 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 60 | Infill | IMP | RC | 60 | RD | 3 | TRUE | TRUE | Moved to shallower slope. Target/total depth increased by 20m from 60m to account for 10m move on surface. |  |  |  |  | 390623.8228 | 8184908.4792 | 10004.7201 | 9799.9975 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_REXP017 | 388905 | 8181321 | 170 | 120 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Southern Extension Exploration | PLN | RC | 90 | EXP | 3 | [7 empty] | 388905 | 8181321 | 9539.7168 | 5848.1156 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RHYD026 | 388809 | 8181261 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-005a | DC | HGD | 100 | HYD | 1 | [7 empty] | 388809 | 8181261 | 9468.2898 | 5760.2425 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RHYD027 | 388799 | 8181244 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 30 | HYD25-005b | DC | HGD | 30 | HYD | 1 | [7 empty] | 388808.5593 | 8181260.0636 | 9468.176 | 5759.2136 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD073 | 391292 | 8185578 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 67 | G Vein Res Def | DC | RC | 67 | RD | 3 | [7 empty] | 391292 | 8185578 | 10420.2883 | 10650.0236 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD070 | 391260 | 8185705 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 35 | G Vein Res Def | DC | RC | 35 | RD | 3 | [7 empty] | 391260 | 8185705 | 10348.8764 | 10759.8569 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD068 | 391278 | 8185784 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 52 | G Vein Res Def | DC | RC | 52 | RD | 3 | [7 empty] | 391278 | 8185784 | 10340.3295 | 10840.4533 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD066 | 391317 | 8185855 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 94 | G Vein Res Def | DC | RC | 94 | RD | 3 | [7 empty] | 391317 | 8185855 | 10354.2482 | 10920.2788 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD075 | 391091 | 8185425 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 120 | G Vein Res Def | DC | RC | 120 | RD | 3 | [7 empty] | 391091 | 8185425 | 10279.6031 | 10440.131 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD173 | 390825 | 8185431 | 187 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | [7 empty] | 390825 | 8185431 | 10025.9113 | 10359.6709 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD074 | 391053 | 8185438 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 196 | G Vein Res Def | DC | RC | 196 | RD | 3 | [5 empty] | RC Dup Calico |  | 391053 | 8185438 | 10239.4292 | 10440.129 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDRD015 | 390879 | 8185455 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 230 | Infill | DC | DD | 230 | RD | 3 | [7 empty] | 390879 | 8185455 | 10069.2463 | 10399.8718 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD223 | 391099 | 8185464 | 177 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | PLN | RC | 180 | RD | 3 | [7 empty] | 391099 | 8185464 | 10274.5451 | 10479.6322 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD222 | 391215 | 8185467 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 70 | Infill | DC | RC | 70 | RD | 3 | [7 empty] | 391215 | 8185467 | 10383.3588 | 10520.0357 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET015 | 390816 | 8185475 | 191 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 85 | Metallurgical Program | DC | DD | 85 | MET | 1 | [7 empty] | 390816 | 8185475 | 10003.145 | 10398.3991 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD221 | 391192 | 8185475 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 120 | Infill | DC | RC | 120 | RD | 3 | [5 empty] | Dup and Waste Sample |  | 391192 | 8185475 | 10359.0004 | 10520.159 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD148 | 390949 | 8185938 | 205 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | IMP | RC | 50 | RD | 3 | [7 empty] | 390949 | 8185938 | 9979.0863 | 10879.6627 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD150 | 390975 | 8185929 | 199 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Infill | PLN | RC | 90 | RD | 3 | [7 empty] | 390975 | 8185929 | 10006.6078 | 10879.5644 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD078 | 391084 | 8185343 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 73 | G Vein Res Def | DC | RC | 73 | RD | 3 | [7 empty] | 391084 | 8185343 | 10299.5321 | 10360.2574 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD176 | 390805 | 8185353 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | PLN | RC | 180 | RD | 3 | [7 empty] | 390805 | 8185353 | 10032.2415 | 10279.3732 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD077 | 391047 | 8185356 | 178 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 133 | G Vein Res Def | DC | RC | 133 | RD | 3 | [7 empty] | 391047 | 8185356 | 10260.3046 | 10360.5792 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD175 | 390782 | 8185361 | 189 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | PLN | RC | 140 | RD | 3 | [7 empty] | 390782 | 8185361 | 10007.8831 | 10279.4965 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD076 | 391009 | 8185368 | 177 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 185 | G Vein Res Def | DC | RC | 185 | RD | 3 | [7 empty] | 391009 | 8185368 | 10220.4546 | 10359.6308 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD174 | 390851 | 8185422 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 210 | Infill | DC | RC | 210 | RD | 3 | [5 empty] | RC Dup Calico |  | 390851 | 8185422 | 10053.4328 | 10359.5726 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD151 | 391008 | 8185918 | 193 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | [5 empty] | RC Waste Samples |  | 391008 | 8185918 | 10041.4019 | 10879.8401 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
[28 empty] | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD046 | 391555 | 8186534 | 173 | 109 | 62 | FALSE | FALSE | 10 | FALSE | 102 | G Vein Res Def | DC | RC | 102 | RD | 3 | [7 empty] | 391555 | 8186534 | 10359.6168 | 11639.9721 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD104 | 391284 | 8186542 | 190 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | PLN | RC | 180 | RD | 3 | [7 empty] | 391284 | 8186542 | 10100.5453 | 11559.7857 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD103 | 391333 | 8186568 | 209 | 69 | 50 | FALSE | FALSE | 10 | FALSE | 50 | Infill | PLN | RC | 50 | RD | 3 | TRUE | TRUE | [5 empty] | 391323.6925 | 8186544.447 | 10137.3187 | 11574.9552 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD205 | 391395 | 8186546 | 203 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | IMP | RC | 50 | RD | 3 | [7 empty] | 391395 | 8186546 | 10204.303 | 11599.5164 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD045 | 391518 | 8186547 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 172 | G Vein Res Def | DC | RC | 172 | RD | 3 | [7 empty] | 391518 | 8186547 | 10320.3893 | 11640.2939 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD204 | 391495 | 8186554 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | PLN | RC | 40 | RD | 3 | [7 empty] | 391495 | 8186554 | 10296.3548 | 11639.4708 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD208 | 391419 | 8186496 | 181 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | PLN | RC | 40 | RD | 3 | [7 empty] | 391419 | 8186496 | 10243.2087 | 11559.9671 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD209 | 391489 | 8186482 | 176 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 70 | Infill | PLN | RC | 70 | RD | 3 | [7 empty] | 391489 | 8186482 | 10313.9919 | 11569.3853 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD210 | 391485 | 8186473 | 177 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 70 | Infill | PLN | RC | 70 | RD | 3 | [7 empty] | 391485 | 8186473 | 10313.1207 | 11559.5721 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD211 | 391377 | 8186468 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 85 | Infill | PLN | RC | 85 | RD | 3 | TRUE | TRUE |  |  |  | RC Dup Calico |  | 391390.2917 | 8186463.4551 | 10226.5774 | 11519.8693 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD141 | 390976 | 8186014 | 206 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | IMP | RC | 50 | RD | 3 | [7 empty] | 390976 | 8186014 | 9980.0287 | 10960.3343 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD144 | 390980 | 8185969 | 201 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Infill | PLN | RC | 80 | RD | 3 | [7 empty] | 390980 | 8185969 | 9998.3867 | 10919.0405 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD142 | 390999 | 8186005 | 196 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 100 | Infill | PLN | RC | 100 | RD | 3 | [7 empty] | 390999 | 8186005 | 10004.7109 | 10959.2646 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD139 | 391002 | 8186047 | 203 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 70 | Infill | IMP | RC | 70 | RD | 3 | [7 empty] | 391002 | 8186047 | 9993.9493 | 10999.9859 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD198 | 391439 | 8186605 | 202 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | IMP | RC | 40 | RD | 3 | [7 empty] | 391439 | 8186605 | 10226.8397 | 11669.604 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD043 | 391600 | 8186603 | 173 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 57 | G Vein Res Def | DC | RC | 57 | RD | 3 | TRUE | TRUE | [5 empty] | 391595.6269 | 8186611.4997 | 10372.9704 | 11726.4759 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD100 | 391307 | 8186618 | 206 | 289 | 58 | FALSE | FALSE | 10 | FALSE | 190 | Infill | PLN | RC | 190 | RD | 3 | TRUE | TRUE | [5 empty] | 391310.8861 | 8186614.4328 | 10102.535 | 11637.0443 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD197 | 391557 | 8186618 | 179 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | IMP | RC | 30 | RD | 3 | [7 empty] | 391557 | 8186618 | 10334.308 | 11720.1194 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD196 | 391524 | 8186629 | 188 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 20 | Infill | IMP | RC | 20 | RD | 3 | [7 empty] | 391524 | 8186629 | 10299.5138 | 11719.8436 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD099 | 391379 | 8186636 | 217 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | PLN | RC | 50 | RD | 3 | [7 empty] | 391379 | 8186636 | 10160.0156 | 11679.5133 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD195 | 391493 | 8186640 | 192 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 20 | Infill | IMP | RC | 20 | RD | 3 | [7 empty] | 391493 | 8186640 | 10266.6126 | 11720.2156 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD098 | 391356 | 8186644 | 217 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | PLN | RC | 50 | RD | 3 | [7 empty] | 391356 | 8186644 | 10135.6572 | 11679.6366 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD044 | 391480 | 8186560 | 180 | 109 | 62 | FALSE | FALSE | 10 | FALSE | 250 | G Vein Res Def | DC | RC | 250 | RD | 3 | [7 empty] | 391480 | 8186560 | 10280.2154 | 11640.2919 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD203 | 391457 | 8186568 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | DC | RC | 30 | RD | 3 | [5 empty] | RC Dup Calico |  | 391457 | 8186568 | 10255.857 | 11640.4152 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD102 | 391302 | 8186578 | 201 | 99 | 70 | FALSE | FALSE | 10 | FALSE | 40 | Infill | PLN | RC | 40 | RD | 3 | TRUE | TRUE | [5 empty] | 391309.1435 | 8186571.1538 | 10114.9008 | 11595.5197 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD201 | 391549 | 8186578 | 175 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | PLN | RC | 40 | RD | 3 | [7 empty] | 391549 | 8186578 | 10339.6897 | 11679.6718 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD202 | 391427 | 8186578 | 195 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | IMP | RC | 40 | RD | 3 | [7 empty] | 391427 | 8186578 | 10224.226 | 11640.1646 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD200 | 391512 | 8186591 | 179 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | PLN | RC | 30 | RD | 3 | [7 empty] | 391512 | 8186591 | 10300.4623 | 11679.9936 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD101 | 391364 | 8186599 | 223 | 94 | 50 | FALSE | FALSE | 10 | FALSE | 70 | Infill | IMP | RC | 60 | RD | 3 | TRUE | TRUE | [5 empty] | 391349.8118 | 8186593.0973 | 10146.2843 | 11629.4571 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD199 | 391475 | 8186604 | 185 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | PLN | RC | 30 | RD | 3 | [7 empty] | 391475 | 8186604 | 10261.2348 | 11680.3154 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD006 | 391803 | 8186941 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 30 | HYD25-006a | DC | RC | 30 | HYD | 1 | [7 empty] | 391803 | 8186941 | 10462.5313 | 12105.4764 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD007 | 391802 | 8186938 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-006b | DC | RC | 100 | HYD | 1 | [7 empty] | 391802 | 8186938 | 10462.5564 | 12102.3133 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD193 | 391557 | 8186702 | 203 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | IMP | RC | 30 | RD | 3 | [7 empty] | 391557 | 8186702 | 10307.1063 | 11799.619 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD194 | 391518 | 8186674 | 201 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | IMP | RC | 30 | RD | 3 | [7 empty] | 391518 | 8186674 | 10279.263 | 11760.4897 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RHYD018 | 390598 | 8185988 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-004 | DC | RC | 100 | HYD | 3 | [7 empty] | 390598 | 8185988 | 9630.7 | 10813.3197 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD147 | 391017 | 8185957 | 193 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [5 empty] | RC Waste Samples |  | 391017 | 8185957 | 10037.2904 | 10919.6651 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD138 | 391019 | 8186062 | 198 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Infill | IMP | RC | 110 | RD | 3 | [7 empty] | 391019 | 8186062 | 10005.1811 | 11019.6873 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD135 | 391019 | 8186083 | 202 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Infill | IMP | RC | 80 | RD | 3 | [7 empty] | 391019 | 8186083 | 9998.3807 | 11039.5622 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD097 | 391333 | 8186652 | 216 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 230 | Infill | PLN | RC | 230 | RD | 3 | [5 empty] | RC Dup Calico |  | 391333 | 8186652 | 10111.2988 | 11679.7599 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD096 | 391396 | 8186672 | 206 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | PLN | RC | 30 | RD | 3 | [7 empty] | 391396 | 8186672 | 10164.4469 | 11719.0897 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET003 | 391282 | 8186674 | 206 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Metallurgical Program | DC | DD | 80 | MET | 1 | [7 empty] | 391282 | 8186674 | 10055.9069 | 11684.066 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET002 | 391281 | 8186674 | 205 | 289 | 68 | FALSE | FALSE | 10 | FALSE | 130 | Metallurgical Program | DC | DD | 130 | MET | 1 | [7 empty] | 391281 | 8186674 | 10054.9605 | 11683.7421 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD095 | 391371 | 8186681 | 207 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | PLN | RC | 30 | RD | 3 | [7 empty] | 391371 | 8186681 | 10137.8718 | 11719.5118 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD094 | 391343 | 8186691 | 207 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 30 | Infill | PLN | RC | 30 | RD | 3 | [7 empty] | 391343 | 8186691 | 10108.1337 | 11719.9088 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD042 | 391628 | 8186715 | 190 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 85 | G Vein Res Def | DC | RC | 85 | RD | 3 | [7 empty] | 391628 | 8186715 | 10370.0926 | 11834.9144 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD206 | 391417 | 8186539 | 190 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | IMP | RC | 40 | RD | 3 | [7 empty] | 391417 | 8186539 | 10227.3911 | 11600.0157 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD121 | 391097 | 8186226 | 199 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Infill | IMP | RC | 110 | RD | 3 | [5 empty] | RC Waste Samples |  | 391097 | 8186226 | 10025.8941 | 11200.1596 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD145 | 391105 | 8185969 | 184 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 160 | Infill | DC | RC | 160 | RD | 3 |  |  |  |  | 2025-08-02 |  |  | 391105 | 8185969 | 10116.6897 | 10959.5192 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD118 | 391115 | 8186262 | 203 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 100 | Infill | PLN | RC | 100 | RD | 3 | [5 empty] | RC Waste Samples |  | 391115 | 8186262 | 10031.2719 | 11240.0598 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD125 | 391124 | 8186174 | 187 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [7 empty] | 391124 | 8186174 | 10068.2867 | 11159.6889 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD143 | 391127 | 8186004 | 181 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | DC | RC | 180 | RD | 3 |  |  |  |  | 2025-08-09 |  |  | 391127 | 8186004 | 10126.177 | 10999.7683 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD122 | 391128 | 8186215 | 190 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 120 | Infill | PLN | RC | 120 | RD | 3 | [7 empty] | 391128 | 8186215 | 10058.7954 | 11199.7876 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD146 | 391132 | 8185960 | 181 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 200 | Infill | DC | RC | 200 | RD | 3 |  |  |  |  | 2025-08-07 |  |  | 391132 | 8185960 | 10145.1576 | 10959.7448 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD116 | 391142 | 8186295 | 198 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Infill | PLN | RC | 110 | RD | 3 | [7 empty] | 391142 | 8186295 | 10046.139 | 11280.0351 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET009 | 391041 | 8185914 | 184 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 105 | Metallurgical Program | DC | DD | 105 | MET | 1 |  |  |  |  | 2025-07-07 |  |  | 391041 | 8185914 | 10073.9292 | 10886.7408 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDGT007 | 391045 | 8185915 | 184 | 110 | 65 | FALSE | FALSE | 10 | FALSE | 120 | Geotechnical Drilling | DC | DD | 120 | GT | 1 | [7 empty] | 391045 | 8185915 | 10077.3911 | 10888.9826 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD132 | 391050 | 8186115 | 197 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 120 | Infill | IMP | RC | 120 | RD | 3 | [5 empty] | RC Waste Samples |  | 391050 | 8186115 | 10017.3573 | 11079.8865 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD128 | 391061 | 8186153 | 201 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 110 | Infill | IMP | RC | 110 | RD | 3 | [7 empty] | 391061 | 8186153 | 10015.4624 | 11119.4127 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DMET008 | 391073 | 8186058 | 188 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 60 | Metallurgical Program | DC | DD | 60 | MET | 1 |  |  |  |  | 2025-07-03 |  |  | 391073 | 8186058 | 10057.5833 | 11033.3884 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD124 | 391076 | 8186190 | 195 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Infill | PLN | RC | 110 | RD | 3 | [5 empty] | RC Waste Samples |  | 391076 | 8186190 | 10017.6771 | 11159.2879 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_DDRD014 | 391087 | 8186145 | 190 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 140 | Infill | R41 | DD | 140 | RD | 3 | [7 empty] | 391087 | 8186145 | 10042.6601 | 11120.2609 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD149 | 391093 | 8185930 | 182 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 170 | Infill | DC | RC | 170 | RD | 3 | [7 empty] | 391093 | 8185930 | 10117.962 | 10918.7227 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514
SF25_RCRD079 | 390992 | 8185290 | 177 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 168 | G Vein Res Def | DC | RC | 168 | RD | 3 | [7 empty] | 390992 | 8185290 | 10229.6241 | 10280.3046 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET016 | 390759 | 8185304 | 190 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 110 | Metallurgical Program | DC | DD | 110 | MET | 1 | [7 empty] | 390759 | 8185304 | 10004.5737 | 10218.1023 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDGT009 | 390759 | 8185305 | 189 | 110 | 80 | FALSE | FALSE | 10 | FALSE | 100 | Geotechnical Drilling | DC | DD | 100 | GT | 1 | [7 empty] | 390759 | 8185305 | 10004.2498 | 10219.0487 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD177 | 390781 | 8185320 | 187 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | PLN | RC | 170 | RD | 3 | [7 empty] | 390781 | 8185320 | 10020.2137 | 10240.3693 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RHYD025 | 391024 | 8184470 | 170 | 0 | 90 | FALSE | FALSE | 10 | FALSE | 100 | HYD25-015 | DC | RC | 100 | HYD | 1 | [7 empty] | 391030.6225 | 8184464.3235 | 10533.5558 | 9511.3718 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD112 | 391100 | 8186352 | 206 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | EXC | RC | 50 | RD | 3 | [5 empty] | RC Waste Samples
SF25_RCRD114 | 391073 | 8186319 | 203 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 60 | Infill | EXC | RC | 60 | RD | 3 | [5 empty] | RC Dup Calico
SF25_RCRD117 | 391059 | 8186281 | 205 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | EXC | RC | 50 | RD | 3 | [5 empty] | RC Waste Samples
SF25_RCRD228 | 390974 | 8185169 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 100 | Infill | PLN | RC | 100 | RD | 3 | [7 empty] | 390974 | 8185169 | 10251.7718 | 10159.9584 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDGT010 | 390935 | 8185181 | 183 | 240 | 60 | FALSE | FALSE | 10 | FALSE | 110 | Geotechnical Drilling | DC | DD | 110 | GT | 1 | [7 empty] | 390939.415 | 8185179.029 | 10215.7921 | 10158.2504 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD227 | 391020 | 8185195 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [7 empty] | 391020 | 8185195 | 10286.8877 | 10199.4616 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD226 | 391002 | 8185201 | 186 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 85 | Infill | PLN | RC | 85 | RD | 3 | [7 empty] | 391002 | 8185201 | 10267.9091 | 10199.3112 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD180 | 390736 | 8185208 | 193 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [7 empty] | 390736 | 8185208 | 10013.8936 | 10119.7975 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD179 | 390754 | 8185244 | 190 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | PLN | RC | 170 | RD | 3 | [7 empty] | 390754 | 8185244 | 10019.2713 | 10159.6977 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD080 | 391030 | 8185277 | 178 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 93 | G Vein Res Def | DC | RC | 93 | RD | 3 | [7 empty] | 391030 | 8185277 | 10269.798 | 10280.3066 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD178 | 390763 | 8185283 | 189 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | [7 empty] | 390763 | 8185283 | 10015.1598 | 10199.5227 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD129 | 390963 | 8186145 | 210 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Infill | EXC | RC | 90 | RD | 3
SF25_RCRD130 | 391011 | 8186129 | 212 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 40 | Infill | PLN | RC | 40 | RD | 3 | [5 empty] | RC Waste Samples
SF25_RCRD134 | 390965 | 8186102 | 220 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | EXC | RC | 50 | RD | 3 | [5 empty] | RC Waste Samples
SF25_RCRD137 | 390956 | 8186063 | 219 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 40 | Infill | EXC | RC | 40 | RD | 3 | [5 empty] | RC Waste Samples
SF25_RCRD156 | 390944 | 8185813 | 187 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 60 | Infill | EXC | RC | 60 | RD | 3 | [5 empty] | RC Waste Samples
SF25_RCRD225 | 391145 | 8185449 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 100 | Infill | PLN | RC | 100 | RD | 3 | [5 empty] | RC Waste Samples |  | 391145 | 8185449 | 10322.938 | 10480.332 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD216 | 391172 | 8185524 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 200 | Infill | PLN | RC | 200 | RD | 3 | [5 empty] | RC Waste Samples |  | 391172 | 8185524 | 10324.2043 | 10560.0572 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD169 | 390897 | 8185533 | 180 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 200 | Infill | PLN | RC | 200 | RD | 3 | [7 empty] | 390897 | 8185533 | 10061.0232 | 10479.5218 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD215 | 391092 | 8185551 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 250 | Infill | PLN | RC | 250 | RD | 3 | [7 empty] | 391092 | 8185551 | 10239.747 | 10559.7042 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDRD018 | 391193 | 8185560 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 130 | Infill | DC | DD | 130 | RD | 3 | [7 empty] | 391193 | 8185560 | 10332.4213 | 10600.9288 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD213 | 391169 | 8185567 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | PLN | RC | 170 | RD | 3 | [7 empty] | 391169 | 8185567 | 10307.4403 | 10599.7819 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD168 | 390918 | 8185568 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 210 | Infill | DC | RC | 210 | RD | 3 | [5 empty] | RC Dup Calico |  | 390918 | 8185568 | 10069.5641 | 10519.4471 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD212 | 391145 | 8185575 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 210 | Infill | DC | RC | 210 | RD | 3 | [5 empty] | RC Dup Calico |  | 391145 | 8185575 | 10282.1355 | 10599.5814 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET014 | 390818 | 8185477 | 190 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 85 | Metallurgical Program | DC | DD | 85 | MET | 1 | [7 empty] | 390818 | 8185477 | 10004.3902 | 10400.9396 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD172 | 391171 | 8185482 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 160 | Infill | PLN | RC | 160 | RD | 3 | [7 empty] | 391171 | 8185482 | 10336.8587 | 10519.9835 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD220 | 391148 | 8185490 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 200 | Infill | DC | RC | 200 | RD | 3 | [5 empty] | RC Waste Samples |  | 391146.6384 | 8185489.4811 | 10311.3796 | 10519.1748 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD218 | 391127 | 8185497 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 250 | Infill | PLN | RC | 250 | RD | 3 | [5 empty] | RC Waste Samples |  | 391127 | 8185497 | 10290.3586 | 10519.9314 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD171 | 390864 | 8185502 | 185 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | PLN | RC | 170 | RD | 3 | [7 empty] | 390864 | 8185502 | 10039.8299 | 10439.4963 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD217 | 391212 | 8185510 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | PLN | RC | 140 | RD | 3 | TRUE | TRUE |  | 2025-07-06 |  |  |  | 391221.1083 | 8185507.2586 | 10376.1029 | 10560.1154 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD170 | 390842 | 8185510 | 188 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 130 | Infill | PLN | RC | 130 | RD | 3 | [7 empty] | 390842 | 8185510 | 10016.418 | 10439.9435 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD224 | 391124 | 8185456 | 176 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 140 | Infill | PLN | RC | 140 | RD | 3 | [7 empty] | 391124 | 8185456 | 10300.7963 | 10480.1565 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET011 | 390891 | 8185666 | 183 | 299 | 60 | FALSE | FALSE | 10 | FALSE | 100 | Metallurgical Program | DC | DD | 100 | MET | 1 | [7 empty] | 390874.9032 | 8185646.8738 | 10003.2346 | 10580.1391 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD163 | 390905 | 8185657 | 182 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 130 | Infill | PLN | RC | 130 | RD | 3 | [7 empty] | 390912.5727 | 8185651.9926 | 10037.2283 | 10597.1822 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD161 | 390921 | 8185694 | 178 | 329 | 55 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [7 empty] | 390913.2946 | 8185656.6849 | 10036.392 | 10601.8569 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD162 | 390952 | 8185684 | 176 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 200 | Infill | DC | RC | 200 | RD | 3 | TRUE | TRUE | moved 10m south out of creek | 2025-07-18 |  |  |  | 390956.4567 | 8185672.6215 | 10072.0809 | 10630.9168 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD160 | 390997 | 8185710 | 177 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 230 | Infill | DC | RC | 230 | RD | 3 | [5 empty] | RC Dup Calico |  | 390997 | 8185710 | 10098.3478 | 10679.4218 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDRD011 | 391221 | 8185719 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 110 | G Vein Res Def | DC | DD | 110 | RD | 3 | [7 empty] | 391221 | 8185719 | 10307.4323 | 10760.4775 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD069 | 391182 | 8185732 | 175 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 160 | G Vein Res Def | DC | RC | 160 | RD | 3 | [7 empty] | 391182 | 8185732 | 10266.312 | 10760.1516 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD159 | 391002 | 8185751 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 210 | Infill | PLN | RC | 210 | RD | 3 | [7 empty] | 391002 | 8185751 | 10089.8029 | 10719.8444 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD167 | 390893 | 8185577 | 182 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 170 | Infill | PLN | RC | 170 | RD | 3 | [7 empty] | 390893 | 8185577 | 10042.989 | 10519.8692 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD166 | 390870 | 8185585 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 130 | Infill | PLN | RC | 130 | RD | 3 | [7 empty] | 390870 | 8185585 | 10018.6306 | 10519.9925 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET012 | 390865 | 8185598 | 186 | 289 | 50 | FALSE | FALSE | 10 | FALSE | 90 | Metallurgical Program | DC | DD | 90 | MET | 1 | [7 empty] | 390865 | 8185598 | 10009.6887 | 10530.6769 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET013 | 390866 | 8185598 | 186 | 289 | 50 | FALSE | FALSE | 10 | FALSE | 90 | Metallurgical Program | DC | DD | 90 | MET | 1 | [7 empty] | 390866 | 8185598 | 10010.6351 | 10531.0007 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD165 | 390936 | 8185605 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 220 | Infill | PLN | RC | 220 | RD | 3 | [7 empty] | 390936 | 8185605 | 10074.618 | 10560.2937 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD072 | 391226 | 8185632 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 46 | G Vein Res Def | DC | RC | 46 | RD | 3 | [7 empty] | 391226 | 8185632 | 10340.3376 | 10679.7577 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD071 | 391188 | 8185645 | 174 | 109 | 60 | FALSE | FALSE | 10 | FALSE | 119 | G Vein Res Def | DC | RC | 119 | RD | 3 | [7 empty] | 391188 | 8185645 | 10300.1637 | 10679.7557 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD164 | 390936 | 8185646 | 178 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 190 | Infill | PLN | RC | 190 | RD | 3 | [7 empty] | 390936 | 8185646 | 10061.341 | 10599.0971 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
[28 empty] | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDRD019 | 390948 | 8184925 | 184 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 130 | Infill | DC | DD | 130 | RD | 3 | [7 empty] | 390948 | 8184925 | 10306.1792 | 9920.6114 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD184 | 390692 | 8184927 | 191 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 90 | Infill | PLN | RC | 90 | RD | 3 | [7 empty] | 390692 | 8184927 | 10063.247 | 9839.6039 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD235 | 390901 | 8184940 | 188 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Infill | PLN | RC | 50 | RD | 3 | [7 empty] | 390901 | 8184940 | 10256.8398 | 9919.5877 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD183 | 390620 | 8184952 | 195 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 40 | Infill | IMP | RC | 40 | RD | 3 | [7 empty] | 390620 | 8184952 | 9987.0087 | 9839.9487 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD234 | 390866 | 8184952 | 195 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Infill | PLN | RC | 90 | RD | 3 | TRUE | TRUE | [5 empty] | 390875.0938 | 8184959.1015 | 10226.1359 | 9929.2766 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD233 | 390951 | 8184965 | 184 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 140 | Infill | DC | RC | 140 | RD | 3 | [5 empty] | RC Dup Calico |  | 390951 | 8184965 | 10296.0653 | 9959.4398 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET024 | 390666 | 8184993 | 185 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 100 | Metallurgical Program | DC | DD | 100 | MET | 1 | [7 empty] | 390666 | 8184993 | 10017.2672 | 9893.6483 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD158 | 390975 | 8185759 | 179 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 160 | Infill | DC | RC | 160 | RD | 3 | [7 empty] | 390989.7165 | 8185755.0915 | 10076.8525 | 10719.7389 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD157 | 391003 | 8185793 | 179 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | DC | RC | 180 | RD | 3 | [5 empty] | RC Dup Calico |  | 391003 | 8185793 | 10077.1485 | 10759.918 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET010 | 390948 | 8185778 | 179 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Metallurgical Program | DC | DD | 100 | MET | 1 | [7 empty] | 390992.4728 | 8185796.9611 | 10065.9025 | 10760.2579 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD154 | 391058 | 8185858 | 180 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 180 | Infill | PLN | RC | 180 | RD | 3 | [7 empty] | 391058 | 8185858 | 10108.1529 | 10839.2462 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD155 | 390941 | 8185856 | 195 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 70 | Infill | PLN | RC | 70 | RD | 3 | [7 empty] | 390945.8101 | 8185862.6139 | 10000.4795 | 10807.2825 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDGT008 | 390945 | 8185870 | 186 | 290 | 70 | FALSE | FALSE | 10 | FALSE | 130 | Geotechnical Drilling | DC | DD | 130 | GT | 1 | [7 empty] | 390951.3603 | 8185865.9036 | 10004.6671 | 10812.1932 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD153 | 390992 | 8185881 | 188 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 150 | Infill | PLN | RC | 150 | RD | 3 | [5 empty] | RC Waste Samples |  | 390992 | 8185881 | 10038.2408 | 10839.6412 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD152 | 390955 | 8185893 | 198 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Infill | IMP | RC | 80 | RD | 3 | [7 empty] | 390955 | 8185893 | 9999.3372 | 10839.0166 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD232 | 390927 | 8185058 | 187 | 279 | 50 | FALSE | FALSE | 10 | FALSE | 100 | Infill | PLN | RC | 100 | RD | 3 | TRUE | FALSE |  |  |  | RC Waste Samples |  | 390934.981 | 8185065.3952 | 10248.3936 | 10049.2689 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET017 | 390903 | 8185065 | 187 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Metallurgical Program | DC | DD | 50 | MET | 1 |  |  |  |  | 2025-08-06 |  |  | 390903 | 8185065 | 10218.254 | 10038.5384 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDGT011 | 390633 | 8185075 | 183 | 310 | 60 | FALSE | FALSE | 10 | FALSE | 130 | Geotechnical Drilling | DC | DD | 130 | GT | 1 | [7 empty] | 390625.5389 | 8185068.0336 | 9954.6758 | 9951.5593 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD231 | 390987 | 8185080 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 125 | Infill | PLN | RC | 125 | RD | 3 | [7 empty] | 390987 | 8185080 | 10292.8962 | 10079.9364 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD182 | 390718 | 8185088 | 183 | 289 | 55 | FALSE | FALSE | 10 | FALSE | 200 | Infill | DC | RC | 200 | RD | 3 | TRUE | TRUE |  |  |  | RC Dup Calico |  | 390734.5322 | 8185089.9076 | 10050.7462 | 10007.5567 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD230 | 390926 | 8185101 | 185 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Infill | PLN | RC | 90 | RD | 3 | [7 empty] | 390926 | 8185101 | 10228.3639 | 10080.0577 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD229 | 390997 | 8185161 | 185 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 150 | Infill | DC | RC | 150 | RD | 3 | [5 empty] | RC Dup Calico |  | 390997 | 8185161 | 10276.1302 | 10159.8351 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_RCRD181 | 390621 | 8185163 | 200 | 109 | 55 | FALSE | FALSE | 10 | FALSE | 80 | Infill | PLN | RC | 80 | RD | 3 | [7 empty] | 390621 | 8185163 | 9919.6271 | 10039.968 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDRD016 | 390709 | 8185004 | 185 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 180 | Infill | R41 | DD | 180 | RD | 3 |  |  |  |  | 2025-08-07 |  |  | 390709 | 8185004 | 10054.4013 | 9917.9836 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET023 | 390676 | 8185037 | 183 | 289 | 60 | FALSE | FALSE | 9 | FALSE | 120 | Metallurgical Program | DC | DD | 120 | MET | 1 | [7 empty] | 390676 | 8185037 | 10012.483 | 9938.5292 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET022 | 390673 | 8185038 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 115 | Metallurgical Program | DC | DD | 115 | MET | 1 | [7 empty] | 390673 | 8185038 | 10009.3199 | 9938.5042 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET020 | 390654 | 8185044 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Metallurgical Program | DC | DD | 90 | MET | 1 | [7 empty] | 390654 | 8185044 | 9989.3948 | 9938.0299 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET021 | 390656 | 8185044 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 90 | Metallurgical Program | DC | DD | 90 | MET | 1 | [7 empty] | 390656 | 8185044 | 9991.2877 | 9938.6776 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DDGT012 | 390654 | 8185045 | 183 | 150 | 60 | FALSE | FALSE | 10 | FALSE | 70 | Geotechnical Drilling | DC | DD | 70 | GT | 1 | [7 empty] | 390654 | 8185045 | 9989.071 | 9938.9764 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET019 | 390950 | 8185049 | 184 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Metallurgical Program | DC | DD | 50 | MET | 1 |  |  |  |  | 2025-08-06 |  |  | 390950 | 8185049 | 10267.9172 | 10038.6156 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET018 | 390638 | 8185050 | 183 | 289 | 60 | FALSE | FALSE | 10 | FALSE | 50 | Metallurgical Program | DC | DD | 50 | MET | 1 | [7 empty] | 390638 | 8185050 | 9972.3091 | 9938.5272 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356
SF25_DMET029 | 189.2 | 50 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Drilled | Half | New | 391068.405 | 8186059.788 | Part2_1 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET030 | 190.4 | 35 | 55 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Drilled | Half | New | 391069.2 | 8186106.7 | Part2_1 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET032 | 192.3 | 30 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Ready to Drill | Half | Replace or share with Infill RC | 391008.7 | 8185916.1 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET035 | 206.4 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Ready to Drill | Half | New | 391281.4 | 8186710.3 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET036 | 205.4 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Drilled | Half | New | 391274.8 | 8186670.4 | Part2_1 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET037 | 199.6 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Ready to Drill | Half | New | 391265.9 | 8186631.3 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET038 | 197.9 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Waiting for Approval | Half | New | 391231.7 | 8186558.3 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET039 | 196.2 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Waiting for Approval | Half | New | 391212.2 | 8186522.6 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET040 | 189.9 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Waiting for Approval | Half | New | 391020.008 | 8185956.031 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET051 | 191.9 | 30 | 60 | 288.5 | Oxide Target Twin 32 |  | Ready to Drill | Full Core | Twin | 391011.5 | 8185915.1 |  | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET053 | 205.6 | 50 | 60 | 288.5 | Oxide Target Twin 36 and extend |  | Drilled | Full Core | Twin | 391273.3 | 8186670.8 | Part2_1 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET055 | 189.2 | 85 | 55 | 288.5 | Twin 006 |  | Drilled | Full Core | 2024 | 391184.9 | 8186326 | Part2_1 | 6 | 23443 | M 8000268 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 9:00 | 47989 | 24:00 | 32639 | 0:00 | M 80/268 | 597.2 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.16432 | 0.00050514 | [6 empty] | M 80/268
SF25_DMET031 | 176.6 | 30 | 55 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Drilled | Half | New | 390650.329 | 8185046.065 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET033 | 197.7 | 35 | 60 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Drilled | Half | New | 390951.199 | 8185864.764 | Part2_1 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET034 | 189.6 | 40 | 55 | 288.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Ready to Drill | Half | Replace or share with Infill RC | 390989.2 | 8185880.3 |  | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET041 | 175.9 | 40 | 60 | 108.5 | Oxide Target | Need oxide short hole 30m, spread spatially rather than twin | Waiting for Approval | Half | New | 391170.073 | 8185480.07 |  | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET042 | 185 | 120 | 55 | 288.5 | Dolerite Target |  | Drilled | Half | New | 390939.055 | 8185059.703 | Part2_1 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET043 | 184.8 | 100 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390929.3 | 8185098 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET044 | 185.4 | 140 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390993.6 | 8185160.5 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET045 | 191.4 | 155 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390738.3 | 8185205.6 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET046 | 189.6 | 165 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390757.2 | 8185241.2 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET047 | 188.9 | 160 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390765.1 | 8185281 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET048 | 187.2 | 160 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390778.5 | 8185318.6 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET049 | 188.4 | 140 | 60 | 288.5 | Dolerite Target |  | Drilled | Half | Replace or share with Infill RC | 390782.9 | 8185359.1 | Part2_2 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET050 | 185 | 120 | 55 | 288.5 | Oxide Target Twin 42 |  | Drilled | Full Core | Twin | 390936.68 | 8185060.812 | Part2_1 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET052 | 197.3 | 40 | 60 | 288.5 | Oxide Target Twin 33 |  | Drilled | Full Core | Twin | 390952.07 | 8185864.721 | Part2_1 | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269
SF25_DMET054 | 174.7 | 40 | 60 | 108.5 | Oxide Target G Vein |  | Waiting for Approval | Half | New | 391186.09 | 8185519.066 |  | 7 | 23444 | M 8000269 | MINING LEASE | SURVEYED | LIVE | 1 | SPEEWAH MINING PTY LTD | PO BOX 40,DUNCRAIG,WA,6023,AUSTRALIA | [16 empty] | 32303 | 10:30 | 47989 | 24:00 | 32639 | 0:00 | M 80/269 | 749 | HA. |  | 45551 | 308/1993 | SPEEWAH MINING PTY LTD | 0.15434 | 0.00063356 | [6 empty] | M 80/269